## Project Tracking
CE Service Number | Account | Project | Priority | Chipset | Software Product | EVT Date | DVT Date | PVT Date | TA Date | Camera Projects CCB overall Score | Volume Projection | Account Rating | Enter Date | Exit Date | Assignment (CE) | Support Type | Level | Status | WE | H | Weeks | Schedule Note | Request | Service # | Basic tuning | IQ fine tuning | ISP/CPP | PDAF TOF | AWB Color | AEC | DualCam | ADRC | Misc | Service Details
00000928 | Yulong | 3705A | SB3 | SDM450 | SDM450.LA.3.2.1 | 2018-07-22 | 2018-09-04 | 2018-10-28 | 2019-02-13 | 22 | Mid | 2-Platinum | 2018-12-15 | 2019-02-13 | Guangjun He | DRI | Low | in pipeline
00000929 | Huaqin | A6005 | SB4 | APQ8009 | MSM8909.LA.3.0.1 | 2018-02-25 | 2018-03-29 | 2018-06-09 | 2018-09-21 | 12 |  | 2-Platinum | 2018-07-23 | 2018-09-21 | Zhiqiang jin | DRI | Low | Finished | [5 empty] | 0
00000930 | OPPO | AD015 | SB4 | SDM660 | SDM660.LA.2.1 | 2017-12-09 | 2018-01-20 | 2018-02-08 | 2018-09-15 | 22 | High | 1-Diamond | 2018-07-17 | 2018-07-31 | Hongliang Jing | DRI | Low | Finished |  |  |  | (4/19/2018) Leverage project [03.27]name change from BD007 |  | 0
00000931 | OPPO | AD055 | SB4 | SDM845 | SDM845.LA.1.0.1.c4 | 2018-06-25 | 2018-07-25 | 2018-08-25 | 2018-10-29 |  |  | 1-Diamond | 2018-07-25 | 2018-10-29 | Hongliang Jing | DRI | High | Finished |  |  |  | (6/1/2018)
00000931 | OPPO | AD055 | SB4 | SDM845 | SDM845.LA.1.0.1.c4 | 2018-06-25 | 2018-07-25 | 2018-08-25 | 2018-10-29 |  |  | 1-Diamond | 2018-07-25 | 2018-10-29 | Hongliang Jing | DRI | High | Finished |  |  |  | (6/1/2018)
00000932 | OPPO | AD059_India | SB4 | SDM710 | SDM710.LA.1.0.c3 | 2018-07-30 | 2018-08-30 | 2018-09-25 | 2018-11-28 | 22 | High | 1-Diamond | 2018-09-29 | 2018-10-31 | Hongliang Jing | DRI | Low | Finished
00000932 | OPPO | AD059_India | SB4 | SDM710 | SDM710.LA.1.0.c3 | 2018-07-30 | 2018-08-30 | 2018-09-25 | 2018-11-28 | 22 | High | 1-Diamond | 2018-09-29 | 2018-10-31 | Hongliang Jing | DRI | Low | Finished
00000933 | OPPO | AD066 | SB4 | SDM710 | SDM710.LA.2.0 | 2018-11-23 | 2018-12-28 | 2019-02-01 | 2019-01-31 | 22 | High | 1-Diamond | 2018-11-21 | 2019-01-31 | Hongliang Jing | DRI | Low | ongoing |  |  |  | [11/05/2018] Assigned to DRI, case support
00000933 | GuangDong OPPO Mobile Telecommunications Corp. Ltd. | AD066 | SB4 | SDM710 | SDM710.LA.2.0 | 2018-11-23 | 2018-12-28 | 2019-02-01 | 2019-01-31 | 22 | High | 1-Diamond | 2018-11-21 | 2019-01-31 | Jun Yang | DRI | Low | ongoing |  |  |  | [11/05/2018] Assigned to DRI, case support
00000934 | OPPO | BD186 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-11-15 | 2018-12-15 | 2019-01-15 | 2019-03-31 | 20 | High | 1-Diamond | 2019-01-30 | 2019-03-31 | Hongliang Jing | DRI | High | in pipeline |  |  |  | Hongliang Jing/Jun Yang/Fan(Shared)
00000934 | OPPO | BD186 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-11-15 | 2018-12-15 | 2019-01-15 | 2019-03-31 | 20 | High | 1-Diamond | 2019-01-30 | 2019-03-31 | Jun Yang | DRI | High | in pipeline |  |  |  | Hongliang Jing/Jun Yang/Fan(Shared)
00000934 | OPPO | BD186 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-11-15 | 2018-12-15 | 2019-01-15 | 2019-03-31 | 20 | High | 1-Diamond | 2019-01-30 | 2019-03-31 | Fan Xiao | DRI | High | in pipeline |  |  |  | Hongliang Jing/Jun Yang/Fan(Shared)
00000935 | GuangDong OPPO Mobile Telecommunications Corp. Ltd. | BD189 | SB4 | SM8150 | SM8150.LA.1.0 | 2018-12-14 | 2019-01-16 | 2019-03-02 | 2019-05-10 | 16 | High | 1-Diamond | 2019-03-11 | 2019-05-10 | Hongliang Jing | DRI | Low | in pipeline |  |  |  | [11/05/2018] case support, same as project BD186
00000935 | GuangDong OPPO Mobile Telecommunications Corp. Ltd. | BD189 | SB4 | SM8150 | SM8150.LA.1.0 | 2018-12-14 | 2019-01-16 | 2019-03-02 | 2019-05-10 | 16 | High | 1-Diamond | 2019-03-11 | 2019-05-10 | Jun Yang | DRI | Low | in pipeline |  |  |  | [11/05/2018] case support, same as project BD186
00000936 | OPPO | BD229 | SB3 | SDX50M + SM8150 | [SM8150.LA.1.5 + SDX50M.TN.2.0].r1 | 2019-01-04 | 2019-02-14 | 2019-03-19 | 2019-04-26 | 20 | High | 1-Diamond | 2019-02-25 | 2019-04-26 | Hongliang Jing | DRI | High | in pipeline |  |  |  | [11/05/2018] case support, same as project BD186
00000936 | OPPO | BD229 | SB3 | SDX50M + SM8150 | [SM8150.LA.1.5 + SDX50M.TN.2.0].r1 | 2019-01-04 | 2019-02-14 | 2019-03-19 | 2019-04-26 | 20 | High | 1-Diamond | 2019-02-25 | 2019-04-26 | Jun Yang | DRI | High | in pipeline |  |  |  | [11/05/2018] case support, same as project BD186
00000937 | TCL | Benz | SB3 | SDM429 | SDM429.LA.1.0 | 2018-08-20 | 2018-10-10 | 2018-11-20 | 2019-04-01 | 18 | Mid | 2-Platinum | 2019-01-31 | 2019-04-01 | Yang Yang | DRI | Low | in pipeline |  |  |  | [11/5/2018] legacy chipset, Case support
00000938 | CKT | BONG | SB3 | SDM660 | SDM660.LA.2.1 | 2017-12-08 | 2018-01-15 | 2018-04-02 | 2018-11-02 | 22 | Mid | 2-Platinum | 2018-05-17 | 2018-11-02 | Jun Yang | DRI | High | Finished |  |  |  | (11/27) First 660 project of CKT |  | 0
00000938 | CKT | BONG | SB3 | SDM660 | SDM660.LA.2.1 | 2017-12-08 | 2018-01-15 | 2018-04-02 | 2018-11-02 | 22 | Mid | 2-Platinum | 2018-07-09 | 2018-08-17 | Boen Song | ServiceLab-TS | High | Finished |  |  |  | (11/27) First 660 project of CKT |  | 2 |  | 1 |  | 1
00000939 | HeYuan | C800_Newsan | SB4 | MSM8940 | MSM8940.LA.3.0.1 | 2016-11-03 | 2016-12-30 | 2017-03-15 | 2018-10-29 | 18 | High | 2-Platinum | 2018-08-30 | 2018-10-29 | Jun Yang | DRI | Low | Finished
00000940 | Huaqin | D2_Latam | SB4 | MSM8953 | MSM8953.LA.3.0.1 | 2016-12-17 | 2017-02-28 | 2017-05-22 | 2018-10-26 | 22 | High | 2-Platinum | 2018-08-27 | 2018-10-26 | Zhiqiang Jin | DRI | Mid | Finished
00000542 | Xiaomi | D2T | SB4 | SDM660 | SDM660.LA.2.1 | 2017-10-25 | 2017-11-25 | 2018-01-10 | 2018-09-19 | 22 | High | 1-Diamond | 2018-07-21 | 2018-09-03 | Mingchen Gao | DRI | Low | Finished |  |  |  | (5/26/2018) SDM660 project, low risk
00000542 | Xiaomi | D2T | SB4 | SDM660 | SDM660.LA.2.1 | 2017-10-25 | 2017-11-25 | 2018-01-10 | 2018-09-19 | 22 | High | 1-Diamond | 2018-07-21 | 2018-09-03 | Yaoyao Hou | DRI | Low | Finished |  |  |  | (5/26/2018) SDM660 project, low risk
00000948 | OPPO | DD155 | SB4 | SDM710 | SDM710.LA.2.0 | 2019-01-30 | 2019-03-19 | 2019-05-20 | 2019-05-30 | 22 | High | 1-Diamond | 2019-03-31 | 2019-05-30 |  |  |  | in pipeline
00000949 | Huawei | Dubai(In-house) | SB3 | SDM450 | SDM450.LA.3.2 | 2018-07-08 | 2018-07-28 | 2018-08-28 | 2018-12-15 | 24 | High | 1-Diamond | 2018-10-16 | 2018-12-15 | Zhiqiang Jin | DRI | Mid | ongoing |  |  |  | [11/5/2018] Case support mainly
00000944 | Xiaomi | E5 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-10-25 | 34 | High | 1-Diamond | 2018-07-02 | 2018-10-15 | Mingchen Gao | DRI | Mid | Finished |  |  |  | [7/27/2018] E5 will run DxO for both Rear and front camera, Mingchen Gao: 7/2 - 9/30, fine tuning(2), ISP/CPP(2) Gary Ge(lab): 8/27 - 9/7, fine tuning(1), ISP/CPP(1) Albert Guo(lab): 8/27 - 9/7, AWB(2) Gary Ge(lab): 9/20 - 9/30, ISP/CPP(2) Albert Guo(lab): 9/20 - 9/30, AWB(2) Yaoyao Hou: 7/2 - 9/30, AEC(4) Jintao Xu:8/27 - 9/14, AF(2) |  | 4 |  | 2 | 2
00000944 | Xiaomi | E5 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-10-25 | 34 | High | 1-Diamond | 2018-08-27 | 2018-09-07 | Gary Ge | Service Lab | Mid | Finished |  |  |  | [7/27/2018] E5 will run DxO for both Rear and front camera, Mingchen Gao: 7/2 - 9/30, fine tuning(2), ISP/CPP(2) Gary Ge(lab): 8/27 - 9/7, fine tuning(1), ISP/CPP(1) Albert Guo(lab): 8/27 - 9/7, AWB(2) Gary Ge(lab): 9/20 - 9/30, ISP/CPP(2) Albert Guo(lab): 9/20 - 9/30, AWB(2) Yaoyao Hou: 7/2 - 9/30, AEC(4) Jintao Xu:8/27 - 9/14, AF(2) |  | 2 |  | 1 | 1
00000944 | Xiaomi | E5 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-10-25 | 34 | High | 1-Diamond | 2018-08-27 | 2018-09-07 | Albert Guo | Service Lab | Mid | Finished |  |  |  | [7/27/2018] E5 will run DxO for both Rear and front camera, Mingchen Gao: 7/2 - 9/30, fine tuning(2), ISP/CPP(2) Gary Ge(lab): 8/27 - 9/7, fine tuning(1), ISP/CPP(1) Albert Guo(lab): 8/27 - 9/7, AWB(2) Gary Ge(lab): 9/20 - 9/30, ISP/CPP(2) Albert Guo(lab): 9/20 - 9/30, AWB(2) Yaoyao Hou: 7/2 - 9/30, AEC(4) Jintao Xu:8/27 - 9/14, AF(2) |  | 2 |  |  |  |  | 2
00000944 | Xiaomi | E5 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-10-25 | 34 | High | 1-Diamond | 2018-09-17 | 2018-09-28 | Gary Ge | Service Lab | Mid | Finished |  |  |  | [7/27/2018] E5 will run DxO for both Rear and front camera, Mingchen Gao: 7/2 - 9/30, fine tuning(2), ISP/CPP(2) Gary Ge(lab): 8/27 - 9/7, fine tuning(1), ISP/CPP(1) Albert Guo(lab): 8/27 - 9/7, AWB(2) Gary Ge(lab): 9/20 - 9/30, ISP/CPP(2) Albert Guo(lab): 9/20 - 9/30, AWB(2) Yaoyao Hou: 7/2 - 9/30, AEC(4) Jintao Xu:8/27 - 9/14, AF(2) |  | 2 |  |  | 2
00000944 | Xiaomi | E5 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-10-25 | 34 | High | 1-Diamond | 2018-09-17 | 2018-09-28 | Albert Guo | Service Lab | Mid | Finished |  |  |  | [7/27/2018] E5 will run DxO for both Rear and front camera, Mingchen Gao: 7/2 - 9/30, fine tuning(2), ISP/CPP(2) Gary Ge(lab): 8/27 - 9/7, fine tuning(1), ISP/CPP(1) Albert Guo(lab): 8/27 - 9/7, AWB(2) Gary Ge(lab): 9/20 - 9/30, ISP/CPP(2) Albert Guo(lab): 9/20 - 9/30, AWB(2) Yaoyao Hou: 7/2 - 9/30, AEC(4) Jintao Xu:8/27 - 9/14, AF(2) |  | 2 |  |  |  |  | 2
00000944 | Xiaomi | E5 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-10-25 | 34 | High | 1-Diamond | 2018-07-02 | 2018-10-12 | Yaoyao Hou | DRI | Mid | Finished |  |  |  | [7/27/2018] E5 will run DxO for both Rear and front camera, Mingchen Gao: 7/2 - 9/30, fine tuning(2), ISP/CPP(2) Gary Ge(lab): 8/27 - 9/7, fine tuning(1), ISP/CPP(1) Albert Guo(lab): 8/27 - 9/7, AWB(2) Gary Ge(lab): 9/20 - 9/30, ISP/CPP(2) Albert Guo(lab): 9/20 - 9/30, AWB(2) Yaoyao Hou: 7/2 - 9/30, AEC(4) Jintao Xu:8/27 - 9/14, AF(2) |  | 4 | [5 empty] | 4
00000944 | Xiaomi | E5 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-10-25 | 34 | High | 1-Diamond | 2018-08-27 | 2018-09-14 | Jintao Xu | DRI | Mid | Finished |  |  |  | [7/27/2018] E5 will run DxO for both Rear and front camera, Mingchen Gao: 7/2 - 9/30, fine tuning(2), ISP/CPP(2) Gary Ge(lab): 8/27 - 9/7, fine tuning(1), ISP/CPP(1) Albert Guo(lab): 8/27 - 9/7, AWB(2) Gary Ge(lab): 9/20 - 9/30, ISP/CPP(2) Albert Guo(lab): 9/20 - 9/30, AWB(2) Yaoyao Hou: 7/2 - 9/30, AEC(4) Jintao Xu:8/27 - 9/14, AF(2) |  | 2 |  |  |  | 2
00000950 | Xiaomi | E5G | SB4 | SDX50M + SM8150 | [SM8150.LA.1.5 + SDX50M.TN.2.0] | 2018-09-13 | 2018-11-20 | 2019-03-15 | 2019-04-01 | 16 | Low | 1-Diamond | 2019-01-31 | 2019-04-01 | Mingchen Gao | DRI | Low | in pipeline |  |  |  | [11/5/2018] Leverage F1, same camera module
00000950 | Xiaomi | E5G | SB4 | SDX50M + SM8150 | [SM8150.LA.1.5 + SDX50M.TN.2.0] | 2018-09-13 | 2018-11-20 | 2019-03-15 | 2019-04-01 | 16 | Low | 1-Diamond | 2019-01-31 | 2019-04-01 | Yaoyao Hou | DRI | Low | in pipeline |  |  |  | [11/5/2018] Leverage F1, same camera module
00000945 | Xiaomi | E8 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-09-20 | 34 | High | 1-Diamond | 2018-07-22 | 2018-08-31 | Yaoyao Hou | DRI | Low | Finished | [5 empty] | 0
00000945 | Xiaomi | E8 | SB3 | SDM845 | SDM845.LA.1.0 | 2018-01-29 | 2018-03-11 | 2018-06-30 | 2018-09-20 | 34 | High | 1-Diamond | 2018-07-22 | 2018-08-31 | Mingchen Gao | DRI | Low | Finished | [5 empty] | 0
00000942 | OPPO | ED007 | SB2 | SDM845 | SDM845.LA.2.0 | 2018-04-25 | 2018-06-28 | 2018-07-29 | 2018-10-10 | 38 | High | 1-Diamond | 2018-08-11 | 2018-10-10 | Hongliang Jing | DRI | Mid | Finished
00000941 | OPPO | ED017 | SB3 | SDM845 | SDM845.LA.2.0 | 2018-04-25 | 2018-06-28 | 2018-07-29 | 2018-09-20 | 34 | High | 1-Diamond | 2018-06-26 | 2018-08-25 | Hongliang Jing | DRI | High | Finished |  |  |  | [6/1] name changed from ED017_NA to ED017 (4/20/2018) Flagship OPPO project on SDM845 with dual camera
00000941 | OPPO | ED017 | SB3 | SDM845 | SDM845.LA.2.0 | 2018-04-25 | 2018-06-28 | 2018-07-29 | 2018-09-20 | 34 | High | 1-Diamond | 2018-06-26 | 2018-08-25 | Hongliang Jing | DRI | High | Finished |  |  |  | [6/1] name changed from ED017_NA to ED017 (4/20/2018) Flagship OPPO project on SDM845 with dual camera
00000941 | OPPO | ED017 | SB3 | SDM845 | SDM845.LA.2.0 | 2018-04-25 | 2018-06-28 | 2018-07-29 | 2018-09-20 | 34 | High | 1-Diamond | 2018-06-26 | 2018-08-25 | Fan Xiao | Service Lab | High | Finished |  |  |  | [6/1] name changed from ED017_NA to ED017 (4/20/2018) Flagship OPPO project on SDM845 with dual camera |  | 3 | 1 | 2
00000941 | OPPO | ED017 | SB3 | SDM845 | SDM845.LA.2.0 | 2018-04-25 | 2018-06-28 | 2018-07-29 | 2018-09-20 | 34 | High | 1-Diamond | 2018-06-26 | 2018-08-25 | Ke He | Service Lab | High | Finished |  |  |  | [6/1] name changed from ED017_NA to ED017 (4/20/2018) Flagship OPPO project on SDM845 with dual camera |  | 3 | 1 | 2
00000941 | OPPO | ED017 | SB3 | SDM845 | SDM845.LA.2.0 | 2018-04-25 | 2018-06-28 | 2018-07-29 | 2018-09-20 | 34 | High | 1-Diamond | 2018-06-26 | 2018-08-25 | Jun Yang | DRI | High | Finished |  |  |  | [6/1] name changed from ED017_NA to ED017 (4/20/2018) Flagship OPPO project on SDM845 with dual camera
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-08 | 2018-10-20 | Fan Xiao | DRI | High | Finished |  |  |  | Fan Xiao: 10/08 - 10/20, ISP(1) |  | 2 |  |  | 1 |  |  |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-08 | 2018-10-20 | Hongliang Jing | DRI | High | Finished |  |  |  | Hongliang Jing: 10/08 - 10/20, AWB(1) |  | 1 |  |  |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-08 | 2018-10-20 | Jun Yang | DRI | High | Finished |  |  |  | Jun Yang(Shared)/Fan Xiao: 10/08 - 10/20, AF (1) |  | 1 | [7 empty] | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-25 | 2018-11-06 | Ke He | Service Lab | High | Finished |  |  |  | Ke He (Lab)(Shared) : 10/25 - 11/16, basic tuning(1), ISP(1) |  | 2 | 1 |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-25 | 2018-11-06 | Boen Song | Service Lab | High | Finished |  |  |  | Boen (Lab)(Shared) : 10/25 - 11/16, basic tuning(1), ISP(1) |  | 2 | 1 |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-25 | 2018-11-06 | Hongliang Jing | DRI | High | Finished |  |  |  | Hongliang Jing: 10/25 - 11/16, basic tuning(1), AWB(1) |  | 2 | 1 |  |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-08 | 2018-10-20 | Jun Yang | DRI | High | Finished |  |  |  | Jun Yang(Shared): 10/08 - 10/20, basic tuning(1) |  | 1 | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-08 | 2018-10-20 | Fan Xiao | DRI | High | Finished |  |  |  | Fan Xiao: 10/08 - 10/20, AF (1) |  | 1 |  |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-11-19 | 2018-12-07 | Ke He | Service Lab | High | Finished |  |  |  | Ke He (Lab)(Shared) : 11/19 - 12/07, ISP(1) |  | 1 |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-11-19 | 2018-12-07 | Boen Song | Service Lab | High | Finished |  |  |  | Boen (Lab)(Shared) : 11/19 - 12/07, ISP(1) |  | 1 |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-11-19 | 2018-12-07 | Hongliang Jing | DRI | High | Finished |  |  |  | Hongliang Jing: 11/19 - 12/07, AWB(1) |  | 1 |  |  |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-11-19 | 2018-12-07 | Jun Yang | DRI | High | Finished |  |  |  | Jun Yang(Shared): 11/19 - 12/07, AF(1) |  | 1 |  |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-10-08 | 2018-10-20 | Fan Xiao | DRI | High | Finished |  |  |  | Fan Xiao: 10/08 - 10/20, AF (1) |  | 1 |  |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-12-10 | 2019-01-28 | Ke He | Service Lab | High | ongoing |  |  |  | Ke He (Lab)(Shared) : 12/10 - 1/28, ISP(4) |  | 4 |  |  | 4
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-12-10 | 2019-01-28 | Boen Song | DRI | High | ongoing |  |  |  | Boen (Lab)(Shared) : 12/10 - 1/28, ISP(4) |  | 4 |  |  | 4
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-12-10 | 2019-01-28 | Hongliang Jing | DRI | High | ongoing |  |  |  | Hongliang Jing: 12/10 - 1/28, AWB(4) |  | 4 |  |  |  |  | 4
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-12-10 | 2019-01-28 | Jun Yang | DRI | High | ongoing |  |  |  | Jun Yang(Shared): 12/10 - 1/28, AF(4) |  | 4 |  |  |  | 4
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2018-12-10 | 2019-01-28 | Fan Xiao | DRI | High | ongoing |  |  |  | Fan Xiao: 12/10 - 1/28, AF (4) |  | 4 |  |  |  | 4
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2019-02-18 | 2019-02-28 | Ke He | Service Lab | High | in pipeline |  |  |  | Ke He (Lab)(Shared) : 2/18 - 2/28, basic tuning(1), ISP(1) |  | 2 | 1 |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2019-02-18 | 2019-02-28 | Boen Song | Service Lab | High | in pipeline |  |  |  | Boen (Lab)(Shared) : 2/18 - 2/28, basic tuning(1), ISP(1) |  | 2 | 1 |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2019-02-18 | 2019-02-28 | Hongliang Jing | DRI | High | in pipeline |  |  |  | Hongliang Jing: 2/18 - 2/28, basic tuning(1), AWB(1) |  | 2 | 1 |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2019-02-18 | 2019-02-28 | Jun Yang | DRI | High | in pipeline |  |  |  | Jun Yang(Shared): 2/18 - 2/28, basic tuning(1) |  |  | 1
00000943 | OPPO | ED103 | SB2 | SM8150 | SM8150.LA.1.0 | 2018-09-26 | 2018-11-29 | 2018-12-24 | 2019-03-04 | 24 | High | 1-Diamond | 2019-02-18 | 2019-02-28 | Fan Xiao | DRI | High | in pipeline |  |  |  | Fan Xiao: 2/18 - 2/28, AF (1) |  | 1 |  |  |  | 1
00000951 | GuangDong OPPO Mobile Telecommunications Corp. Ltd. | ED109 | SB2 | SDX50M + SM8150 | [SM8150.LA.1.5 + SDX50M.TN.2.0] | 2018-08-06 | 2019-02-05 | 2019-03-09 | 2019-04-15 | 24 | High | 1-Diamond | 2019-02-14 | 2019-04-15 | Fan Xiao | DRI | High | in pipeline |  |  |  | [11/05/2018] Assigned to DRI, same as project ED103
00000952 | GuangDong OPPO Mobile Telecommunications Corp. Ltd. | ED113 | SB3 | SM8150 | SM8150.LA.1.0 | 2018-09-24 | 2018-02-05 | 2018-02-09 | 2019-04-25 | 20 | High | 1-Diamond | 2019-02-24 | 2019-04-25 | Fan Xiao | DRI | Low | in pipeline |  |  |  | [11/05/2018] Assigned to DRI, same as project ED103
00000953 | OPPO | ED139 | SB3 | SM8150 | SM8150.LA.1.0 | 2018-11-10 | 2019-01-18 | 2019-02-28 | 2019-03-25 | 20 | High | 1-Diamond | 2019-01-24 | 2019-03-25 | Hongliang Jing | DRI | Mid | in pipeline
00000953 | OPPO | ED139 | SB3 | SM8150 | SM8150.LA.1.0 | 2018-11-10 | 2019-01-18 | 2019-02-28 | 2019-03-25 | 20 | High | 1-Diamond | 2019-01-24 | 2019-03-25 | Jun Yang | DRI | Mid | in pipeline
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-10-22 | 2018-11-16 | Mingchen Gao | DRI | High | Finished | [5 empty] | 3 | 1 |  | 1 | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-10-22 | 2018-11-16 | Yaoyao Hou | DRI | High | Finished | [5 empty] | 2 | 1 |  |  |  |  | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-10-22 | 2018-11-16 | Gary Ge | Service Lab | High | Finished | [5 empty] | 2 | 1 |  | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-10-22 | 2018-11-16 | Albert Guo | Service Lab | High | Finished | [5 empty] | 2 | 1 |  |  |  | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-11-19 | 2018-12-07 | Mingchen Gao | DRI | High | ongoing | [5 empty] | 2 |  | 1 | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-11-19 | 2018-12-07 | Yaoyao Hou | DRI | High | ongoing | [5 empty] | 3 | [5 empty] | 1 |  | 1 | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-11-19 | 2018-12-07 | Jintao Xu | DRI | High | ongoing | [5 empty] | 2 |  |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-11-19 | 2018-12-07 | Gary Ge | Service Lab | High | ongoing | [5 empty] | 2 |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-11-19 | 2018-12-07 | Albert Guo | Service Lab | High | ongoing | [5 empty] | 2 |  |  |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-12-08 | 2018-12-30 | Mingchen Gao | DRI | High | in pipeline | [5 empty] | 2 |  | 1 | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-12-08 | 2018-12-30 | Yaoyao Hou | DRI | High | in pipeline | [5 empty] | 3 | [5 empty] | 1 |  | 1 | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-12-08 | 2018-12-30 | Jintao Xu | DRI | High | in pipeline | [5 empty] | 2 |  |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-12-08 | 2018-12-30 | Gary Ge | Service Lab | High | in pipeline | [5 empty] | 2 |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2018-12-08 | 2018-12-30 | Albert Guo | Service Lab | High | in pipeline | [5 empty] | 2 |  |  |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-02 | 2019-01-18 | Mingchen Gao | DRI | High | in pipeline | [5 empty] | 2 |  | 1 | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-02 | 2019-01-18 | Yaoyao Hou | DRI | High | in pipeline | [5 empty] | 3 | [5 empty] | 1 |  | 1 | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-02 | 2019-01-18 | Jintao Xu | DRI | High | in pipeline | [5 empty] | 2 |  |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-02 | 2019-01-18 | Gary Ge | Service Lab | High | in pipeline | [5 empty] | 2 |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-02 | 2019-01-18 | Albert Guo | Service Lab | High | in pipeline | [5 empty] | 2 |  |  |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-21 | 2019-02-15 | Mingchen Gao | DRI | High | in pipeline | [5 empty] | 2 |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-21 | 2019-02-15 | Yaoyao Hou | DRI | High | in pipeline | [5 empty] | 2 | [5 empty] | 1 |  | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-21 | 2019-02-15 | Jintao Xu | DRI | High | in pipeline | [5 empty] | 1 |  |  |  | 1
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-21 | 2019-02-15 | Gary Ge | Service Lab | High | in pipeline | [5 empty] | 2 |  |  | 2
00000927 | Xiaomi | F1 | SB1 | SM8150 | SDM855.LA.1.0 | 2018-05-22 | 2018-07-19 | 2018-11-22 | 2019-01-20 | 28 |  | 1-Diamond | 2019-01-21 | 2019-02-15 | Albert Guo | Service Lab | High | in pipeline | [5 empty] | 2 |  |  |  |  | 2
00000542 | Xiaomi | F11 | SB3 | SM8150 | SM8150.LA.1.0 | 2018-08-29 | 2018-11-06 | 2019-03-05 | 2019-04-30 | 20 | High | 1-Diamond | 2019-03-01 | 2019-04-30 | Mingchen Gao | DRI | Mid | in pipeline |  |  |  | [11/23/2018] Name changed from F10 [11/5/2018] same support resource as F1 |  | 0
00000542 | Xiaomi | F11 | SB3 | SM8150 | SM8150.LA.1.0 | 2018-08-29 | 2018-11-06 | 2019-03-05 | 2019-04-30 | 20 | High | 1-Diamond | 2019-03-01 | 2019-04-30 | Yaoyao Hou | DRI | Mid | in pipeline |  |  |  | [11/23/2018] Name changed from F10 [11/5/2018] same support resource as F1 |  | 0
00000946 | Xiaomi | F2 | SB3 | SDM710 | SDM710.LA.2.0 | 2017-09-06 | 2018-02-26 | 2018-04-08 | 2019-02-26 | 26 | High | 1-Diamond | 2018-10-17 | 2019-02-26 | Mingcheng Gao | DRI | Low | ongoing
00000946 | Xiaomi | F2 | SB3 | SDM710 | SDM710.LA.2.0 | 2017-09-06 | 2018-02-26 | 2018-04-08 | 2019-02-26 | 26 | High | 1-Diamond | 2018-10-17 | 2019-02-26 | Yaoyao Hou | DRI | Low | ongoing
00000947 | Xiaomi | F3A | SB3 | SM6150 | SM6150.LA.1.0 | 2018-09-19 | 2018-09-19 | 2018-09-19 | 2019-04-08 | 16 | High | 1-Diamond | 2019-02-07 | 2019-04-08 | Mingchen Gao | DRI | High | in pipeline |  |  |  | [11/5/2018] same support resource as F1
00000947 | Xiaomi | F3A | SB3 | SM6150 | SM6150.LA.1.0 | 2018-09-19 | 2018-09-19 | 2018-09-19 | 2019-04-08 | 16 | High | 1-Diamond | 2019-02-07 | 2019-04-08 | Yaoyao Hou | DRI | High | in pipeline |  |  |  | [11/5/2018] same support resource as F1
00000954 | Xiaomi | F3B | SB4 | SM6150 | SM6150.LA.1.0 | 2019-01-16 | 2019-03-07 | 2019-04-19 | 2019-04-19 | 16 | High | 1-Diamond | 2019-02-18 | 2019-04-19 |  |  |  | in pipeline
00000955 | Lenovo | Foles | SB3 | SM6150 | SM6150.LA.1.0 | 2018-09-26 | 2018-11-09 | 2019-02-18 | 2019-04-30 | 18 | High | 1-Diamond | 2019-03-01 | 2019-04-30 | Jintao Xu | DRI | Mid | in pipeline
00000955 | Lenovo | Foles | SB3 | SM6150 | SM6150.LA.1.0 | 2018-09-26 | 2018-11-09 | 2019-02-18 | 2019-04-30 | 18 | High | 1-Diamond | 2019-03-01 | 2019-04-30 | Neo Zha | DRI | Mid | in pipeline
00000956 | Lenovo | Golf lite | SB4 | MSM8917 | MSM8940.LA.3.0.1.c1 | 2017-09-09 | 2017-10-12 | 2018-01-24 | 2018-10-30 | 20 | High | 1-Diamond | 2018-08-31 | 2018-10-30 | Jintao Xu | DRI | Low | Finished |  |  |  | (5/25/2018)
00000957 | Lenovo Mobile Communication Technology Ltd. | Heart | SB3 | SM8150 | SM8150.LA.1.0 | 2018-09-03 | 2018-10-14 | 2018-11-15 | 2018-12-30 | 18 | Low | 1-Diamond | 2018-10-31 | 2018-12-30 | Jintao Xu | DRI | Low | ongoing
00000958 | Longcheer | L2052 | SB4 | SDM636 | SDM636.LA.2.1 | 2018-03-08 | 2018-05-21 | 2018-06-25 | 2018-09-03 | 14 |  | 2-Platinum | 2018-07-05 | 2018-09-03 | Zhiqiang jin | DRI | Low | Finished | [5 empty] | 0
00000959 | Longcheer | L6882 | SB4 | SDM630 | SDM660.LA.2.1 | 2018-02-26 | 2018-05-15 | 2018-09-24 | 2018-12-03 | 14 |  | 2-Platinum | 2018-10-04 | 2018-12-03 | Zhenhua Qiang | TS | Mid | Finished
00000960 | Longcheer | L9500(EE)-GM | SB3 | SDM660 | SDM660.LA.2.1 | 2017-06-29 | 2017-09-15 | 2017-12-19 | 2018-09-10 | 18 |  | 2-Platinum | 2018-07-12 | 2018-06-29 | Donglian Zeng | ServiceLab-TS | Mid | Finished |  |  |  | [10.10]chipset changed from SDM630 to SDM660 |  | 3 | 1 | 2
00000961 | Lenovo | Lake LTA | SB3 | SDM660 | SDM636.LA.2.1 | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-12-31 | 24 | High | 1-Diamond | 2018-11-01 | 2018-12-31 | Jintao Xu | DRI | Mid | ongoing
00000962 | Lenovo | Lake RoW | SB4 | SDM636 | SDM636.LA.2.1 | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2019-03-31 | 20 | Mid | 1-Diamond | 2019-01-30 | 2019-03-31 |  |  |  | in pipeline
00000963 | Meizu | M1822 | SB3 | SDM636 | SDM660.LA.2.1 | 2017-06-13 | 2017-08-08 | 2017-09-27 | 2018-10-26 | 22 | Mid | 2-Platinum | 2018-08-27 | 2018-10-26 | Guangjun He | DRI | Mid | Finished
00000789 | Meizu | M1852 | SB3 | SDM670 | SDM670.LA.1.0 | 2018-05-09 | 2018-06-12 | 2018-08-13 | 2018-10-15 | 22 | High | 2-Platinum | 2018-08-16 | 2018-10-15 | Guangjun He | DRI | Mid | Finished |  |  |  | (5/25/2018) Leverage M1882, different rear sensors
Formulas:
Enter Date = Table2243[[#This Row],[TA Date]]-60
Exit Date = Table2243[[#This Row],[TA Date]]

## Name Mapping
Assignment (CE) Name in Project Tracking Sheet | Name in CE Service System
Albert Guo | Albert Guo
Boen Song | Boen Song
Donglian Zeng | Donglian Zeng
Fan Xiao | Fan Xiao
Gary Ge | Peiguang Ge
Guangjun He | Guangjun He
Hongliang Jing | Hongliang Jing
Jintao Xu | Jintao Xu
Jun Yang | Jun Yang (juyang@qct.qualcomm.com)
Ke He | Ke He
Mingchen Gao | Mingchen Gao
Neo Zha | Zha Neo
Yang Yang | Yang Yang (yanyan@qct.qualcomm.com)
Yaoyao Hou | Monkey Hou
Zhenhua Qiang | Zhenhua Qiang
Xin Huang | Xin Huang
Chenlin Wang | Chenlin Wang
Weitao Lin | Weitao Lin
Zhiqiang jin | Zhiqiang Jin