## Project Tracking
CE Service Number | Account | Project | Priority | Chipset | Software Product | EVT Date | DVT Date | PVT Date | TA Date | Camera Projects CCB overall Score | Volume Projection | Account Rating | Enter Date | Exit Date | Assignment (CE) | Support Type | Level | Status | WE | H | Weeks | Schedule Note | Request | Service # | Basic tuning | IQ fine tuning | ISP/CPP | PDAF/TOF | AWB Color | AEC | DualCam | ADRC | Misc | Service Details
00000789 | Meizu | M1872 | SB4 | SDM670 | SDM636.LA.2.1 | 2018-03-18 | 2018-04-28 | 2018-06-08 | 2018-09-15 | 22 | High | 2-Platinum | 2018-07-17 | 2018-08-27 | Guangjun He | DRI | Mid | Finished |  |  |  | (4/20/2018) first Meizu 670 project |  | 0
00000964 | Meizu | M1923 | SB3 | SM6150 | SM6150.LA.1.0 | 2018-09-28 | 2018-11-20 | 2018-12-26 | 2019-02-22 | 16 | Mid | 2-Platinum | 2018-12-24 | 2019-02-22 | Guangjun He | DRI | High | in pipeline
00000965 | Meizu | M1971 | SB3 | SM8150 | SM8150.LA.1.0 | 2018-10-25 | 2018-12-26 | 2019-03-03 | 2019-04-12 | 16 | High | 2-Platinum | 2019-02-11 | 2019-04-12 | Guangjun He | DRI | Mid | in pipeline |  |  |  | [11/05/2018] Assigned to DRI, TS Serivice Lab, and customer may use TSP
00000965 | Meizu | M1971 | SB3 | SM8150 | SM8150.LA.1.0 | 2018-10-25 | 2018-12-26 | 2019-03-03 | 2019-04-12 | 16 | High | 2-Platinum | 2019-02-11 | 2019-04-12 | Fei Mao | ServiceLab-TS | Mid | in pipeline |  |  |  | [11/05/2018] Assigned to DRI, TS Serivice Lab, and customer may use TSP
00000966 | Longcheer | M5100 | SB3 | SDM632 | SDM632.LA.1.0 | 2018-05-01 | 2018-06-06 | 2018-08-20 | 2019-02-18 | 22 |  | 2-Platinum | 2018-11-19 | 2018-11-30 | Donglian Zeng | ServiceLab-TS | Mid | Finished | [5 empty] | 1 | 1
00000966 | Longcheer | M5100 | SB3 | SDM632 | SDM632.LA.1.0 | 2018-05-01 | 2018-06-06 | 2018-08-20 | 2019-02-18 | 22 |  | 2-Platinum | 2018-12-03 | 2018-12-31 | Donglian Zeng | ServiceLab-TS | Mid | ongoing | [5 empty] | 4 |  | 1 |  | 1 | 1 | 1
00000966 | Longcheer | M5100 | SB3 | SDM632 | SDM632.LA.1.0 | 2018-05-01 | 2018-06-06 | 2018-08-20 | 2019-02-18 | 22 |  | 2-Platinum | 2019-01-02 | 2019-01-31 | Donglian Zeng | ServiceLab-TS | Mid | in pipeline |  |  |  | (5/26/2018) Xiaomi ODM, IQ Ready: 10/15 |  | 3 |  |  | 1 | 1 | 1
00000967 | Longcheer | M6101 | SB3 | SDM660 | SDM660.LA.3.0 |  |  |  | 2019-01-29 | 22 |  | 2-Platinum | 2018-11-30 | 2019-01-29 | Zhenhua Qiang | TS | High | ongoing |  |  |  | [11/23/2018] Assgined to TS due to resource conflict
00000968 | Longcheer | M6300 | SB1 | SM6150 | SM6150.LA.1.0 | 2018-08-29 | 2018-11-24 | 2019-01-15 | 2019-03-10 | 28 |  | 2-Platinum | 2019-01-09 | 2019-03-10 | Zhiqiang Jin | DRI | High | in pipeline |  |  |  | [11/5/2018] SM6150 leading project, assigned 2 DRI to support
00000968 | Longcheer | M6300 | SB1 | SM6150 | SM6150.LA.1.0 | 2018-08-29 | 2018-11-24 | 2019-01-15 | 2019-03-10 | 28 |  | 2-Platinum | 2019-01-09 | 2019-03-10 | Yang Yang | DRI | High | in pipeline |  |  |  | [11/5/2018] SM6150 leading project, assigned 2 DRI to support
00000969 | Lenovo | Messi | SB4 | ZZ_A Product Not Listed | SDM636.LA.2.1 | 2016-03-07 | 2016-04-11 | 2016-07-25 | 2018-09-30 | 16 | Low | 1-Diamond | 2018-08-01 | 2018-09-30 | Jintao Xu | DRI | Low | Finished |  |  |  | (5/25/2018) Leverage 660 project
00000446 | ZTE | NX606J | SB3 | SDM845 | SDM845.LA.1.0 | 2017-08-01 | 2017-10-10 | 2017-12-04 | 2018-09-05 | 32 | High | 1-Diamond | 2018-07-23 | 2018-08-17 | Gary Ge | Service Lab | High | Finished |  |  |  | [7/26/2018] Key 845 project for Nubia Gary Ge: 7/23 - 8/17, ISP fine tuing (1), ISP/CPP (2) Albert Guo: 7/23 - 8/17, AWB (3) Yang Yang: 8/1 - 8/10, ISP(1) [4.20] support suspend due to company policy |  | 2 |  | 1 | 1
00000446 | ZTE | NX606J | SB3 | SDM845 | SDM845.LA.1.0 | 2017-08-01 | 2017-10-10 | 2017-12-04 | 2018-09-05 | 32 | High | 1-Diamond | 2018-07-23 | 2018-08-17 | Albert Guo | Service Lab | High | Finished |  |  |  | [7/26/2018] Key 845 project for Nubia Gary Ge: 7/23 - 8/17, ISP fine tuing (1), ISP/CPP (2) Albert Guo: 7/23 - 8/17, AWB (3) Yang Yang: 8/1 - 8/10, ISP(1) [4.20] support suspend due to company policy |  | 3 |  |  |  |  | 3
00000446 | ZTE | NX606J | SB3 | SDM845 | SDM845.LA.1.0 | 2017-08-01 | 2017-10-10 | 2017-12-04 | 2018-09-05 | 32 | High | 1-Diamond | 2018-07-20 | 2018-08-31 | Yang Yang | DRI | High | Finished |  |  |  | [7/26/2018] Key 845 project for Nubia Gary Ge: 7/23 - 8/17, ISP fine tuing (1), ISP/CPP (2) Albert Guo: 7/23 - 8/17, AWB (3) Yang Yang: 8/1 - 8/10, ISP(1) [4.20] support suspend due to company policy |  | 1 |  |  | 1
00000446 | ZTE | NX606J | SB3 | SDM845 | SDM845.LA.1.0 | 2017-08-01 | 2017-10-10 | 2017-12-04 | 2018-09-05 | 32 | High | 1-Diamond | 2018-07-20 | 2018-08-31 | Xin Huang | DRI | High | Finished |  |  |  | [7/26/2018] Key 845 project for Nubia Gary Ge: 7/23 - 8/17, ISP fine tuing (1), ISP/CPP (2) Albert Guo: 7/23 - 8/17, AWB (3) Yang Yang: 8/1 - 8/10, ISP(1) [4.20] support suspend due to company policy |  | 0
00000970 | ZTE | NX616J | SB4 | SDM845 | SDM845.LA.1.0 | 2017-08-01 | 2017-10-10 | 2017-12-04 | 2018-09-30 | 28 | High | 1-Diamond | 2018-07-20 | 2018-09-30 | Xin Huang | DRI | High | Finished
00000971 | ZTE | P845A01 | SB4 | SDM845 | SDM845.LA.1.0 | 2017-12-01 | 2017-01-20 | 2017-03-20 | 2018-09-17 | 20 |  | 1-Diamond | 2018-07-16 | 2018-08-17 | Gary Ge | Service Lab | High | Finished |  |  |  | (7/26/2018) Key 845 project for ZTE Neoe: 7/16/2018 - 8/31, ISP fine tuning(1), ISP/CPP(1) Gary Ge: 7/16/2018 - 8/2, ISP fine tuning(1), ISP/CPP(1) |  | 2 |  | 1 | 1
00000971 | ZTE | P845A01 | SB4 | SDM845 | SDM845.LA.1.0 | 2017-12-01 | 2017-01-20 | 2017-03-20 | 2018-09-17 | 20 |  | 1-Diamond | 2018-07-16 | 2018-09-17 | Neo Zha | DRI | High | Finished |  |  |  | (7/26/2018) Key 845 project for ZTE Neoe: 7/16/2018 - 8/31, ISP fine tuning(1), ISP/CPP(1) Gary Ge: 7/16/2018 - 8/2, ISP fine tuning(1), ISP/CPP(1) [4.20] support suspend due to company policy |  | 2 |  | 1 | 1
00000972 | ZTE | P855A01 | SB4 | SM8150 | SM8150.LA.1.0 | 2018-11-15 |  |  | 2019-04-09 | 14 |  | 1-Diamond | 2019-02-08 | 2019-04-09 | Neo Zha | DRI | Mid | in pipeline |  |  |  | [11/05/2018] Customer has experience on SDM845, will need support on SM8150 improvement and new 3A features
00000974 | BBK | PD1813BA (670) | SB4 | SDM670 | SDM710.LA.1.0 | 2018-06-15 | 2018-07-15 | 2018-08-15 | 2018-10-10 | 18 | High | 1-Diamond | 2018-07-19 | 2018-10-10 | Weitao Lin | DRI | Low | Finished
00000974 | BBK | PD1813BA (670) | SB4 | SDM670 | SDM710.LA.1.0 | 2018-06-15 | 2018-07-15 | 2018-08-15 | 2018-10-10 | 18 | High | 1-Diamond | 2018-07-19 | 2018-10-10 | Chenlin Wang | DRI | Low | Finished |  |  |  | [07.31] name changed from PD1809(710) to PD1813BA (670)
00000975 | BBK | PD1816 | SB4 | SDM660 | SDM660.LA.2.1.c4 | 2018-06-14 | 2018-07-14 | 2018-08-17 | 2018-10-10 | 22 | High | 1-Diamond | 2018-08-11 | 2018-10-10 | Weitao Lin | DRI | Mid | Finished |  |  |  | [07.10] name changed. [previous name: PD1816 (SDM670)]
00000975 | BBK | PD1816 | SB4 | SDM660 | SDM660.LA.2.1.c4 | 2018-06-14 | 2018-07-14 | 2018-08-17 | 2018-10-10 | 22 | High | 1-Diamond | 2018-08-11 | 2018-10-10 | Chenlin Wang | DRI | Mid | Finished |  |  |  | [07.10] name changed. [previous name: PD1816 (SDM670)]
00000976 | BBK | PD1820 ( SDM710) | SB3 | SDM710 | SDM710.LA.1.0 | 2018-06-15 | 2018-07-15 | 2018-08-15 | 2018-10-31 | 22 | High | 1-Diamond | 2018-09-01 | 2018-10-31 | Weitao Lin | DRI | Low | Finished |  |  |  | [7/31/2018] name changed from PD1807(710) to PD1820 (SDM710) [07.10] name changed. Previous name: SPD1814 (710) (5/26/2018) Leverage PD1805
00000976 | BBK | PD1820 ( SDM710) | SB3 | SDM710 | SDM710.LA.1.0 | 2018-06-15 | 2018-07-15 | 2018-08-15 | 2018-10-31 | 22 | High | 1-Diamond | 2018-09-01 | 2018-10-31 | Chenlin Wang | DRI | Low | Finished |  |  |  | [7/31/2018] name changed from PD1807(710) to PD1820 (SDM710) [07.10] name changed. Previous name: SPD1814 (710) (5/26/2018) Leverage PD1805
00000977 | BBK | PD1821A(ET2019) | SB3 | SDM845 | SDM845.LA.2.0 | 2018-08-26 | 2018-10-10 | 2018-11-07 | 2018-12-03 | 22 | Unknown | 1-Diamond | 2018-10-04 | 2018-12-03 | Weitao Lin | DRI | Mid | ongoing
00000977 | BBK | PD1821A(ET2019) | SB3 | SDM845 | SDM845.LA.2.0 | 2018-08-26 | 2018-10-10 | 2018-11-07 | 2018-12-03 | 22 | Unknown | 1-Diamond | 2018-10-04 | 2018-12-03 | Chenlin Wang | DRI | Mid | ongoing
00000973 | BBK | PD1829 | SB4 | SDM710 | SDM710.LA.2.0 | 2018-06-15 | 2018-07-15 | 2018-08-15 | 2019-03-08 | 18 |  | 1-Diamond | 2018-11-26 | 2019-03-08 | Weitao Lin | DRI | Low | ongoing |  |  |  | [11/05/2018] Assigned to DRI, case support
00000973 | BBK | PD1829 | SB4 | SDM710 | SDM710.LA.2.0 | 2018-06-15 | 2018-07-15 | 2018-08-15 | 2019-03-08 | 18 |  | 1-Diamond | 2018-11-26 | 2019-03-08 | Chenlin Wang | DRI | Low | ongoing |  |  |  | [11/05/2018] Assigned to DRI, case support
00000978 | BBK | PD1832F_EX | SB1 | SM6150 | SM6150.LA.1.0 | 2018-10-30 | 2018-11-15 | 2018-12-25 | 2019-02-01 | 20 |  | 1-Diamond | 2018-12-03 | 2019-02-01 | Chenlin Wang | DRI | Mid | in pipeline |  |  |  | [11/23/2018]Assigned Chenlin on ISP, Xin on AEC, gap on ISP tuning support [11/23/2018]Name changed from PD1823 (TD1827 ) [11/05/2018] Assigned to DRI |  |  |  |  | 1
00000978 | BBK | PD1832F_EX | SB1 | SM6150 | SM6150.LA.1.0 | 2018-10-30 | 2018-11-15 | 2018-12-25 | 2019-02-01 | 20 |  | 1-Diamond | 2018-12-03 | 2019-02-01 | Xin Huang | DRI | Mid | in pipeline |  |  |  | [11/23/2018]Assigned Chenlin on ISP, Xin on AEC, gap on ISP tuning support[11/23/2018]Name changed from PD1823 (TD1827 ) [11/05/2018] Assigned to DRI | [7 empty] | 1
00000979 | Huaqin | PE1812 | SB3 | SDM632 | SDM632.LA.1.0 | 2018-05-15 | 2018-06-11 | 2017-06-26 | 2018-10-10 | 22 | High | 2-Platinum | 2018-07-12 | 2018-08-26 | Zhiqiang Jin | DRI | Mid | Finished |  |  |  | (5/26/2018) Huawie ODM
00000980 | Huaqin | QL1616 | SB4 | MSM8937 | MSM8937.LA.3.0.1 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-10-29 | 18 | Mid | 2-Platinum | 2018-08-30 | 2018-08-31 | Zhiqiang Jin | DRI | Low | Finished
00000981 | Huaqin | QL1655-Lenovo | SB4 | SDM636 | SDM636.LA.2.1 | 2018-06-06 | 2018-07-03 | 2018-07-31 | 2018-09-24 | 18 | Mid | 2-Platinum | 2018-07-26 | 2018-09-24 | Zhiqiang Jin | DRI | Low | Finished |  |  |  | (5/26/2018) Lenovo ODM, SDM636 project, low risk
00000982 | Huaqin | QL1685(ROW)-Lenovo | SB4 | SDM632 | SDM632.LA.1.0 | 2018-06-18 | 2018-07-17 | 2018-10-14 | 2018-12-30 |  |  | 2-Platinum | 2018-10-31 | 2018-12-30 | Zhiqiang jin | DRI | Low | ongoing |  |  |  | (5/26/2018) Lenovo ODM, SDM632 project, low risk
00000983 | Huaqin | QL2202-Ares | SB3 | SDM636 | SDM660.LA.2.1 | 2018-03-26 | 2018-04-20 | 2018-05-30 | 2018-09-15 | 26 | High | 2-Platinum | 2018-07-17 | 2018-09-03 | Zhiqiang Jin | DRI | Mid | Finished |  |  |  | [5/29]changed from Zhenhua to Zhiqiang (4/20/2018) Huawei ODM |  | 0
00000984 | Huaqin | QL6019-XiaoMi | SB4 | SDM660 | SDM660.LA.2.1 | 2018-04-16 | 2018-05-28 | 2018-07-27 | 2018-10-12 | 22 | High | 2-Platinum | 2018-08-13 | 2018-10-12 | Zhiqiang Jin | DRI | High | Finished
00000985 | OPPO | RA010 | SB3 | SDM710 | SDM710.LA.2.0 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-02-15 | 26 |  | 1-Diamond | 2018-12-17 | 2019-02-15 | Hongliang Jing | DRI | High | in pipeline |  |  |  | [11/05/2018] case support
00000985 | OPPO | RA010 | SB3 | SDM710 | SDM710.LA.2.0 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-02-15 | 26 | High | 1-Diamond | 2018-12-17 | 2019-02-15 | Jun Yang | DRI | High | in pipeline |  |  |  | [11/05/2018] case support
00000986 | Lenovo | Robusta note PRC | SB4 | SDM660 | SDM636.LA.2.1 | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-09-30 | 20 | High | 1-Diamond | 2018-08-01 | 2018-09-30 | Jintao Xu | DRI | Low | Finished |  |  |  | (5/25/2018) Leverage 660 project
00000987 | Wingtech | S88508AA1 | SB3 | MSM8917 | MSM8917.LA.3.0.1 | 2018-09-07 | 2018-09-28 | 2018-10-26 | 2019-01-11 | 26 | High | 2-Platinum | 2018-11-01 | 2019-01-11 | Donglian Zeng | ServiceLab-TS | Mid | ongoing | [5 empty] | 3 | 1 | 1 | 1
00000988 | Wingtech | S88568 | SB3 | SDM632 | SDM632.LA.1.0 | 2018-11-05 | 2018-12-07 | 2019-01-13 | 2019-04-06 | 22 | High | 2-Platinum | 2019-02-05 | 2019-04-06 | Donglian Zeng | ServiceLab-TS | Mid | in pipeline | [5 empty] | 5 |  | 1 | 1 | 1 | 1 | 1
00000989 | Wingtech | S88618AA1 | SB4 | SDM632 | SDM632.LA.1.0 | 2018-06-17 | 2018-08-17 | 2018-10-17 | 2018-12-26 | 18 | Mid | 2-Platinum | 2018-10-27 | 2018-12-26 | Zhiqiang Jin | DRI | Low | ongoing
00000990 | Wingtech | S88619AA1 | SB4 | SDM632 | SDM632.LA.1.0 | 2018-06-17 | 2018-08-17 | 2018-10-17 | 2019-01-11 | 18 | Mid | 2-Platinum | 2018-11-12 | 2019-01-11 | Zhiqiang Jin | DRI | Mid | ongoing
00000991 | Wingtech | S88661AA1 | SB3 | SDM660 | SDM660.LA.2.1 | 2018-05-17 | 2018-09-17 | 2018-10-17 | 2018-10-26 |  |  | 2-Platinum | 2018-08-27 | 2018-10-26 | Zhenhua Qiang | TS | Mid | Finished |  |  |  | (5/26/2018) SS ODM project, IQ Ready: 9/10
00000992 | Wingtech | S88760AA1 | SB3 | SDM636 | SDM660.LA.2.1 | 2018-12-24 | 2018-03-01 | 2018-05-03 | 2018-10-12 | 22 | Mid | 2-Platinum | 2018-08-13 | 2018-10-12 | Zhiqiang Jin | DRI | Mid | Finished |  |  |  | (12/28/2017) Lenovo ODM/K9 Note |  | 0
00000993 | Wingtech | S88770AA1 | SB4 | SDM636 | SDM660.LA.2.1 | 2018-10-31 | 2018-11-16 | 2018-12-14 | 2019-01-25 | 18 | Mid | 2-Platinum | 2018-11-26 | 2018-12-31 | Donglian Zeng | ServiceLab-TS | Mid | ongoing | [5 empty] | 4 | 1 | 1 |  |  | 1 | 1
00000993 | Wingtech | S88770AA1 | SB4 | SDM636 | SDM660.LA.2.1 | 2018-10-31 | 2018-11-16 | 2018-12-14 | 2019-01-25 | 18 | Mid | 2-Platinum | 2019-01-02 | 2019-01-25 | Donglian Zeng | ServiceLab-TS | Mid | in pipeline | [5 empty] | 3 |  |  | 1 | 1 | 1
00000994 | Wingtech | S88940AA1 | SB4 | MSM8940 | Snapdragon_High_Med_2016.SPF.1.0 | 2018-10-19 | 2018-12-21 | 2019-01-18 | 2019-05-17 | 14 | High | 2-Platinum | 2019-03-18 | 2019-05-17 | Zhiqiang Jin | DRI | Low | in pipeline |  |  |  | [11/24/2018] Legacy chipset, normal support
00000995 | Wingtech | S88941AA1 | SB4 | MSM8940 | MSM8917.LA.3.2.1 | 2018-10-19 | 2018-12-21 | 2019-01-18 | 2019-05-17 | 14 | High | 2-Platinum | 2019-03-18 | 2019-05-17 | Zhiqiang Jin | DRI | Low | in pipeline |  |  |  | [11/24/2018] Legacy chipset, normal support
00000996 | Wingtech | T89571 | SB4 | SDM439 | SDM439.LA.1.0.1 | 2018-08-31 | 2018-09-21 | 2018-10-12 | 2019-01-18 | 16 | High | 2-Platinum | 2018-11-19 | 2019-01-18 | Zhenhua Qiang | TS | Mid | ongoing |  |  |  | [11/5/2018] legacy chipset, TS to support
00000997 | Wingtech | T89626AA1 | SB4 | SDM429 | SDM429.LA.1.0.1 | 2018-10-19 | 2018-12-19 | 2019-01-31 | 2019-03-15 | 14 | High | 2-Platinum | 2019-01-14 | 2019-03-15 | Zhiqiang Jin | DRI | Low | in pipeline |  |  |  | [11/24/2018] Legacy chipset, normal support
00000998 | BBK | TD1804 (PD1824 4G) | SB2 | SM8150 | SM8150.LA.1.0 | 2019-02-01 | 2019-04-20 | 2019-05-30 | 2019-02-21 | 16 | Mid | 1-Diamond | 2018-12-23 | 2019-02-21 | Weitao Lin | DRI | Low | in pipeline |  |  |  | [11/23] Assigned Weitao to support AF. And gaps for ISP and AEC [11.07] name change to TD1804 (PD1824 4G only) Previous name: TD1804 (8150 4G only) [11/05/2018] Assigned to DRI, dev and system provide support |  | 3 |  |  | 1 | 1 |  | 1
00000999 | Thundersoft | TS_636_K9 note | SB4 | SDM636 | SDM660.LA.2.1 | 2018-12-24 | 2018-03-01 | 2018-05-03 | 2018-10-12 | 18 | Mid | 2-Platinum | 2018-08-13 | 2018-10-12 | Zhenhua Qiang | TS | Low | Finished | [5 empty] | 0
00001000 | Wind Science | Z225 | SB4 | SDM636 | SDM636.LA.2.1 | 2018-07-10 | 2018-08-06 | 2018-09-19 | 2018-12-03 | 14 |  | 2-Platinum | 2018-08-20 | 2018-11-30 | Donglian Zeng | Service-Lab | Mid | Finished | [5 empty] | 5 |  | 1 | 1 | 1 | 1 | 1
00001001 | Lenovo | Zippo | SB4 | SM8150 | SM8150.LA.1.0 | 2018-09-03 | 2018-10-14 | 2018-11-15 | 2019-03-30 | 14 | Low | 1-Diamond | 2019-01-29 | 2019-03-30 | Jintao Xu | DRI | Mid | in pipeline
00001002 | Huaqin | ZQ1989 | SB4 | APQ8009 | MSM8920.LA.3.0.1 | 2017-09-19 | 2017-10-19 | 2017-12-12 | 2018-11-07 | 16 | Mid | 2-Platinum | 2018-09-08 | 2018-11-07 | Zhiqiang Jin | DRI | Low | Finished |  |  |  | [5.13] project chipset/SW/TA date changed. [origin: MSM8920, 5/30TA. [03.30] Name change from QL1578-Lenovo (12/28/2017)8920 project, low risk |  | 0
Formulas:
Enter Date = Table2243[[#This Row],[TA Date]]-60
Exit Date = Table2243[[#This Row],[TA Date]]