## CPEZ
Originating Region | Account | Account Rating | Account Customer Number | Indirect Account | Project | Device Official Name | Project Type | OEM/Target Equipment | Customer Project ID | Chip Group | Chipset | China OEM City | Chipset Attribute | Application Processor Speed | CC_PM | CC_RF | RF Configuration | PA Power Management IC | Power AMP Integrated Front-End IC | Reconfigurable Impedance Matching IC | CC_WLAN_IC | CC_Bluetooth_IC | RAM Size | Battery Capacity in mAh | Display Physical Size (inches) | Display Resolution | 1st Rear Sensor Resolution | OS Delivered by Qualcomm | Current Software/SBA Version | Software Product | SB | Key Project Justification | Link Type | Linked Project | Project Stage | Operator1 | EVT Date | DVT Date | PVT Date | OTA Ready Start | Pre-Lab Start | Lab Cycle 1 Start | Lab Cycle 1 End | Lab Cycle 2 Start | Lab Cycle 2 End | Lab Cycle 3 Start | Lab Cycle 3 End | Originally Planned First TA Date | TA Date | Reason For TA Delay | Assigned TAM: Full Name | TAM Champion: Full Name | Visible To Customer Checkbox | Allow Case Creation Checkbox | TAM Project Checklist | Path to picture of the project | PE Executive Status Summary | Executive Status Summary | Executive Status Summary Updated By: Full Name | Executive Status Summary Updated On | Design Readiness Status | Design Readiness Planned Start Date | Design Readiness Actual Start Date | Design Readiness Comments | Design Readiness Last Modified By | HW Simulation/Tuning Status | HW Simulation/Tuning Planned Start Date | HW Simulation/Tuning Actual Start Date | HW Simulation/Tuning Comments | HW Simulation/Tuning Last Modified By | Component Verif. Status | Component Verif. Planned Start Date | Component Verif. Actual Start Date | Component Verif. Comments | Component Verif. Last Modified By | Bring Up Status | Bring Up Planned Start Date | Bring Up Actual Start Date | Bring Up Comments | Bring Up Last Modified By | RF 360 Status | RF 360 Planned Start Date | RF 360 Actual Start Date | RF 360 Comments | RF 360 Last Modified By | Camera Tuning Status | Camera Tuning Planned Start Date | Camera Tuning Actual Start Date | Camera Tuning Comments | Camera Tuning Last Modified By | Display Tuning Status | Display Tuning Planned Start Date | Display Tuning Actual Start Date | Display Tuning Comments | Display Tuning Last Modified By | Audio Tuning Status | Audio Tuning Planned Start Date | Audio Tuning Actual Start Date | Audio Tuning Comments | Audio Tuning Last Modified By | Power Tuning Status | Power Tuning Planned Start Date | Power Tuning Actual Start Date | Power Tuning Comments | Power Tuning Last Modified By | Thermal Tuning Status | Thermal Tuning Planned Start Date | Thermal Tuning Actual Start Date | Thermal Tuning Comments | Thermal Tuning Last Modified By | Performance Tuning Status | Performance Tuning Planned Start Date | Performance Tuning Actual Start Date | Performance Tuning Comments | Performance Tuning Last Modified By | Factory Tool Status | Factory Tool Planned Start Date | Factory Tool Actual Start Date | Factory Tool Comments | Factory Tool Last Modified By | Pre-Certification Status | Pre-Certification Planned Start Date | Pre-Certification Actual Start Date | Pre-Certification Comments | Pre-Certification Last Modified By | Carrier Support Status | Carrier Support Planned Start Date | Carrier Support Actual Start Date | Carrier Support Comments | Carrier Support Last Modified By | Features Status | Features Planned Start Date | Features Actual Start Date | Features Comments | Features Last Modified By | Stability Status | Stability Planned Start Date | Stability Actual Start Date | Stability Comments | Stability Last Modified By | Mass Prod Status | Mass Prod Planned Start Date | Mass Prod Actual Start Date | Mass Prod Comments | Mass Prod Last Modified By | Basic Information & Chipset updated | Case# | Design Review Request Type | Subject | Req_Recom Without Feedback Count | Impact | L. QC Progress | Case Health Indicator | Internal TAM Comments | PA1 | PA2 | Status | Audio CODEC | RF (Ant Switch) | Summit Battery Charger | Business Unit/Segment | Support Model | CC_Other_RF_IC | Target Region | Speaker Amplifier IC | NFC IC/Module | FM IC/Module | Days Open | LTE Capability | LTE Supported Bands | CDMA | CDMA Supported Bands | Tuning Support Level | Tuning Support Request | RAM Type/technology | L0 | Camera Special Notes | DRI/PoC | CCB Score | CCB Support Level | CCB Note | CCB Support Type | CCB Assignment | Wireless Connectivity Review | Thermal HW Simulation Request | Thermal Hardware Review | System Review | SnapDragon IoE Product Review | Schematic Review | RF Non-POR & Customization | RF Modem Performance | RF Hardware Performance Review | RF Factory Implementation | RF Bring Up | RF block diagram/Front end architecture review | PDN Review | Multimedia Review | Layout Review | Lab Conformance (NV/Pics Review) | DDR Routing Review (Non-PoP MSM) | Component Placement Review | BSP Review | Acoustic Design Review | CPI Audit Result | Customer Project Locked | [8 empty] | 2018-11-01 | [29 empty] | 2018-12-01 | [30 empty] | 2019-01-01 | [30 empty] | 2019-02-01 | [27 empty] | 2019-03-01 | [30 empty] | 2019-04-01 | [29 empty] | 2019-05-01 | [30 empty] | 2019-06-01 | [29 empty] | 2019-07-01 | [30 empty] | 2019-08-01 | [30 empty] | 2019-09-01 | [29 empty] | 2019-10-01 | [30 empty] | 2019-11-01 | [29 empty] | 2019-12-01 | [30 empty] | 2020-01-01 | [30 empty] | 2020-02-01 | [28 empty] | 2020-03-01 | [30 empty] | 2020-04-01 | [29 empty] | 2020-05-01
Originating Region | Account | Account Rating | Account Customer Number | Indirect Account | Project | Device Official Name | Project Type | OEM/Target Equipment | Customer Project ID | Chip Group | Chipset | China OEM City | Chipset Attribute | Application Processor Speed | CC_PM | CC_RF | RF Configuration | PA Power Management IC | Power AMP Integrated Front-End IC | Reconfigurable Impedance Matching IC | CC_WLAN_IC | CC_Bluetooth_IC | RAM Size | Battery Capacity in mAh | Display Physical Size (inches) | Display Resolution | 1st Rear Sensor Resolution | OS Delivered by Qualcomm | Current Software/SBA Version | Software Product | SB | Key Project Justification | Link Type | Linked Project | Project Stage | Operator1 | EVT Date | DVT Date | PVT Date | OTA Ready Start | Pre-Lab Start | Lab Cycle 1 Start | Lab Cycle 1 End | Lab Cycle 2 Start | Lab Cycle 2 End | Lab Cycle 3 Start | Lab Cycle 3 End | Originally Planned First TA Date | TA Date | Reason For TA Delay | Assigned TAM: Full Name | TAM Champion: Full Name | Visible To Customer Checkbox | Allow Case Creation Checkbox | TAM Project Checklist | Path to picture of the project | PE Executive Status Summary | Executive Status Summary | Executive Status Summary Updated By: Full Name | Executive Status Summary Updated On | Design Readiness Status | Design Readiness Planned Start Date | Design Readiness Actual Start Date | Design Readiness Comments | Design Readiness Last Modified By | HW Simulation/Tuning Status | HW Simulation/Tuning Planned Start Date | HW Simulation/Tuning Actual Start Date | HW Simulation/Tuning Comments | HW Simulation/Tuning Last Modified By | Component Verif. Status | Component Verif. Planned Start Date | Component Verif. Actual Start Date | Component Verif. Comments | Component Verif. Last Modified By | Bring Up Status | Bring Up Planned Start Date | Bring Up Actual Start Date | Bring Up Comments | Bring Up Last Modified By | RF 360 Status | RF 360 Planned Start Date | RF 360 Actual Start Date | RF 360 Comments | RF 360 Last Modified By | Camera Tuning Status | Camera Tuning Planned Start Date | Camera Tuning Actual Start Date | Camera Tuning Comments | Camera Tuning Last Modified By | Display Tuning Status | Display Tuning Planned Start Date | Display Tuning Actual Start Date | Display Tuning Comments | Display Tuning Last Modified By | Audio Tuning Status | Audio Tuning Planned Start Date | Audio Tuning Actual Start Date | Audio Tuning Comments | Audio Tuning Last Modified By | Power Tuning Status | Power Tuning Planned Start Date | Power Tuning Actual Start Date | Power Tuning Comments | Power Tuning Last Modified By | Thermal Tuning Status | Thermal Tuning Planned Start Date | Thermal Tuning Actual Start Date | Thermal Tuning Comments | Thermal Tuning Last Modified By | Performance Tuning Status | Performance Tuning Planned Start Date | Performance Tuning Actual Start Date | Performance Tuning Comments | Performance Tuning Last Modified By | Factory Tool Status | Factory Tool Planned Start Date | Factory Tool Actual Start Date | Factory Tool Comments | Factory Tool Last Modified By | Pre-Certification Status | Pre-Certification Planned Start Date | Pre-Certification Actual Start Date | Pre-Certification Comments | Pre-Certification Last Modified By | Carrier Support Status | Carrier Support Planned Start Date | Carrier Support Actual Start Date | Carrier Support Comments | Carrier Support Last Modified By | Features Status | Features Planned Start Date | Features Actual Start Date | Features Comments | Features Last Modified By | Stability Status | Stability Planned Start Date | Stability Actual Start Date | Stability Comments | Stability Last Modified By | Mass Prod Status | Mass Prod Planned Start Date | Mass Prod Actual Start Date | Mass Prod Comments | Mass Prod Last Modified By | Basic Information & Chipset updated | Case# | Design Review Request Type | Subject | Req_Recom Without Feedback Count | Impact | L. QC Progress | Case Health Indicator | Internal TAM Comments | PA1 | PA2 | Status | Audio CODEC | RF (Ant Switch) | Summit Battery Charger | Business Unit/Segment | Support Model | CC_Other_RF_IC | Target Region | Speaker Amplifier IC | NFC IC/Module | FM IC/Module | Days Open | LTE Capability | LTE Supported Bands | CDMA | CDMA Supported Bands | Tuning Support Level | Tuning Support Request | RAM Type/technology | L0 | Camera Special Notes | DRI/PoC | CCB Score | CCB Support Level | CCB Note | CCB Support Type | CCB Assignment | Wireless Connectivity Review | Thermal HW Simulation Request | Thermal Hardware Review | System Review | SnapDragon IoE Product Review | Schematic Review | RF Non-POR & Customization | RF Modem Performance | RF Hardware Performance Review | RF Factory Implementation | RF Bring Up | RF block diagram/Front end architecture review | PDN Review | Multimedia Review | Layout Review | Lab Conformance (NV/Pics Review) | DDR Routing Review (Non-PoP MSM) | Component Placement Review | BSP Review | Acoustic Design Review | CPI Audit Result | Customer Project Locked | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42 | Column43 | Column44 | Column45 | Column46 | Column47 | Column48 | Column49 | Column50 | Column51 | Column52 | Column53 | Column54 | Column55 | Column56 | Column57 | Column58 | Column59 | Column60 | Column61 | Column62 | Column63 | Column64 | Column65 | Column66 | Column67 | Column68 | Column69 | Column70 | Column71 | Column72 | Column73 | Column74 | Column75 | Column76 | Column77 | Column78 | Column79 | Column80 | Column81 | Column82 | Column83 | Column84 | Column85 | Column86 | Column87 | Column88 | Column89 | Column90 | Column91 | Column92 | Column93 | Column94 | Column95 | Column96 | Column97 | Column98 | Column99 | Column100 | Column101 | Column102 | Column103 | Column104 | Column105 | Column106 | Column107 | Column108 | Column109 | Column110 | Column111 | Column112 | Column113 | Column114 | Column115 | Column116 | Column117 | Column118 | Column119 | Column120 | Column121 | Column122 | Column123 | Column124 | Column125 | Column126 | Column127 | Column128 | Column129 | Column130 | Column131 | Column132 | Column133 | Column134 | Column135 | Column136 | Column137 | Column138 | Column139 | Column140 | Column141 | Column142 | Column143 | Column144 | Column145 | Column146 | Column147 | Column148 | Column149 | Column150 | Column151 | Column152 | Column153 | Column154 | Column155 | Column156 | Column157 | Column158 | Column159 | Column160 | Column161 | Column162 | Column163 | Column164 | Column165 | Column166 | Column167 | Column168 | Column169 | Column170 | Column171 | Column172 | Column173 | Column174 | Column175 | Column176 | Column177 | Column178 | Column179 | Column180 | Column181 | Column182 | Column183 | Column184 | Column185 | Column186 | Column187 | Column188 | Column189 | Column190 | Column191 | Column192 | Column193 | Column194 | Column195 | Column196 | Column197 | Column198 | Column199 | Column200 | Column201 | Column202 | Column203 | Column204 | Column205 | Column206 | Column207 | Column208 | Column209 | Column210 | Column211 | Column212 | Column213 | Column214 | Column215 | Column216 | Column217 | Column218 | Column219 | Column220 | Column221 | Column222 | Column223 | Column224 | Column225 | Column226 | Column227 | Column228 | Column229 | Column230 | Column231 | Column232 | Column233 | Column234 | Column235 | Column236 | Column237 | Column238 | Column239 | Column240 | Column241 | Column242 | Column243 | Column244 | Column245 | Column246 | Column247 | Column248 | Column249 | Column250 | Column251 | Column252 | Column253 | Column254 | Column255 | Column256 | Column257 | Column258 | Column259 | Column260 | Column261 | Column262 | Column263 | Column264 | Column265 | Column266 | Column267 | Column268 | Column269 | Column270 | Column271 | Column272 | Column273 | Column274 | Column275 | Column276 | Column277 | Column278 | Column279 | Column280 | Column281 | Column282 | Column283 | Column284 | Column285 | Column286 | Column287 | Column288 | Column289 | Column290 | Column291 | Column292 | Column293 | Column294 | Column295 | Column296 | Column297 | Column298 | Column299 | Column300 | Column301 | Column302 | Column303 | Column304 | Column305 | Column306 | Column307 | Column308 | Column309 | Column310 | Column311 | Column312 | Column313 | Column314 | Column315 | Column316 | Column317 | Column318 | Column319 | Column320 | Column321 | Column322 | Column323 | Column324 | Column325 | Column326 | Column327 | Column328 | Column329 | Column330 | Column331 | Column332 | Column333 | Column334 | Column335 | Column336 | Column337 | Column338 | Column339 | Column340 | Column341 | Column342 | Column343 | Column344 | Column345 | Column346 | Column347 | Column348 | Column349 | Column350 | Column351 | Column352 | Column353 | Column354 | Column355 | Column356 | Column357 | Column358 | Column359 | Column360 | Column361 | Column362 | Column363 | Column364 | Column365 | Column366 | Column367 | Column368 | Column369 | Column370 | Column371 | Column372 | Column373 | Column374 | Column375 | Column376 | Column377 | Column378 | Column379 | Column380 | Column381 | Column382 | Column383 | Column384 | Column385 | Column386 | Column387 | Column388 | Column389 | Column390 | Column391 | Column392 | Column393 | Column394 | Column395 | Column396 | Column397 | Column398 | Column399 | Column400 | Column401 | Column402 | Column403 | Column404 | Column405 | Column406 | Column407 | Column408 | Column409 | Column410 | Column411 | Column412 | Column413 | Column414 | Column415 | Column416 | Column417 | Column418 | Column419 | Column420 | Column421 | Column422 | Column423 | Column424 | Column425 | Column426 | Column427 | Column428 | Column429 | Column430 | Column431 | Column432 | Column433 | Column434 | Column435 | Column436 | Column437 | Column438 | Column439 | Column440 | Column441 | Column442 | Column443 | Column444 | Column445 | Column446 | Column447 | Column448 | Column449 | Column450 | Column451 | Column452 | Column453 | Column454 | Column455 | Column456 | Column457 | Column458 | Column459 | Column460 | Column461 | Column462 | Column463 | Column464 | Column465 | Column466 | Column467 | Column468 | Column469 | Column470 | Column471 | Column472 | Column473 | Column474 | Column475 | Column476 | Column477 | Column478 | Column479 | Column480 | Column481 | Column482 | Column483 | Column484 | Column485 | Column486 | Column487 | Column488 | Column489 | Column490 | Column491 | Column492 | Column493 | Column494 | Column495 | Column496 | Column497 | Column498 | Column499 | Column500 | Column501 | Column502 | Column503 | Column504 | Column505 | Column506 | Column507 | Column508 | Column509 | Column510 | Column511 | Column512 | Column513 | Column514 | Column515 | Column516 | Column517 | Column518 | Column519 | Column520 | Column521 | Column522 | Column523 | Column524 | Column525 | Column526 | Column527 | Column528 | Column529 | Column530 | Column531 | Column532 | Column533 | Column534 | Column535 | Column536 | Column537 | Column538 | Column539 | Column540 | Column541 | Column542 | Column543 | Column544 | Column545 | Column546 | Column547 | Column548 | Column549 | Column550 | Column551 | Column552 | Column553 | Column554 | Column555 | Column556 | Column557 | Column558 | Column559 | Column560 | Column561 | Column562 | Column563 | Column564 | Column565 | Column566 | Column567 | Column568 | Column569 | Column570 | Column571 | Column572 | Column573 | Column574 | Column575 | Column576 | Column577 | Column578 | Column579 | Column580 | Column581 | Column582 | Column583 | Column584 | Column585 | Column586 | Column587 | Column588 | Column589 | Column590 | Column591 | Column592 | Column593 | Column594 | Column595 | Column596 | Column597 | Column598 | Column599 | Column600
China | Huaqin | 2-Platinum |  |  | QL1650-Asus-ROW | Asus ZenFone Max Pro M1 ( ZB601KL) | Wireless Device | SmartPhone | a0D3A00000OSKta | Blackbolt | SDM636 | Shanghai |  |  | PM660;PM660L | SDR660 |  | QET4101 | None | QAT3550 | WCN3980 | WCN3980 BT | 3GB | 5000 | 6 |  | 13M | Android O | r2.1_00014.0.145678.1.147090.0 | SDM636.LA.2.1 | SB4 |  | Existing design to a different carrier | QL1650-Asus | Design/Development | ROW - Open Market | 2018-02-06 | 2018-02-24 | 2018-03-23 | [8 empty] | 2018-09-17 | 2018-12-24 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | *HQ upgraded google security patches and started CTS test *Huaqin work on issue debug normally. * Created new project for ROW. HW is same as QL1650. | Qiang Liu | 2018-12-16 | Staffed/In progress |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [5 empty] | Planning |  |  |  |  | Planning | 2016-06-08 | [8 empty] | Planning | 2016-06-20 |  | 4 |  | Planning | 2016-06-13 |  |  |  | Planning | 2016-07-04 |  |  |  | Staffed/In progress | 2016-06-20 |  |  |  | Staffed/In progress | 2016-06-27 |  |  |  |  | 2016-07-01 | [8 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2016-09-30 |  |  |  | binli@qct.qualcomm.com ; 2018-10-08 08:16:51Z | [11 empty] | PM660 |  |  | Mobile |  |  | Rest of World (ROW) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | [CCB Note: [7/27/2018] SDM636/SB4 project, Case by Case Support] |  |  |  | [7/27/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column62
China | Huaqin | 2-Platinum |  |  | QL1820-Asus |  | Wireless Device | SmartPhone | a0D3A00000OeGCT | Starlord | SDM660 | Shanghai |  |  | PM660L | SDR660 |  | QET4101 | Third Party | None | WCN3980 | WCN3980 BT | 4GB | 5000 | 6.26 |  | 12M | Android O | tbd | SDM636.LA.2.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | ROW - Open Market | 2018-07-18 | 2018-08-04 | 2018-09-04 | [8 empty] | 2018-10-08 | 2018-12-24 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | *MR0 software is under test, plan to finish the test next week, then decide if it can be released as TA software *India and Indonesia version started MP. Russia version got TA *Another 636 project for Asus. Target TA date is Dec.11.2018. | Qiang Liu | 2018-12-16 |  |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [80 empty] | qiangliu@qct.qualcomm.com ; 2018-12-17 07:46:43Z | [11 empty] | PM660 |  |  | Mobile |  |  | India; Rest of World (ROW); South East Asia (SEA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR4X |  | [CCB Note: [7/27/2018] SDM636/SB4 project, Case by Case Support] |  |  |  | [7/27/2018 | [22 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2018-12-01 Column62
China | Wind | 2-Platinum |  |  | E630 | GS280 | Wireless Device | SmartPhone | a0D3A00000OdTHd | Feero | MSM8937 | Shanghai |  |  | PM8937 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 3GB | 4000 | 5.45" HD+ (1440*720) |  | 16M | Android O |  | MSM8937.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-05-14 | 2018-06-21 | 2018-08-18 | [8 empty] | 2018-12-17 | 2018-12-24 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *TA software is finalized and CTS report is under review by google, status is good so far *smartphone project for WE open market, TA: Dec'18 | Qiang Liu | 2018-12-16 |  |  |  |  | tzhou@qct.qualcomm.com ; 2016-09-12 00:38:52Z | [80 empty] | qiangliu@qct.qualcomm.com ; 2018-12-17 07:49:00Z | [11 empty] | Other |  |  | Mobile |  |  | Western Europe (WE) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column62
China | Xiaomi | 1-Diamond |  |  | F7-A | Xiaomi Redmi PRO | Wireless Device | SmartPhone | a0D3A00000OeKhX | Starlord | SDM660 | Shanghai |  |  | PM660;PM660L | SDR660 |  | QET4101 | Third Party | None | WCN3980 | WCN3980 BT | 4GB | 4000 | 5.95" |  | 13M+5M | Android P |  | SDM660.LA.3.0 | SB3 | SDM660-3 Project as Xiaomi F7-A project. First project from Xiaomi to use QPA. | Parent CP for Original design (OEM) | M6101 | Design/Development | China - Open Market | [11 empty] | 2019-01-29 | 2018-12-24 |  | Li Wang | qipl.ce.PEs qipl.ce.PEs | 0 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *SDM660-3 smartphone for Xiaomi as F7-A, 2 PCBA running, one with QPA and one with Qorvo. *TA Delayed to Camera xTS regression Failure. Case#03801663 test_burst_sameness_manual failure << Suggest LC to add debug log for sensorExpTime incorrectness Case#03800351 12M upscaling to 48 causing CTS regression << Xiaomi's feature request cause such regression, giving suggestion to WA this CTS. Case#03776799 In Portrait Mode, the focus frame is shaking << WA fix worked but will cause CTS failure. Cas | Li Wang | 2018-12-17 | [28 empty] | 4 | [11 empty] | Completed | 2018-02-27 |  |  |  | Completed | 2018-02-27 | [38 empty] | liw@qct.qualcomm.com ; 2018-12-17 03:29:42Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note:Link to ODM project Longcheer L6651, "Tuning Request " changed to customer] |  |  |  | Link to ODM project Longcheer L6651, "Tuning Request " changed to customer | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column62
China | Longcheer | 2-Platinum |  |  | L9500_Android_P_Upgrade |  | Wireless Device | SmartPhone | a0D3A00000ORU0S | Starlord | SDM660 | Shenzhen |  |  | PM660L | SDR660 |  | QET4101 | Third Party | None | WCN3980 | WCN3980 BT | >4GB |  | 5.5" |  | 13M AF | Android P |  | SDM660.LA.3.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | EE - Open Market | 2018-08-08 | 2018-09-17 | 2018-10-29 | [8 empty] | 2018-12-24 | 2018-12-24 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * customer reported one CTS issue(case#03783358) before TA software release, CE confirmed it's google bug, customer is checking with google | Qiang Liu | 2018-12-16 | [85 empty] | qiangliu@qct.qualcomm.com ; 2018-12-17 07:47:38Z | [11 empty] | NA |  |  | Mobile |  |  | Eastern Europe (EE) | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note: (10/31/2018) Upgrading project. changed to CUSTOMER] |  |  |  | (10/31/2018) Upgrading project. changed to CUSTOMER | [22 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column6: PVT; 2018-12-01 Column62: TA
China | Huaqin | 2-Platinum |  |  | QL1830-Asus | Asus ZB632 | Wireless Device | SmartPhone | a0D3A00000OdyvY | Shanti | SDM632 | Shanghai |  |  | PM8953;PMI632 | WTR2965 |  | QET4101 | Third Party | Third Party | WCN3615 | WCN3615 | 2GB | 4000 | 6.26 |  | 13M | Android O | TBD | SDM632.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-07-15 | 2018-08-01 | 2018-09-01 |  |  | 2018-08-13 | [5 empty] | 2018-09-24 | 2018-12-24 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | *MR0 is planned to support France/Italy/Turkey market, the software is under test ,plan to finish the test next week, then decide if it can be released as TA software * This project won't use camrea holder for cost down, calibratoin in production line is needed. Related production tool have been developed. * Kicked off new 632 project for Asus. It leveraged design of PE1812. Huaqin requested 4 memory verification request。 | Qiang Liu | 2018-12-16 |  |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [20 empty] | Planning | [24 empty] | Staffed/In progress | [19 empty] | Planning | [9 empty] | Planning |  |  |  |  | qiangliu@qct.qualcomm.com ; 2018-12-17 07:47:09Z | [11 empty] | PM8953 |  |  | Mobile |  |  | Eastern Europe (EE); India; Rest of World (ROW); South East Asia (SEA) | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 |  | [CCB Note: [8/26/2018] SDM632 project, case by case support] |  |  |  | [8/26/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column62
China | Uascent Technology Co., Ltd. | 4-Silver |  |  | NB-09 |  | Wireless Device | M2M Module | a0D3A00000OL5bg | Lykan | MDM9206 | Shenzhen |  |  | PMD9607 | WTR2655 |  | None | Third Party | None | No WLAN | No BT | 256MB | 3400 | 5.65 | FHD (1920x1080) |  | Linux Other |  | MDM9206.TX.2.0 | SB4 | *Uascent's first project. | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | [11 empty] | 2018-04-30 | 2018-12-26 | Still In bring up stage now | Jiaqi Fan |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | * Uascent's first project. M2M module. * Function development stage | Jiaqi Fan | 2018-11-18 | [85 empty] | jiaqfan@qct.qualcomm.com ; 2018-11-19 03:37:17Z | [11 empty] | Other |  |  | IoT Smart-Cities |  |  | China | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | [31 empty] | Strongly Requested Filed: Device Official Name : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column64
China | Wingtech | 2-Platinum |  |  | S88618AA1 | Moto | Wireless Device | SmartPhone | a0D3A00000ODyrP | Shanti | SDM632 | Shanghai |  |  | PM8953 | WTR3925 |  | QET4101 | Third Party | QAT3550 (x2) | WCN3615 | WCN3615 | 3GB | 3000 | 6.2 |  | 12M | Android O |  | SDM632.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-06-17 | 2018-08-17 | 2018-10-17 | [8 empty] | 2018-12-26 | 2018-12-26 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * New project kicks off | Tian Zhou | 2018-12-09 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [35 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-12-10 01:21:13Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column64
China | ZTE | 1-Diamond |  |  | P450S10_P_Upgrade | Blade V9 | Wireless Device | SmartPhone | a0D3A00000OS83g | Jacala | SDM450 | Shanghai |  |  | PM8953 | WTR3925 |  | QFE2101 | Third Party | Third Party | WCN3615 | WCN3615 | 3GB |  | 5.7" |  | 16M | Android P | SDM450.LA.3.1.2 | SDM450.LA.3.1.2 | SB4 | ZTE Blade Center's key SDM450 V9 model | Existing design to a different carrier |  | Design/Development | China - Open Market |  |  | 2018-11-11 |  |  | 2018-11-05 | [5 empty] | 2018-12-26 | 2018-12-26 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Blade SH's V9 model with 5.7", FHD+, 2160 *1080 for China Market with P upgrading. | Baoming Zhang | 2018-09-25 | Planning |  |  |  | baomingz@qct.qualcomm.com ; 2015-08-18 10:17:34Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [24 empty] | baomingz@qct.qualcomm.com ; 2018-09-25 08:18:20Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 |  | [CCB Note: [7/26/2018] SDM450 project, support case by case] |  |  |  | [7/26/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column19: PVT; 2018-12-01 Column64: TA
China | BBK | 1-Diamond |  |  | PD1816_RF_Update | likely X23i | Wireless Device | SmartPhone | a0D3A00000OSXn8 | Starlord | SDM660 | Shenzhen |  |  | PM660 | SDR660 |  | QET4101 | QPA8675;QPA8685 | Third Party | WCN3990 | WCN3990 BT | 4GB | 3700 | 6.1" |  | 12M | Android O | SDM660.LA.2.1.c4-00001-STD.PROD-1 | SDM660.LA.2.1.c4 | SB4 | PD1816 RF Design update from 3rd party PA to QPA(QPA8675+QPA8685) | Updated design | PD1816 | Design/Development | China - Open Market | 2018-06-14 | 2018-07-14 | 2018-08-17 | [8 empty] | 2018-12-17 | 2018-12-26 | Performance is OK, work on product line QCN compatibility issue. | Jiaqi Fan | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | *PD1816 RF Design update from 3rd party PA to QPA(QPA8675+QPA8685) *Performance is OK. working on QCN compatibility issue | Jiaqi Fan | 2018-12-16 | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2017-11-13 23:38:11Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2017-02-06 |  |  |  | Planning |  |  |  |  | Staffed/In progress | 2017-12-03 |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2017-12-08 |  |  |  | Planning | [19 empty] | Planning |  |  |  |  | Planning |  |  |  |  | jiaqfan@qct.qualcomm.com ; 2018-12-17 03:18:52Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | Other | No NFC | None |  | TDD | B1 (FDD); B3 (FDD); B5 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 |  | [CCB Note: (10/31/2018) Upgrading project. changed to CUSTOMER] [CCB Support Level:High] [CCB Score:26] [DRI/PoC:Weitao Lin] | Weitao Lin | 26 | High | (10/31/2018) Upgrading project. changed to CUSTOMER | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column64
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_8996_T288 | T288 | Wireless Device | SmartPhone | a0D3A00000OGtEr | Istari | MSM8996 | Beijing |  |  | PM8996;PMI8996 | WTR3925 |  | QFE3100 | Third Party | None | QCA6174A-1 | QCA6174A-1 | 4GB | 3000 | 5.7" |  | 21M | Android N |  | MSM8996.LA.2.0.1.c4 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-04-26 | 2018-06-16 | 2018-08-04 | [8 empty] | 2018-12-27 | 2018-12-27 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | * SIM Beijing glass project. * Base project is SIM_8996_M5E, Same software. * PL: Nie QiLei 13810493899 * It is delayed to 12/27. * No blocking issue is for this project. | Jiuyao Shu | 2018-12-09 | [24 empty] | kemingd@qct.qualcomm.com ; 2016-11-18 02:15:17Z | [19 empty] | yifeiz@qct.qualcomm.com ; 2016-11-19 11:16:17Z |  |  |  |  | yifeiz@qct.qualcomm.com ; 2016-11-19 11:16:17Z |  |  |  |  | yanlongh@qct.qualcomm.com ; 2016-11-20 19:34:17Z | [30 empty] | jshu@qct.qualcomm.com ; 2018-08-29 02:17:53Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 1 High: Full QTI Support Required | Customer | LPDDR4 | bar: 2018-12-01 Column65
China | Emdoor Holdings Limited | 4-Silver |  |  | A835 |  | Wireless Device | IOT AIO VR | a0D3A00000OKnSP | Nazgul | APQ8098 | Shenzhen |  |  | PM8998;PMI8998 | Other |  | None | None | None | WCN3990 | WCN3990 BT | 4GB |  | 2.8 |  | NA | Android N |  | MSM8998.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2018-12-27 | 2018-12-27 |  | Andy Li |  | 1 | 1 |  |  |  | * All in one VR device, with 6 DoF； * No confirmed OEM now. | Andy Li | 2018-07-02 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-09-03 03:41:11Z | [11 empty] | WCD9335 |  |  | IoT VR/AR | Direct OEM Support |  | China | WSA8815 x2 (Stereo) | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column65
China | Huaqin | 2-Platinum |  |  | D2A_P_Upgrade | XiaoMi | Wireless Device | SmartPhone | a0D3A00000ORq8D | Jacala | MSM8953 | Shanghai |  |  | Other;PM8953 | WTR3925 |  | None | Third Party | None | WCN3660B | WCN3660B | 3GB | 3200 | 5.5 |  | 13M | Android P | Snapdragon_High_Med_2016.SPF.3.1.2 | MSM8953.LA.3.1.2 | SB4 |  | MR - Updated OS | D2A_India | Design/Development | India - Open Market | 2016-12-17 | 2017-02-28 | 2017-05-22 |  |  | 2017-04-17 | [5 empty] | 2018-12-28 | 2018-12-28 |  | Hongye Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | * Anroid O OTA upgrade project * 9/17 ~ 10/ 12 1st round full test * 10/3 ~ 11/2 oversea field test * 10/25 ~ 11/9 2nd round full test * 11/30 MP version release | Hongye Liu | 2018-11-26 | Staffed/In progress |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [5 empty] | Planning |  |  |  |  | Planning | 2016-06-08 | [8 empty] | Planning | 2016-06-20 |  | 4 |  | Planning | 2016-06-13 |  |  |  | Planning | 2016-07-04 |  |  |  | Staffed/In progress | 2016-06-20 |  |  |  | Staffed/In progress | 2016-06-27 |  |  |  | Staffed/In progress | 2016-07-01 | [8 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2016-09-30 |  |  |  | hongyel@qct.qualcomm.com ; 2018-09-05 08:22:12Z | [11 empty] | PM8953 |  |  | Mobile |  |  | India | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 |  | [CCB Note:[9/28/2018] Upgrading project for D2A] customer will use 3rd party Arcsoft solution for dual camera part, ported 8998 framework |  |  |  | [9/28/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column66
China | Huawei | 1-Diamond |  |  | Dubai(ODM)-CT |  | Wireless Device | SmartPhone | a0D3A00000OSb2h | Jacala | SDM450 | Xi'an |  |  | PMI632;PM8953 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 3GB | 4000 | 6.29" |  | 13M+2M | Android O |  | SDM450.LA.3.2 | SB4 | *Huawei's leading SDM450 project. It has big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | 2018-07-08 | 2018-07-28 | 2018-08-28 |  |  | 2018-10-08 | [5 empty] | 2018-12-15 | 2018-12-28 |  | Yizhen Yang | Nikhil Shevade | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | *ODM design. *For CT. | Yizhen Yang | 2018-11-29 | [85 empty] | yizheny@qct.qualcomm.com ; 2018-12-14 09:12:05Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2018-12-01 Column66
China | Huawei | 1-Diamond |  |  | Dubai(In-house)-CT |  | Wireless Device | SmartPhone | a0D3A00000OSb2m | Jacala | SDM450 | Xi'an |  |  | PMI632;PM8953 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 3GB | 4000 | 6.29" |  | 13M+2M | Android O |  | SDM450.LA.3.2 | SB4 | *Huawei's leading SDM450 project. It has big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | 2018-07-08 | 2018-07-28 | 2018-08-28 |  |  | 2018-10-08 | [5 empty] | 2018-12-15 | 2018-12-28 |  | Yizhen Yang | Nikhil Shevade | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | *In-house design. For CT. | Yizhen Yang | 2018-11-29 | [85 empty] | yizheny@qct.qualcomm.com ; 2018-12-14 09:12:28Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2018-12-01 Column66
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | Sim_8917_DW1000_ChinaOpen |  | Wireless Device | SmartPhone | a0D3A00000OdsAp | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | QFE2101 | None | Third Party | WCN3660B | WCN3680B | 2GB | 2400 |  |  | 13MP | Android O |  | MSM8917.LA.3.0.c1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-06-20 | 2018-08-30 | 2018-10-08 | [8 empty] | 2018-12-28 | 2018-12-28 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | *SIM Shanghai project. * PL: Zuo Hongyan 18121093752 * No blocking issue is reproted for this project. | Jiuyao Shu | 2018-12-09 | [85 empty] | jshu@qct.qualcomm.com ; 2018-10-08 03:27:41Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column66
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_SDM450_ST801 | ST801 | Wireless Device | SmartPhone | a0D3A00000OeuGD | Jacala | SDM450 | Beijing |  |  | PMI632 | WTR3925 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 3GB |  |  |  |  | Android O |  | SDM450.LA.3.2.c1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-08-02 | 2018-09-07 | 2018-10-08 | [8 empty] | 2018-12-28 | 2018-12-28 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * SDM450 Shanghai smartphone project * Pl: Zuo Hongyan 18121093752. * EVT was ready. * No blocking issue is for this project. | Jiuyao Shu | 2018-12-09 | [85 empty] | jshu@qct.qualcomm.com ; 2018-10-08 03:28:12Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column66
China | ZTE | 1-Diamond |  |  | Z610DL_MR | Z610DL | Wireless Device | SmartPhone | a0D3A00000OT5gg | Feero | MSM8940 | Shanghai |  |  | PM8940;PMI8952 | WTR3925 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 3GB | 4000 | 6.0" |  | 16M | Android O | Snapdragon_High_Med_2016.SPF.3.0.1.c2 | MSM8940.LA.3.0.1.c1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2017-08-20 | 2017-10-20 | [9 empty] | 2018-12-18 | 2018-12-28 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Z610DL Android O upgrade project for NA open market based on SPF 3.0.1.c2. * ZTE plan to release the TA SW build on 12/18, and target TA on 12/28. * Only need to pass CTS and internal TA testing as it will be launched for open market. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-12-17 03:05:10Z | [11 empty] | PM8952 |  |  | Mobile |  |  | North America (NA) | Other | Other | WCN |  | FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column66
China | OPPO | 1-Diamond |  |  | CC063_CT | NA | Wireless Device | SmartPhone | a0D3A00000ORspo | Jacala | SDM450 | Shenzhen |  |  | PMI632;PM8953 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3660B | WCN3660B | 2GB |  | 5.5" |  | 13M | Android O | 2016.SPF.1.0-02000-STD.PROD-1 | SDM450.LA.3.2 | SB4 | *CT model | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) |  |  |  |  | 2018-09-10 | 2018-09-14 | 2018-10-15 |  |  |  |  | 2018-10-30 | 2018-12-28 |  | Hongbo Chen | Nikhil Shevade | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *CT model *Under testing , no blocking issues | Zhiyang Gao | 2018-11-06 |  |  |  |  | qiw@qct.qualcomm.com ; 2016-05-16 00:30:01Z | [25 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [5 empty] | 2016-07-11 |  |  |  | Completed | 2016-08-22 |  |  |  | Staffed/In progress | 2017-10-30 | [33 empty] | lxie@qct.qualcomm.com ; 2018-12-03 03:05:48Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column66
China | OPPO | 1-Diamond |  |  | EB101_Android_P_Upgrade | OnePlus 5/5T_P_OTA | Wireless Device | SmartPhone | a0D3A00000ORst3 | Nazgul | MSM8998 | Shenzhen |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | Third Party | QAT3514;QAT3550 | WCN3990 | WCN3990 BT | 6GB | 3400 | 6.01 |  |  | Android P |  | MSM8998.LA.2.0.2 | SB4 | Oneplus 1st MSM8998 project and Key product of 2017 Forecast 3KK | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market |  |  | 2018-12-10 | 2018-11-17 | [7 empty] | 2018-12-28 | 2018-12-28 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Schematics Review; Layout Review; SW architecture review |  |  | *MSM8998 Android P OTA *WLAN CPL released | Zhiyang Gao | 2018-12-17 | [20 empty] | Staffed/In progress | [29 empty] | Staffed/In progress | 2017-11-20 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-09-07 07:03:29Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support | QLN1020/QLN1030 | China | Other | Other | WCN |  |  |  | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note: [9/28/2018] Upgrading project for EB101] Dual PD or Optical Zoom not fixed |  |  |  | [9/28/2018 | [22 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column48: PVT; 2018-12-01 Column66: TA
China | CloudMinds Inc. | 4-Silver |  |  | A2H_CHN |  | Wireless Device | SmartPhone | a0D3A00000OSawr | Nazgul | MSM8998 | Beijing |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | Third Party | QAT3514 | WCN3990 | WCN3990 BT | 4GB | 4500 | 5.7inch |  | 12M | Android O | MSM8998.LA.2.0.1-00162-STD.PROD-1 | MSM8998.LA.2.0.1 | SB4 |  | Existing design to a different carrier | A2H_ATT | Design/Development | China - Open Market | [5 empty] | 2019-03-04 |  | 2019-04-01 |  |  |  | 2018-12-28 | 2018-12-28 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * A2H project for China market * CTA test is ongoing. | Huize Wang | 2018-12-10 | [85 empty] | huizew@qct.qualcomm.com ; 2018-12-11 02:41:21Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | North America (NA) | WSA8815 | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD); B29 (FDD); B30 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | 3D camera | [26 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column66
China | Shenzhen Heyuan Electronics Co., Ltd | 2-Platinum |  |  | P700AS | SUGAR Y17 | Wireless Device | SmartPhone | a0D3A00000OeF2U | Jacala | SDM450 | Shenzhen |  |  | PMI8952 | WTR3925 |  | None | None | None | WCN3680B | WCN3680B | 3GB | 3250 | 5.2 |  | 16MP | Android N | SDM450.LA.3.1.1 | SDM450.LA.3.1.1 | SB4 | * Tinno 1st SDM450 project based on LA 3.1.1 SP (with TA 3.0 modem). | Updated design |  | Under Acceptance | China - Open Market | 2016-11-03 | 2016-12-30 | 2017-03-15 |  |  | 2017-03-15 | [5 empty] | 2018-10-29 | 2018-12-29 |  | Frank Lu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | * Tinno 1st SDM450 project based on LA 3.1.1 SP (with TA 3.0 modem). * the test samples had been delivered to CMCC lab on 9th Nov. | Frank Lu | 2018-12-16 | [25 empty] | Staffed/In progress | 2016-12-01 | [13 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress | 2016-04-25 | [33 empty] | yonggang@qct.qualcomm.com ; 2018-12-24 05:52:04Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Customer | SDRAM-LPDDR3 |  | [CCB Note: [7/26/2018] SDM450/SB4 project, support case by case] |  |  |  | [7/26/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column67
China | Xiaomi | 1-Diamond |  |  | A1_Android_O_Upgrade |  | Wireless Device | SmartPhone | a0D3A00000OCq53 | Istari | MSM8996 | Beijing |  |  | PM8996;PMI8994 | WTR3925 |  | QFE3100 | Third Party | None | QCA6164A-1 | QCA6164A-1 | >2GB | 2900 | 5.1" | FHD (1920x1080) | 16MP | Android O | MSM8996.LA.1.0.1.c2-01275-STD.PROD-1 | MSM8996.LA.2.0.1.c4 | SB4 | Xiaomi next flagship product with high volume | MR - Updated OS |  | Design/Development | China - Open Market | 2017-09-22 | 2018-04-30 | 2018-06-30 | 2015-11-10 | 2016-01-07 | [6 empty] | 2018-05-01 | 2018-12-30 |  | Guowei Qin | Michael Liu | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training |  |  | *Xiaomi 8996 O release upgrade project； *APSS build, MSM8996.LA.2.0.2/Post-CS 0.0.030.1/ LA.UM.6.5.r1-04300-8x96.0-1; *Non-HLOS build:MSM8996.LA.2.0.1/Post-CS 0.1.002.1a/MSM8996.LA.2.0.1.c4-01002-STD.PROD-1/WLAN.RM.4.3.c3-00018-QCARMSWPZ-1.113566.2/MPSS.TH.2.0.c1.9-00113-M8996FAAAANAZM-1.126839.2/TZ.BF.4.0.1-00301-M8996AAAAANAZT-1.100589.1.109507.1 | Guowei Qin | 2018-12-16 | Completed | 2015-03-16 | 2015-03-16 |  | gqin@qct.qualcomm.com ; 2015-06-19 02:18:09Z | Staffed/In progress |  |  |  | gqin@qct.qualcomm.com ; 2015-06-19 02:18:09Z | Staffed/In progress | 2015-06-25 |  |  | gqin@qct.qualcomm.com ; 2015-06-19 02:28:02Z | Staffed/In progress | 2015-06-25 |  |  | xinliu@qct.qualcomm.com ; 2015-10-29 18:41:45Z | Planning | 2015-06-30 |  | *A1 fails LTE spurious test in FDD B1+B3 due to 3rd party component inconsistency. this is not blocking issue for MP but need 3rd party to improve in the long run | xinliu@qct.qualcomm.com ; 2015-12-17 19:26:37Z | Planning | 2015-10-01 |  |  | xiwang@qct.qualcomm.com ; 2017-08-14 22:52:41Z | Planning | 2015-10-01 |  | *XiaoMI raises Color temperature request on A1, display team will work on it *Xiaomi plans to do per panel calibration in vendors factory, golden sample will be brought to Toronto in Jan * | xinliu@qct.qualcomm.com ; 2015-12-17 19:26:37Z | Planning | 2015-10-01 |  | *Ultrasound in call mode has sensitivity and latency issues to be improved by this week *3rd party SVA integration needs to complete by this week | xinliu@qct.qualcomm.com ; 2015-12-17 19:26:37Z | Planning | 2015-10-01 |  | [2/19]A1 will be launch at 2/24 and no more issue reported[1/21]abnoraml leakage due to DAC pins connect to GND wrongly, this is a random issue, SW WA has been provided, further verification is on-going by XiaoMi and I[1/14]Latest DoU is 64% no more issues now[1/8]Latest DoU is 62%, no other concern from OEM now [12/24]Power fine tunning on WIFI idle current, data transfer 4G power; Fruitninja game power from graphic side DoU hits 61% , met XiaoMi`s expecting | lhua@qct.qualcomm.com ; 2016-02-19 03:57:06Z | Staffed/In progress | 2015-10-01 |  | [2/19]A1 will be launch at 2/24 and no more issue reported[1/21]Factory ramping up know, no more update[1/14]No more update[1/8]No update for this part now [12/20] 1080P recording can’t pass Xiaomi criteria, but power is good, so it depends on Xiaomi HW and Camera module optimization *: 3.2W@17C Tdelta (back); Tskin cannot meet Xiaomi spec in 1080p Video encode/decode with 30min test Waiting for Xiaomi final thermal data after HW mod; RR3 can meet Xiaomi spec | lhua@qct.qualcomm.com ; 2016-02-19 03:57:06Z | Staffed/In progress | 2015-10-28 | 2015-10-28 | TOP issue: we focused on application launching. and already provide bunch of patches to Xiaomi. With which Xiaomi already see that A1 is compatible for most application launching with Mate8. They accept this. Now they concern for some gaming launching issue. analyze case by case. | yunguo@qct.qualcomm.com ; 2016-02-19 00:21:08Z | Planning | 2015-08-03 |  |  | gqin@qct.qualcomm.com ; 2015-06-19 02:28:02Z | Planning |  |  | first launch target for open market; there will be carrier variants after first launch | gqin@qct.qualcomm.com ; 2015-06-19 02:28:02Z | Planning |  |  | first launch target for open market; | gqin@qct.qualcomm.com ; 2015-06-19 02:28:02Z | Planning | 2015-07-01 |  |  | gqin@qct.qualcomm.com ; 2015-06-19 02:28:02Z | Planning | 2015-11-02 |  |  | gqin@qct.qualcomm.com ; 2015-06-19 02:28:02Z | Planning | 2015-12-15 |  |  | gqin@qct.qualcomm.com ; 2015-06-19 02:28:02Z | gqin@qct.qualcomm.com ; 2018-11-02 01:43:28Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China | Other | Other | SiLab |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | C850 BC0; C1900 BC1 | 1 High: Full QTI Support Required | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty | bar: 2018-12-01 Column68
China | Shenzhen Friendcom Technology Development Co., Ltd. | 4-Silver |  |  | CMN110 |  | Wireless Device | M2M Module | a0D3A00000OLi6P | Lykan | MDM9206 | Shenzhen |  |  | PMD9607 | WTR2655 |  | None | Third Party | None | No WLAN | No BT | <128MB |  |  |  |  | ThreadX |  | MDM9206.TX.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2018-08-24 | 2018-12-30 | Customer postpone the schedule. Final customer is not identified. | Jiaqi Fan |  | 1 | 1 |  |  |  | *EVT returned and all functions worked, keep on performance profile. *Promoting to final customer.final customer still not confirmed. Reschedule Plan | Jiaqi Fan | 2018-06-10 | [85 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-03 02:44:06Z | [11 empty] | Other |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B26 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column68
China | Lenovo | 1-Diamond |  |  | Ocean | Moto G (OSLO H ) | Wireless Device | SmartPhone | a0D3A00000OdLZQ | Jacala | MSM8953 | Shanghai |  |  | PM8953 | WTR3925 |  | Third Party | None | QAT3550 | WCN3615 | WCN3615 | 3GB | 3000 | 6.5'' |  | 12M | Android P | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 | Next generation Moto G on SDM632 | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2018-12-30 | 2018-12-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *As Lenovo still no SDM632 contact, put this project onto MSM8953 | Gavin Song | 2018-04-28 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-12 |  |  |  |  | 2015-07-30 |  |  |  |  | 2015-05-15 |  |  |  |  | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  |  | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-10-08 02:38:33Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column68
China | Lenovo | 1-Diamond |  |  | OSLO-H NA | Moto G (Ocean ) | Wireless Device | SmartPhone | a0D3A00000OdLZV | Jacala | MSM8953 | Shanghai |  |  | PM8953 | WTR3925 |  | Third Party | None | QAT3550 | WCN3660 | WCN3660 | 3GB | 3000 | 6.5'' |  | 12M | Android P | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 | Next generation Moto G on SDM632 | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2018-12-30 | 2018-12-30 |  | Gavin Song |  | 0 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *As Lenovo still no SDM632 contact, put this project onto MSM8953 | Gavin Song | 2018-04-28 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-12 |  |  |  |  | 2015-07-30 |  |  |  |  | 2015-05-15 |  |  |  |  | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  |  | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-10-08 02:38:21Z | [11 empty] | Other |  |  | Mobile |  |  | North America (NA) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column68
China | Xiaomi | 1-Diamond |  |  | E2_Android P_upgrade |  | Wireless Device | SmartPhone | a0D3A00000OdvVx | Warlock | SDM710 | Beijing |  |  | PM670;PM670L | SDR660 |  | QET4101 | None | None;Third Party | WCN3990 | WCN3990 BT | >4GB | 3000 | 5.5 |  | 12M | Android P |  | SDM710.LA.2.0 | SB4 | Xiaomi SDM710 leading project; Expect 2M shipment. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-09-06 | 2018-02-26 | 2018-04-08 |  |  | 2018-05-03 | [5 empty] | 2018-12-30 | 2018-12-30 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *E2 Android P upgrade project; *MPSS/CNSS stay on the SDM LA1.0.c1; *Camera keep on the SDM710 LA1.0 camera SBA; *Camera hang issue for 3rd party algrithem in CDSP has block the Dec OTA public push; | Guowei Qin | 2018-12-09 | [25 empty] | Planning | [24 empty] | Staffed/In progress | 2017-11-27 | [33 empty] | gqin@qct.qualcomm.com ; 2018-06-04 03:04:32Z | [11 empty] | PM660 |  |  | Mobile |  | QLN | China | Other | No NFC | WCN |  |  |  | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note: (6/19/2018) E2 Upgrade project] 1.2PD 2. Real-time Bokeh 3. Manual 3A 4. slow motion(480fps/240 fps/120fps) |  |  |  | (6/19/2018) E2 Upgrade project | [22 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column68
China | Lenovo | 1-Diamond |  |  | Channel | Moto G (OSLO M ) | Wireless Device | SmartPhone | a0D3A00000OdYux | Jacala | MSM8953 | Nanjing |  |  | PM8953 | WTR3925 |  | Third Party | None | QAT3550 | WCN3615 | WCN3615 | 3GB | 3000 | 6.5'' |  | 12M | Android P | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 | Next generation Moto G on SDM632 | Parent CP for Original design (OEM) | QL1685(ROW)-Lenovo | Design/Development | LA - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2018-12-30 | 2018-12-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *As Lenovo still no SDM632 contact, put this project onto MSM8953 *SDM632 project *HW ODM by huaqin | Gavin Song | 2018-05-11 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-12 |  |  |  |  | 2015-07-30 |  |  |  |  | 2015-05-15 |  |  |  |  | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  |  | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-10-08 02:38:08Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column68
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | SHEEP |  | Wireless Device | IOT Smart POS | a0D3A00000OFAsv | Jacala | APQ8053 | Shanghai |  |  | Other;PM8953 | None | DSDS L/W/G+G | None | None | None | WCN3660B | WCN3660B | 1GB | 0 | 5" | FHD (1920x1080) | None | Android O | MSM8953.LA.3.2 | MSM8953.LA.3.2 | SB4 | HP cash system ODM | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2015-12-30 | 2016-01-31 | 2016-03-30 | [8 empty] | 2018-12-30 | 2018-12-30 |  | Tianhao Fei |  | 1 | 1 |  |  |  | P payment system ODM. PMI632 used， and SW is 2018.SPF.1.0. PVT in final debugging, and trial MP ongoing. TA SW make code freeze on Dec 8th. CTS and MP Issues in support by case. Status on track It plans to get TA by end of 2018. | Tianhao Fei | 2018-12-16 | [40 empty] | Staffed/In progress | 2016-07-29 | 2016-07-29 | [10/14] No critical issue so far [09/30] No critical issue so far [09/23] RBSC is 3mA, a bit higher than QRD reference. Will do GPIO dump comparison then. [09/09] No critical issue so far [09/03] No critical issues so far. [08/26] No critical issues so far. [08/19] No critical issue so far. already provide customer the detailed analysis. [8/12]1.Power DB: No critical issue so far. already provide customer the detailed analysis. 2.Thermal DB: Waiting for New HW board after thermal optimization to perform another test. [8/6]1.Power DB: Their software version has changed to disable fingerprint and magnetism, just get their latest board. Now the RBSC has decreased to 2.6mA. For the static image display current, need to debug further. 2.Thermal: Their DVT0 board didn’t review thermal hardware design with our engineer. It’s not surprising that the TPE test result is so poor. Liu Gang is doing reviewing and simulation together with BYD. [7/31] 1.RBSC is 8.32 (ref 1.67) and can be decreased to 4-5 by disable fingerprint 2. Static image display is 141.43 (ref 107.24) , Seems the gap of most failed cases are closed to the gap of static image display | yifeiz@qct.qualcomm.com ; 2016-10-14 01:39:16Z | Staffed/In progress | 2016-07-29 | 2016-07-29 | [10/14] No critical issue so far [09/30] No critical issue so far [09/23] Need customer check if any power saving changes can be done from FPS, sensoroutput, etc. [09/09] Cam recording temp is high, need do further thermal tunning [09/03] Need BYD capture tsens log to analyze hotspot [7/31] TPE test result seems not so good, need further tunning | yifeiz@qct.qualcomm.com ; 2016-10-14 01:39:16Z | Staffed/In progress | 2016-07-21 | 2016-07-21 | [08/26] No critical issues so far. [08/19] No critical issues so far. [08/12] No critical issues so far. already provide customer the detailed analysis. [08/05] detailed analysis is on-going, plan to release to customer at 08/10 [8/01] 1st round of ppt performance testing is finished and released to customer, detailed analysis is on-going. [7/22] 1st round of PPT performance profiling is on-going. For now, the data is not as good as expected. | yunguo@qct.qualcomm.com ; 2016-08-28 19:39:52Z | [30 empty] | tfei@qct.qualcomm.com ; 2018-10-16 02:47:41Z | [11 empty] | PM8953 |  |  | IoT Smart-Cities | Direct OEM Support |  | China | Integrated | Other | WCN |  | TDD/FDD | B3 (FDD); B5 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2018-12-01 Column68
China | Lenovo | 1-Diamond |  |  | River | Moto G | Wireless Device | SmartPhone | a0D3A00000OH5Kj | Jacala | MSM8953 | Beijing |  |  | PM8953 | WTR3925 |  | Third Party | None | QAT3550 (x2) | WCN3660B | WCN3660B | 3GB | 3000 | 6.5'' |  | 12M | Android P | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 | Next generation Moto G on SDM632 | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2018-12-30 | 2018-12-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *As Lenovo still no SDM632 contact, put this project onto MSM8953 | Gavin Song | 2018-03-26 | Completed | 2015-02-13 | 2015-02-13 |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 | 2015-03-05 |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:52:20Z | Completed | 2015-03-05 | 2015-03-05 |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-18 | 2015-03-18 |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:52:20Z | Completed | 2015-03-18 | 2015-03-18 | [6/12] get the S1p file, will start simulation this week | yajunc@qct.qualcomm.com ; 2017-06-11 17:59:18Z | Staffed/In progress | 2015-06-01 | 2015-06-01 |  | xiwang@qct.qualcomm.com ; 2016-08-29 21:22:52Z | Completed | 2015-07-15 | 2015-07-15 |  | huangeng@qct.qualcomm.com ; 2015-08-27 21:08:45Z | Completed | 2015-07-08 | 2015-07-08 | Lenovo use 3rd party audio codec, most tuning come from Wolfson as the codec vendor | huangeng@qct.qualcomm.com ; 2015-08-03 19:59:33Z |  | 2015-06-15 | 2015-06-15 |  | huangeng@qct.qualcomm.com ; 2015-08-27 21:08:45Z |  | 2015-07-13 |  |  | huangeng@qct.qualcomm.com ; 2015-08-27 21:08:45Z |  | 2015-07-12 |  |  | yanlongh@qct.qualcomm.com ; 2017-02-26 22:50:28Z |  | 2015-07-30 | 2015-07-30 |  | huangeng@qct.qualcomm.com ; 2015-08-27 21:08:45Z |  | 2015-05-15 | 2015-05-15 |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z |  | 2015-05-15 | 2015-05-15 |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:52:20Z | Completed | 2015-06-05 | 2015-06-05 |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z |  | 2015-07-15 | 2015-07-15 |  | huangeng@qct.qualcomm.com ; 2015-08-27 21:08:45Z | Planning | 2015-09-15 |  |  | huangeng@qct.qualcomm.com ; 2015-08-03 20:21:34Z | huangeng@qct.qualcomm.com ; 2018-10-10 06:58:57Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | Rev A | C850 ext BC0+BC10; C1900 + Blk G BC1 + BC14; C2100 BC6 | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | bar: 2018-12-01 Column68
China | Lenovo | 1-Diamond |  |  | Kunlun | K5X | Wireless Device | SmartPhone | a0D3A00000ORYyQ | Blackbolt | SDM636 | Beijing |  |  | PM660 | SDR660 |  | None | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 5MP | Android N | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SDM710.LA.2.0 | SB4 | *Next generation Moto G, high volume expected | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-04-15 |  | 2018-04-15 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *Lenovo China BU product | Gavin Song | 2018-08-15 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2017-08-17 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-08-15 07:35:42Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note: [9/28/2018] ODM project: Huaqin QL1655-Lenovo] |  |  |  | [9/28/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column69
China | Hisense | 2-Platinum |  |  | HLTE213M | HLTE213M | Wireless Device | SmartPhone | a0D3A00000OSLed | Hathi | SDM439 | Qingdao |  |  | PM439 | WTR2965 |  | None | Third Party | Third Party | WCN3680B | WCN3680B | 4GB | 4500 | 6.21 |  | 13M | Android O | SDM439.LA.1.0-00230-STD.PROD-1 | SDM439.LA.1.0 | SB4 | It is Hisense first 439 project. | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2018-09-04 | 2018-09-23 | 2018-10-05 | 2018-09-27 |  | 2018-09-28 | [5 empty] | 2018-10-23 | 2018-12-31 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * Derived from HLTE213T, target for CMCC.。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-23 15:59:35Z | [11 empty] | NA |  |  | Mobile | Direct OEM Support |  | China | Other | No NFC | None |  |  |  | No |  |  | Customer | [29 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | IDE8 Technology (Shanghai) Co., Ltd. | 4-Silver |  |  | Pulse |  | Wireless Device | SmartPhone | a0D3A00000OFF15 | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR4905 | Single SIM L/W/G/C | QFE2101 | Third Party | Third Party | WCN3660B | WCN3660B | 1GB | 3200 |  |  |  | Android N | MSM8909.LA.3.0 | MSM8909.LA.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2017-03-20 | 2017-05-18 | 2018-01-18 |  |  | 2017-11-11 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Baoming Zhang |  | 1 | 1 |  |  |  | * IDE8's 8909 smart phone project for Republic Wireless; * Carrier agreed with very limited lab certifications; * RD is on progress | Baoming Zhang | 2018-10-09 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-10-10 02:28:48Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B26 (FDD); B41 (TDD) | 1x | C850 BC0; C1900 BC1 | [31 empty] | Strongly Requested Filed: Device Official Name : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | OPPO | 1-Diamond |  |  | DD003_RJIL | NA | Wireless Device | SmartPhone | a0D3A00000ORXwh | Jacala | SDM450 | Shenzhen |  |  | PMI632;PM8953 | WTR2965 |  | QFE2101 | QPA8675;QPA8685 | Third Party | WCN3660B | WCN3660B | 2GB |  | 5.5" |  | 25M | Android N |  | SDM450.LA.3.2.c1 | SB4 | *OPPO 1st QPA project, Forecast 5KK. | Parent CP for Original design (OEM) |  | Under Acceptance | India - Reliance Jio (RJIL) | [11 empty] | 2018-12-31 | 2018-12-31 |  | Hongbo Chen | Nikhil Shevade | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *RJIL model | Zhiyang Gao | 2018-08-13 |  |  |  |  | qiw@qct.qualcomm.com ; 2016-05-16 00:30:01Z | [25 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [5 empty] | 2016-07-11 |  |  |  | Completed | 2016-08-22 |  |  |  | Staffed/In progress | 2017-10-30 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-10-19 10:16:10Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column69
China | ZTE | 1-Diamond |  |  | Z5151V | Z5151V | Wireless Device | SmartPhone | a0D3A00000OLFca | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 3100 | 5.45" | HD (1280x720) | 13M | Android O | Snapdragon_High_Med_2016.SPF.3.0.1.c2 | MSM8917.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless | 2017-12-27 | 2018-02-05 | 2018-03-14 | 2018-03-20 |  | 2018-02-22 |  | 2018-03-22 |  | 2018-04-23 |  | 2018-06-11 | 2018-12-31 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE-NA 8917 project for VzW VISIBLE. * VzW lab testing in progress. * Project status: confirmed, target TA by end of Dec. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-10-25 08:09:32Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Integrated | Other | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B13 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column69
China | Wind | 2-Platinum |  |  | D640 |  | Wireless Device | SmartPhone | a0D3A00000OePSM | Shanti | SDM632 | Shanghai |  |  | PM8953;PMI632 | WTR2965 |  | QET4101 | Third Party | Third Party | WCN3680B | WCN3680B | 4GB |  | 5.84 FHD+ |  | 13M | Android O |  | SDM632.LA.1.0 | SB4 | ODM for BQ as Bardock | ODM or partner CP associated with an indirect account |  | Evaluation | SEA - Open Market | 2018-07-23 | 2018-08-20 | 2018-09-17 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * review/DDR simulation finished, the project schedule is under discussion with their customer | Qiang Liu | 2018-08-26 | [85 empty] | qiangliu@qct.qualcomm.com ; 2018-11-26 07:09:40Z | [11 empty] | Other |  |  | Mobile |  |  | South East Asia (SEA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Evaluation project: No need CPI audit | bar: 2018-12-01 Column69
China | Huaqin | 2-Platinum |  |  | A6006-LTE |  | Wireless Device | Tablet | a0D3A00000OeNvI | Cheel | MSM8909 | Xi'an |  |  | PM8916 | WTR4905 |  | Third Party | None | None | WCN3610 | WCN3610 (BT) | 1GB | 7200 | 10.1" |  | 5M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | NA - Open Market | 2018-08-15 | 2018-09-30 | 2018-11-15 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Hongye Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * new LTE version project. all 1st PCBA bring up function finished * 3GB DDR bring up finished. * DVT is ongoing | Hongye Liu | 2018-11-26 | Completed |  |  |  | yizheny@qct.qualcomm.com ; 2015-07-10 01:51:30Z | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Planning |  |  |  |  | hongyel@qct.qualcomm.com ; 2018-09-17 05:31:50Z | [11 empty] | PM8916 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  | No | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 |  | [CCB Note: [7/27/2018] 8909 project, support case by case] |  |  |  | [7/27/2018 | [22 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column23: PVT; 2018-12-01 Column69: TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV-APQ8096-SOM |  | Wireless Device | IOT Industrial Handheld | a0D3A00000OGyTP | Istari | APQ8096 | Beijing |  |  | PM8996;PMI8994 | Other |  | None | None | None | QCA6174A-1 | QCA6174A-1 | 4GB |  | Null |  | 8M | Android M | MSM8996.LA.2.0-01600-STD.PROD-1 | MSM8996.LA.2.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-03-30 | 2018-05-30 | 2018-06-25 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | * Thundercomm APQ8096 SOM project. * It is D820 SOM. It is linked with Pinao project. * PM Wangwei 13910219876. * EVT was ready in May * DVT is ready and testing. | Jiuyao Shu | 2018-12-09 |  |  |  | JV’s reference design support | junjiel@qct.qualcomm.com ; 2016-04-22 02:04:21Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-10-29 06:19:19Z | [11 empty] | NA |  |  | IoT Smart-Cities | Transparent OEM Support |  | North America (NA) | NA | No NFC | None |  |  |  | No |  |  | Sensor Vendor | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | Di_820A_Demo | N/A | Wireless Device | Auto Infotainment | a0D3A00000OS7fk | IstariAU | APQ8096AU | Shenzhen |  |  | PMM8996AU | RGR7640AU |  | None | None | None | QCA6564AU-3 | QCA6564AU-3 | 4GB | 0 | 12.8" |  | 13M | Android O | MSM8996AU.LA.1.2 | MSM8996AU.LA.1.2 | SB4 | Didi demo project, will install on 10 cars. Further business will negotiate on top of this project. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-10-15 | 2018-01-10 | 2019-04-18 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Tianhao Fei |  | 1 | 1 |  |  |  | idi demo project. | Tianhao Fei | 2018-09-24 | [85 empty] | tfei@qct.qualcomm.com ; 2018-09-24 15:34:16Z | [11 empty] | WCD9335 |  |  | Automotive |  |  | China | Other | No NFC | WCN |  | No |  | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR4 | [28 empty] | Strongly Requested Filed: LTE Supported Bands : Empty CDMA Supported Bands : Empty | [177 empty] | PVT | bar: 2018-12-01 Column69
China | Quectel | 2-Platinum |  |  | EM12-G |  | Wireless Device | Embedded Module | a0D3A00000OM6pB | Stingray | SDX20 | Shanghai |  |  | PMX20 | SDR845 |  | QET4100 | QPM2622;QPM2632;QPM2642 | Third Party | QCA6174A-1 | No BT | 512MB |  |  |  |  | ThinUI (no MM) |  | SDX20.LE.1.1 | SB3 | Quectel’s first SDX20 design for Global Open Market | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-04-02 | 2018-07-02 | 2018-09-03 | [8 empty] | 2018-10-29 | 2018-12-31 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *Quectel SDX20 CAT12 Module to Global Open Market, Quectel's first SDX20 design-in. *Confirmed new design win as Laptop M.2 module to ACER and Technicolor *Reported that Rx Sensitivity is below Fibocomm's Intel modem << front-end loss is higher than competitor's ~1.5db. The difference comes from Extractor and Triplexer. | Li Wang | 2018-12-17 | [20 empty] | Staffed/In progress |  |  | [QPA-0330] • Customer raised RF BD review • SCH modification is still ongoing | qingweil@qct.qualcomm.com ; 2018-06-15 16:11:21Z |  |  |  |  | qingweil@qct.qualcomm.com ; 2018-07-20 01:35:15Z | [55 empty] | liw@qct.qualcomm.com ; 2018-11-28 06:15:48Z | [11 empty] | NA |  |  | Mobile |  |  | Rest of World (ROW) | NA | No NFC | None |  | FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B6 (FDD); B7 (FDD); B8 (FDD); B9 (FDD); B10 (FDD); B11 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B21 (FDD); B22 (FDD); B23 (FDD); B24 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Flextronics | 4-Silver |  |  | Venus_RJIL |  | Wireless Device | FeaturePhone | a0D3A00000OZNNo | Cheel | MSM8905 | Beijing |  |  | PM8909 | WTR2965 |  | None | None | None | WCN3610 | WCN3610 (BT) | 512MB |  | 2.4 |  |  | KaiOS |  | MSM8905.LF.1.3.1 | SB4 | MARS phase 2 project. | Parent CP for Original design (OEM) |  | Design/Development | India - Reliance Jio (RJIL) | 2017-03-10 | 2017-04-10 | 2017-05-10 | [8 empty] | 2018-05-30 | 2018-12-31 |  | Maharajan Panchanathan |  | 1 | 1 |  |  |  | *MARS phase 2 project.(Venus) *Same as MARS project. | Xiaoping Shi | 2018-03-04 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-12-03 05:44:19Z | [11 empty] | PM8909 |  |  | Mobile |  |  | India | NA | Undecided | WCN |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Suzhou Snail Digital Technology Co., Ltd. | 4-Silver |  |  | I7S | I7S | Wireless Device | SmartPhone | a0D3A00000Odd95 | Warlock | SDM670 | Shenzhen |  |  | PM670;PM670L | SDR660 |  | QET4100;QET4101 | QPA8802;QPA5460 | None | WCN3990 | WCN3990 BT | 6GB | 6000 | 6" |  | 16M | Android O |  | SDM710.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-06-12 | 2018-09-01 | 2018-11-01 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Training; Concept review; Kickoff meeting; Requirement Review; Schedule review; SW architecture review |  |  | * Snail first SDM710/670 project and HW design is ongoing. | Bruce Wang | 2018-05-20 | [20 empty] | Staffed/In progress |  |  |  | qingweil@qct.qualcomm.com ; 2018-06-15 16:12:21Z |  |  |  |  | qingweil@qct.qualcomm.com ; 2018-08-07 00:41:13Z | [55 empty] | wbruce@qct.qualcomm.com ; 2018-05-16 04:07:56Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support | 1020, 1030 | China |  | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | [29 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column9: PVT; 2018-12-01 Column69: TA
China | Quectel | 2-Platinum |  |  | EG12 |  | Wireless Device | Embedded Module | a0D3A00000ODweM | Stingray | SDX20 | Shanghai |  |  | PMX20 | SDR845 |  | QET4100 | Third Party | Third Party | QCA6174A-1 | No BT | 512MB |  | None |  | None | ThinUI (no MM) |  | SDX20.LE.1.1 | SB4 | Quectel’s first SDX20 design for Global Open Market | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-04-02 | 2018-07-02 | 2018-09-03 | [8 empty] | 2018-10-29 | 2018-12-31 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *Quectel SDX20 CAT12 Module to Global Open Market, using PCIE module and 3rd party PA. *Follow with EM12 as PCI-E module. | Li Wang | 2018-11-26 | [20 empty] | Planning | [64 empty] | liw@qct.qualcomm.com ; 2018-11-28 06:14:54Z | [11 empty] | NA |  |  | Mobile |  |  | Rest of World (ROW) | NA | No NFC | None |  | FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B6 (FDD); B7 (FDD); B8 (FDD); B9 (FDD); B10 (FDD); B11 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B21 (FDD); B22 (FDD); B23 (FDD); B24 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | ZTE | 1-Diamond |  |  | P809F15_O_Upgrade |  | Wireless Device | SmartPhone | a0D3A00000OCsfZ | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR4905 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 2GB | 4000 | 5.5" | HD (1280x720) | 8M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 | ZTE Blade Center's key 8909 project for Global Market. | MR - Updated OS |  | Design/Development | ROW - Open Market | 2018-01-25 | 2018-02-25 | 2018-04-10 |  |  | 2018-03-27 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * 8909 O upgrading model of P809F15 for ROW market | Baoming Zhang | 2018-10-09 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-10-10 02:27:31Z | [11 empty] | PM8909 |  |  | Mobile |  |  | Rest of World (ROW) | NA | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | C850 BC0 | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 |  | [CCB Note:[7/26/2018] upgarding project, support case by case] |  |  |  | [7/26/2018 | [22 empty] | Strongly Requested Filed: Device Official Name : Empty | bar: 2018-12-01 Column69
China | ZTE | 1-Diamond |  |  | N9137U | N9137U | Wireless Device | SmartPhone | a0D3A00000OMLwH | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR4905 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2115 | 5.0 | HD (1280x720) | 5M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - US Cellular | [5 empty] | 2018-05-07 |  | 2018-06-25 |  |  |  | 2018-08-12 | 2018-12-31 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE-NA 8909 Android Go project for USCC based on LA 3.0.1 PL. * Leverage the HW design as N9137. * Project status: suspend, still TBD. | Frank Lu | 2018-12-16 | [53 empty] | [2/2] 1.no urgent issue. [1/26] 1.no urgent issue. [1/19] 1.no urgent issue. [1/12] 1.no urgent issue. [1/7] 1.no urgent issue. from ZTE info, seems their US team is working on this project. [12/29] no urgent issue. [12/22] no urgent issue. [12/17] no urgent issue. | peshen@qct.qualcomm.com ; 2018-02-02 01:08:03Z | [30 empty] | yonggang@qct.qualcomm.com ; 2018-10-25 08:21:28Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | None |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B13 (FDD); B41 (TDD) | Rev A | C850 ext BC0+BC10; C1900 BC1 | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | bar: 2018-12-01 Column69
China | Wind | 2-Platinum |  |  | LDI-Y10 |  | Wireless Device | SmartPhone | a0D3A00000OCpcy | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR4905 |  | QFE2101 | Third Party | Third Party | WCN3610 | WCN3610 (BT) | 8GB | 2000 |  |  | 5M | Android M |  | MSM8909.LA.2.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Evaluation |  | 2017-06-14 | [10 empty] | 2018-12-31 | 2018-12-31 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  |  | Qiang Liu | 2018-01-07 | [85 empty] | qiangliu@qct.qualcomm.com ; 2018-11-26 07:10:01Z | [11 empty] | NA |  |  | Mobile |  |  |  | NA | No NFC | WCN |  | No | B1 (FDD); B3 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Evaluation project: No need CPI audit | bar: 2018-12-01 Column69
China | Linkchip | 1-Diamond |  |  | Q5002(Teelepoch)-Reseller | L50 | Wireless Device | SmartPhone | a0D3A00000OSoqH | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2000 | 5 |  |  | Android O |  | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Under Acceptance | NA - Verizon Wireless | 2018-04-14 | 2018-05-16 |  |  |  | 2018-03-18 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Schematics Review; Layout Review |  |  | *MSM8909 Reseller Project to Teleepoch for Verizon *Base on Q4501, 8909-6 + 2965-1, 16+16, Android O, SP ,Verizon,open market. *GCF Ongoing. | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-12-03 15:58:02Z | [11 empty] | PM8909 |  |  | Mobile | JV's Reference Design |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Huaqin | 2-Platinum |  |  | A6008-WiFi | Lenovo Achilles 4 | Wireless Device | Tablet | a0D3A00000OedBa | Cheel | MSM8909 | Shanghai |  |  | PM8909 | None |  | None | None | None | WCN3615 | WCN3615 | 2GB |  | 10.1 |  |  | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | ROW - Open Market | 2018-09-14 | 2018-10-31 | 2018-11-23 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Hongye Liu |  | 1 | 1 |  |  |  | * This project MSM8917 WIFI Tablet ODM for Lenovo. * DVT will be back in next week | Hongye Liu | 2018-11-26 | [28 empty] | 2 | [56 empty] | hongyel@qct.qualcomm.com ; 2018-09-17 05:37:25Z | [11 empty] | NA |  |  | Mobile |  |  | Rest of World (ROW) | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B38 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note:[9/28/2018] 8909 Tablet project, customer to handle by themselves] |  |  |  | [9/28/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column8: DVT; 2018-11-01 Column31: PVT; 2018-12-01 Column69: TA
China | Lenovo | 1-Diamond |  |  | Lake LTA | Moto G | Wireless Device | SmartPhone | a0D3A00000ODyuE | Blackbolt | SDM636 | XiaMen |  |  | PM660 | SDR660 |  | None | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 5MP | Android N | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SDM636.LA.2.1 | SB3 | *Next generation Moto G, high volume expected | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-04-15 |  | 2018-04-15 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *Wave2 SW freezed *Wave1 TA done， under production *Wave1 SW freezed *PVT done *Target freeze QC SW baseline on the 10/26 release *ADR on-final stage, pending on FR35486 to pass the NFC section *CTS/VTS pre-test going smooth. *System testing on-going. *Provided AI training to Lenovo *Lenovo no longer consider change platform. *Lenovo working on P early access SW *Bring up on-going, system brought up *EVB back at 5/24 *SDM636 ,Moto G * wait for 11/12 release for final release. | Gavin Song | 2018-12-18 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2017-08-17 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-04-18 06:47:46Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [606 empty] | TA | bar: 2018-12-01 Column69
China | BBK | 1-Diamond |  |  | PD1818F_EX(L+L) | Y95 | Wireless Device | SmartPhone | a0D3A00000OSeTS | Hathi | SDM439 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | Third Party | Third Party | None | WCN3660B | WCN3660B | 4GB | 4000 | 6.22" |  | 13MP | Android O | TBD | SDM439.LA.1.0.c2 | SB3 | First SDM439 L+L project with tight schedule and big volume forecast, Vivo/QC are doing joint-test for SEA(Taiwan)/India market. | Updated design | PD1818F_EX & BF_EX | Design/Development | SEA - Far Eastone Telecommunications Co. (Taiwan) |  | 2018-11-30 | 2018-12-31 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Jiaqi Fan | Karthik Koneru | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | *L+L upgrade for PD1818F_EX, TA plan on end/2018， *Target market India/SEA/Russi *QC/Vivo Joint test 12/3 -12/18 in 5 cities of India/Taiwan/Russia/Philippines. Vivo test in other 10+ cities. *L+L SW: QC 12/14 released post-CS version, Vivo plan finish update on 12/17, to start FT round2 test and lab stability test *Many modem issues reported. team are working with high priority.so far 26 highlighted issues, 6 remain. | Jiaqi Fan | 2018-12-17 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-09-02 00:16:33Z | [46 empty] | 2018-02-01 | [33 empty] | hongtaod@qct.qualcomm.com ; 2018-10-29 07:54:29Z | [11 empty] | PM8937 |  |  | Mobile |  |  | India; South East Asia (SEA) | Other | Other | WCN |  | TDD | B1 (FDD); B3 (FDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Third Party | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column38: DVT; 2018-12-01 Column69: PVT
China | Sierra Wireless, Inc. | 3-Gold |  |  | AR7582 |  | Wireless Device | Telematics | a0D3000000Ky6HN | Lykan | MDM9628 | Shenzhen |  |  | PMD9607 | WTR2965 | DSDA SVLTE+G | Third Party | Third Party | None | Other | Other | TBD/Unknown |  | None |  | None | Linux Other | Tip | MDM9607.LE.1.0.1 | SB3 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - AT&T Wireless | [5 empty] | 2016-12-01 | [5 empty] | 2017-07-31 | 2018-12-31 |  | Raj Pratha | Raj Pratha | 1 | 1 |  |  |  | * Case 02652662 - GNSS 10HZ feature in the roadmap of 9x28 firmware: QC informed Sierra that backporting the 10Hz operation is very difficult, and cannot be supported on LE1.0.1. * Case 02724870 – 9x28 Linux kernel: Customer is asking QC to explain how much man-hour would be needed to converge LK versions from 3.18.20 to 3.18.31. Based on this information, Sierra will go back to VW to push back. * Case 02684023 -SGMII wake up can't work: Need more info about use case from Sierra. | Juno Kwak | 2016-12-09 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-11-05 03:40:16Z | [11 empty] | WCD9306 |  |  | Automotive |  |  | North America (NA) | Other | No NFC | None |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B17 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Wind | 2-Platinum |  |  | Z225 |  | Wireless Device | SmartPhone | a0D3A00000OeG5n | Blackbolt | SDM636 | Shanghai |  |  | PM660L;PM660 | SDR660 |  | Third Party | Third Party | None | WCN3980 | WCN3980 BT | 4GB |  | 6.18" FHD+ |  | 20M+12M | Android O |  | SDM636.LA.2.1 | SB4 | 1st SDM630 project, ODM for Meizu | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-07-10 | 2018-08-06 | 2018-09-19 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *started trial production and focused on efficiency problem of production line, no critical issues in QC side, plan to start mass production from the end of Dec | Qiang Liu | 2018-12-16 | [40 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | qiangliu@qct.qualcomm.com ; 2018-12-17 07:48:22Z | [11 empty] | PM660 |  |  | Mobile |  |  | China; South East Asia (SEA) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Continental Automotive Guadalajara Mexico S.A. de C.V. | 4-Silver |  |  | BL28CN_GEELY_BT_SYN | CHINA TCAM BLE | Wireless Device | Auto Connectivity | a0D3A00000OduyI | Lykan | MDM9628 |  |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | QCA6564AU-3 | QCA6564AU-3 | 256MB |  |  |  |  | Linux Other |  | MDM9607.LE.2.0.1.c1 | SB4 | This is the lead Telematics Project for MDM928. | Parent CP for Original design (OEM) | BL28-Wi_Fi | Design/Development | China - China Mobile (CMCC) | [5 empty] | 2016-06-19 | [5 empty] | 2017-06-16 | 2018-12-31 |  | Raj Pratha | Raj Pratha | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Requirement Review |  |  | ustomer agreed to do a Kickoff Meeting. Schedule to be finalized. | Raj Pratha | 2018-06-01 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-11-05 03:41:14Z | [11 empty] | NA |  |  | Automotive |  | RF1956TR13, RF1492A | North America (NA) | NA | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Longcheer | 2-Platinum |  |  | L2300_Android_P_Upgrade | GM7 | Wireless Device | SmartPhone | a0D3A00000OS280 | Feero | MSM8940 | Shanghai |  |  | PM8940;PMI8940 | WTR3925 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 3GB |  | 5.7 HD+ 720*1440 |  | 13M | Android P |  | MSM8940.LA.3.1.2 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | WE - Open Market | 2017-08-05 | 2017-09-05 | 2017-10-15 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *Customer completed the requirements from GM, CTS self-test is ongoing | Qiang Liu | 2018-12-09 | [28 empty] | 2 | [56 empty] | qiangliu@qct.qualcomm.com ; 2018-09-18 08:21:15Z | [11 empty] | PM8937 |  |  | Mobile |  |  | Western Europe (WE) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B38 (TDD); B40 (TDD) | No |  | 1 High: Full QTI Support Required | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Fibocom Wireless Inc. | 3-Gold |  |  | NL668-757S-01 | NL668-757S-01 | Wireless Device | M2M Module | a0D3A00000OS1Oc | Lykan | MDM9607 | Shenzhen |  |  | PMD9607 | WTR2965 |  | None | None;Third Party | None | No WLAN | No BT | 128MB |  |  |  |  | ThreadX |  | MDM9607.TX.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-30 | 2018-10-30 | 2018-11-15 |  |  | 2018-11-01 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review |  |  | * PVT phase. L3 candidate image stress test on going and customer is planning to send module sample to end user for further TA test; * Passed the L3 phase, and plan to finish the L4 in this week. | Xiangkui Liu | 2018-12-16 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-09-17 06:55:19Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty |  | Column7: DVT; 2018-11-01 Column23: PVT; 2018-12-01 Column69: TA
China | Sierra Wireless, Inc. | 3-Gold |  |  | AR7592 |  | Wireless Device | Telematics | a0D3000000KxxYX | Tesla | MDM9640 | Shenzhen | MDM9640-0 |  | PMD9645 | WTR3925;WTR4905 | DSDA SVLTE+G | Third Party | Third Party | Third Party | Other | Other | TBD/Unknown |  |  |  |  | Linux Other | MDM9640.LE.3.1-00132-STD.PROD-1 | MDM9640.LE.3.1 | SB3 | * VW 2018 automotive business with MDM9240. * GCF/PTCRB: LE (Oct 2016), TA (Jan 2017) * AT&T: AVL testing (Nov 2016), TA (Apr 2017) * CCC: LE (Jan 2017), TA (Feb 2017) * NTT DoCoMo: LE (May 2017), TA (Jul 2017) | Parent CP for Original design (OEM) |  | Design/Development | NA - AT&T Wireless | [5 empty] | 2016-04-29 | [5 empty] | 2017-12-30 | 2018-12-31 |  | Raj Pratha |  | 1 | 1 |  |  |  | * AT&T: AVL testing (May 2017), TA (Dec 2017) | Juno Kwak | 2017-02-10 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-12-03 05:43:41Z | [11 empty] | WCD9304 |  |  | Automotive |  |  | North America (NA) | Other | No NFC | None |  | FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B29 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Shenzhen Heyuan Electronics Co., Ltd | 2-Platinum |  |  | X800AS | SUGAR Passion | Wireless Device | SmartPhone | a0D3A00000OeF1R | Jacala | SDM450 | Shenzhen |  |  | PMI8952 | WTR3925 |  | None | None | None | WCN3680B | WCN3680B | 3GB | 3250 | 5.2 |  | 16MP | Android N | SDM450.LA.3.1.1 | SDM450.LA.3.1.1 | SB4 | *Tinno's leading MSM8953 project.The forecast is 200K. | Updated design |  | Design/Development | China - Open Market | 2016-11-03 | 2016-12-30 | 2017-03-15 |  |  | 2017-03-15 | [5 empty] | 2018-10-31 | 2018-12-31 |  | Frank Lu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | * 4-mic design, plan to use Fluence Pro or 3rd party algo (TBD). * The test samples had been delivered to CMCC lab on 15th Nov. | Frank Lu | 2018-12-16 | [25 empty] | Staffed/In progress | 2016-12-01 | [13 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress | 2016-04-25 | [33 empty] | yonggang@qct.qualcomm.com ; 2018-10-22 09:17:37Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Customer | SDRAM-LPDDR3 |  | [CCB Note: [7/26/2018] SDM450/SB4 project, support case by case] |  |  |  | [7/26/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column69
China | Fibocom Wireless Inc. | 3-Gold |  |  | SC820-CN-50 | SC820-CN-50 | Wireless Device | IOT Smart POS | a0D3A00000OS7ZO | Jacala | MSM8953 | Shenzhen |  |  | PM8953;PMI8952 | WTR3925 |  | None | Third Party | None | WCN3660B | WCN3680B | 1GB | 4620 | 5" |  | 13M | Android N | MSM8953.LA.2.0 | MSM8953.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-07-28 | 2018-08-28 | 2018-10-10 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Smart POS module. Passed the L3 phase. * End customer develop their SW based one the Fibocom's SDK currently. | Xiangkui Liu | 2018-12-16 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-09-24 13:02:58Z | [11 empty] | PM8953 |  |  | IoT Smart-Cities | Direct OEM Support |  | North America (NA) | NA | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column69
China | Sierra Wireless, Inc. | 3-Gold |  |  | AR7594 |  | Wireless Device | Telematics | a0D3A00000OEqUm | Tesla | MDM9640 | Shenzhen | MDM9640-0 |  | PMD9645 | WTR3925;WTR4905 | DSDA SVLTE+G | Third Party | Third Party | Third Party | Other | Other | TBD/Unknown |  |  |  |  | Linux Other | MDM9640.LE.3.1-00132-STD.PROD-1 | MDM9640.LE.3.1 | SB4 | * VW 2018 automotive business with MDM9240. * GCF/PTCRB: LE (Oct 2016), TA (Jan 2017) * AT&T: AVL testing (Nov 2016), TA (Apr 2017) * CCC: LE (Jan 2017), TA (Feb 2017) * NTT DoCoMo: LE (May 2017), TA (Jul 2017) | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | [5 empty] | 2016-12-01 | [5 empty] | 2017-09-30 | 2018-12-31 |  | Raj Pratha | Raj Pratha | 1 | 1 |  |  |  | * LE (Dec 2016), TA (Apr 2017) | Juno Kwak | 2017-02-10 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-11-05 03:41:39Z | [11 empty] | WCD9304 |  |  | Automotive |  |  | Western Europe (WE) | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Sierra Wireless, Inc. | 3-Gold |  |  | AR8582 |  | Wireless Device | Telematics | a0D3A00000OEqVG | Lykan | MDM9628 | Shenzhen |  |  | PMD9607 | WTR2965 | DSDA SVLTE+G | Third Party | Third Party | None | Other | Other | TBD/Unknown |  |  |  |  | Linux Other | MDM9607.LE.1.0.1-00185-STD.PROD-1 | MDM9607.LE.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | [5 empty] | 2016-11-01 | [5 empty] | 2017-05-30 | 2018-12-31 |  | Raj Pratha | Raj Pratha | 1 | 1 |  |  |  | * Case 02652662 - GNSS 10HZ feature in the roadmap of 9x28 firmware: QC informed Sierra that backporting the 10Hz operation is very difficult, and cannot be supported on LE1.0.1. * Case 02724870 – 9x28 Linux kernel: Customer is asking QC to explain how much man-hour would be needed to converge LK versions from 3.18.20 to 3.18.31. Based on this information, Sierra will go back to VW to push back. * Case 02684023 -SGMII wake up can't work: Need more info about use case from Sierra. | Juno Kwak | 2016-12-09 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-11-05 03:41:59Z | [11 empty] | WCD9306 |  |  | Automotive |  |  | Western Europe (WE) | Other | No NFC | None |  | No |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Sierra Wireless, Inc. | 3-Gold |  |  | AR7588 |  | Wireless Device | Telematics | a0D3A00000OEqVB | Lykan | MDM9628 | Shenzhen |  |  | PMD9607 | WTR2965 | DSDA SVLTE+G | Third Party | Third Party | None | Other | Other | TBD/Unknown |  |  |  |  | Linux Other | MDM9607.LE.1.0.1-00185-STD.PROD-1 | MDM9607.LE.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | Japan - NTT DoCoMo | [5 empty] | 2017-05-31 | [5 empty] | 2017-07-31 | 2018-12-31 |  | Raj Pratha | Raj Pratha | 1 | 1 |  |  |  | * Case 02652662 - GNSS 10HZ feature in the roadmap of 9x28 firmware: QC informed Sierra that backporting the 10Hz operation is very difficult, and cannot be supported on LE1.0.1. * Case 02724870 – 9x28 Linux kernel: Customer is asking QC to explain how much man-hour would be needed to converge LK versions from 3.18.20 to 3.18.31. Based on this information, Sierra will go back to VW to push back. * Case 02684023 -SGMII wake up can't work: Need more info about use case from Sierra. | Juno Kwak | 2016-12-09 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-11-05 03:42:24Z | [11 empty] | WCD9306 |  |  | Automotive |  |  | Japan; Rest of World (ROW) | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B19 (FDD); B21 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Sierra Wireless, Inc. | 3-Gold |  |  | AR7584 |  | Wireless Device | Telematics | a0D3A00000OEqV1 | Lykan | MDM9628 | Shenzhen |  |  | PMD9607 | WTR2965 | DSDA SVLTE+G | Third Party | Third Party | None | Other | Other | TBD/Unknown |  |  |  |  | Linux Other | MDM9607.LE.1.0.1-00185-STD.PROD-1 | MDM9607.LE.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | [5 empty] | 2016-11-01 | [5 empty] | 2017-07-31 | 2018-12-31 |  | Raj Pratha | Raj Pratha | 1 | 1 |  |  |  | * Case 02652662 - GNSS 10HZ feature in the roadmap of 9x28 firmware: QC informed Sierra that backporting the 10Hz operation is very difficult, and cannot be supported on LE1.0.1. * Case 02724870 – 9x28 Linux kernel: Customer is asking QC to explain how much man-hour would be needed to converge LK versions from 3.18.20 to 3.18.31. Based on this information, Sierra will go back to VW to push back. * Case 02684023 -SGMII wake up can't work: Need more info about use case from Sierra. | Juno Kwak | 2016-12-09 | [85 empty] | chenpeng@qct.qualcomm.com ; 2018-11-05 03:42:48Z | [11 empty] | WCD9306 |  |  | Automotive |  |  | Western Europe (WE) | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | ZTE | 1-Diamond |  |  | WF723DL | WF723DL | Wireless Device | Fixed WAN Router | a0D3A00000OLB97 | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3680B | WCN3680B | 512MB | 2800 | No display |  |  | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Under Acceptance | NA - T-Mobile (USA) | [5 empty] | 2017-12-26 |  | 2018-01-09 |  |  |  | 2018-06-15 | 2018-12-31 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * 8909 fixed terminal project for Tracfone-TMO&VzW based on 8909 LA 3.0.1 Android O PL. * need to support TMO/VzW VoLTE and B14/B71. * no LCD, no GMS. * Project status: suspend. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-10-25 08:22:58Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  | FDD | B2 (FDD); B4 (FDD); B12 (FDD); B13 (FDD); B14 (FDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column69
China | Linkchip | 1-Diamond |  |  | F281(XF)-Reseller |  | Wireless Device | FeaturePhone | a0D3A00000OSi8d | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2000 | 5 |  |  | Android O |  | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Under Acceptance | NA - T-Mobile (USA) | 2018-06-18 | 2018-07-18 | 2018-09-10 |  |  | 2018-07-14 | [5 empty] | 2018-10-29 | 2018-12-31 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Schematics Review; Layout Review |  |  | *MSM8909 Reseller Project to Xingfei and branded with Coolpad. *Project further delayed to Dec/18 *To send final round of RC2 lab entry on 12/19 << Fixes with Wifi Standby current. *TMC- E911 regression test restarted << 3 failure techmemo given to TMO | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-12-03 15:51:57Z | [11 empty] | PM8909 |  |  | Mobile | JV's Reference Design |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Shanghai MobileTek Communication Ltd. | 4-Silver |  |  | L506X |  | Wireless Device | Embedded Module | a0D3A00000OSi8Y | Lykan | MDM9607 | Shanghai |  |  | PMD9607 | WTR2965 |  | QFE2101 | Third Party | None | No WLAN | No BT | 128MB |  |  |  |  | ThreadX | MDM9607.LE.1.0-00060-STD.PROD | MDM9607.TX.1.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-08-01 | 2018-09-01 | 2018-11-01 |  |  | 2016-02-25 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *9x07 Module project based on ThreadX for costdown. *General case support | Li Wang | 2018-11-19 | [24 empty] | liw@qct.qualcomm.com ; 2018-11-27 23:20:54Z | [60 empty] | liw@qct.qualcomm.com ; 2018-11-28 06:20:02Z | [11 empty] | NA |  |  | Mobile |  |  | China | Other | No NFC | None |  | FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column9: PVT; 2018-12-01 Column69: TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV-APQ8016-Haima |  | Wireless Device | Robotics | a0D3A00000OCzAF | Bagheera | APQ8016 | Beijing |  |  | PM8916 | Other |  | None | None | None | WCN3660B | WCN3660B | 1GB |  |  |  |  | Android L |  | APQ8016.LE.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2018-12-31 | 2018-12-31 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | *Thundercomm 8016 Robot project for MircoPoint. TC handle PCBA and SW. * Base project is JV-Poppy-ThreePapas, no big risk for this project. *HW Leader Name and Mobile#(BB and RF) Wang Shiqian 18665939856 *SW Leader Name and Mobile# Zhang Jianyong 18318036609 *Project Manager and Mobile# Lei Lei 13161162655 * DVT validation passed. * PVT need to modify I/O board due to customer change. TA date changed to 2018/12/30 due to long time validation . * Project delayed due to customer want to change ID. | Jiuyao Shu | 2018-12-09 |  |  |  | Transparent OEM support | [81 empty] | jshu@qct.qualcomm.com ; 2018-06-11 07:02:43Z | [11 empty] | NA |  |  | IoT Robotics | Transparent OEM Support |  | China | NA | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Motorola | 1-Diamond |  |  | Payton_P_India | Moto X | Wireless Device | SmartPhone | a0D3A00000OeIcG | Starhawk | SDM630 | Beijing |  |  | PM660 | SDR660 |  | QET4101 | Third Party | QAT3550 | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 12M | Android P | SDM630.LA.2.1.c1-00003-STD.PROD-1 | SDM630.LA.3.0 | SB4 | *This Payton project is for O-MR1 upgrade driven from MOTO-India office. *Hardware is same as original Payton device. *Leading SDM630 product, Moto G brand, high volume expected | MR - Updated OS |  | Design/Development | MEA - Open Market | 2016-03-07 | 2016-04-11 | 2016-07-25 | 2016-06-15 |  | 2018-11-09 | [5 empty] | 2018-10-08 | 2018-12-31 |  | Raheem Baig |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *SW freeze plan confirmed, to freeze onto the 7/28 post CS4 release *Move TA from 8/31 to 9/15 to reflect LenovSMT o internal process. *PVT on-going *Sporton 1st round testing done *Stability testing start *PPT 1st round lab testing done *ADR pre-test on-going， 1st round result expect ready by 6/22 *DVT1B done *DVT1 SMT done, samples back *the 5pcs pre-ES SDM630 bring up done, memory half speed issue solved *On-site support for tuner bring up | Raheem Baig | 2018-06-21 | Completed | 2018-01-23 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | chenpeng@qct.qualcomm.com ; 2018-12-03 05:46:22Z | [11 empty] | Other |  |  | Mobile |  |  | Middle East & Africa (MEA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 |  | [CCB Note:Lenovo BJ takes front camera tuning] |  |  |  | Lenovo BJ takes front camera tuning | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2018-12-01 Column69
China | ZTE | 1-Diamond |  |  | P845A02_Android_P_Upgrade | AXON 9 Pro | Wireless Device | SmartPhone | a0D3A00000ORSUH | Napali | SDM845 | Shanghai |  |  | PM8998 | SDR845 |  | QET4100 | Third Party | QAT3550 | WCN3990 | WCN3990 BT | 6GB |  | 6.21'' |  | 20M | Android P | SDM845.LA.2.0 | SDM845.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-01-22 | 2018-03-08 | 2018-04-10 |  |  | 2018-09-30 | [5 empty] | 2018-12-31 | 2018-12-31 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training |  |  | * ZTE SDM845 Android P upgrade project based on LA 2.0 PL. * Keep the same camera module as Android O project. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-10-25 08:19:43Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | [CCBNote:[7/26/2018] removed. Same camera mdule as P845A01] | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2018-12-01 Column69
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | HS501 | N/A | Wireless Device | IOT Industrial Handheld | a0D3A00000OLcBk | Jacala | MSM8953 | Shenzhen |  |  | PM8953;PMI8952 | WTR2965 |  | QFE2101 | Third Party | None | WCN3680B | WCN3680B | 2GB | 0 | 12.8" | FHD (1920x1080) | 13M | Android N | MSM8953.LA.2.0 | MSM8953.LA.2.0 | SB4 | BYD skyrail handheld device | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-12-30 | 2018-03-01 | 2018-04-05 | [8 empty] | 2018-12-31 | 2018-12-31 |  | Tianhao Fei |  | 1 | 1 |  |  |  | YD skyrail handheld | Tianhao Fei | 2017-12-04 | [85 empty] | tfei@qct.qualcomm.com ; 2018-11-20 06:08:40Z | [11 empty] | Other |  |  | IoT Smart-Cities | Direct OEM Support |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | bar: 2018-12-01 Column69
China | BBK | 1-Diamond |  |  | PD1805_P_upgrade | NEX S | Wireless Device | SmartPhone | a0D3A00000OeBHk | Napali | SDM845 | Shenzhen |  |  | PM8005;PM8998;PM845 | SDR845 |  | QET4101 | Third Party | QAT3518 | WCN3990 | WCN3990 BT | 8GB | 4000 | 6 |  | 12M+5M | Android P | TBD | SDM845.LA.2.0 | SB4 |  | MR - Updated OS | PD1805(ET2011) | Design/Development | China - Open Market | 2018-02-28 | 2018-04-18 | 2018-06-02 | [8 empty] | 2018-12-15 | 2019-01-02 |  | Hongtao Dong | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *Android P upgrade of NEX S; *Exact same SW with PD1821: MPSS cPL(MPSS.AT.4.0.c2.14) + others from SDM845.LA.2.0 mainline; *SW SE@Penglanhua. | Hongtao Dong | 2018-12-23 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z | [20 empty] | Staffed/In progress | 2016-07-11 | [13 empty] | Staffed/In progress | 2016-07-11 |  |  |  | Planning | 2016-08-14 |  |  |  | Staffed/In progress | 2018-04-01 | [28 empty] | Planning | 2016-02-20 |  |  |  | hongtaod@qct.qualcomm.com ; 2018-10-25 09:11:20Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B4 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR4X |  | [CCB Note: (10/31/2019) Upgrading project. changed to CUSTOMER] |  |  |  | (10/31/2019) Upgrading project. changed to CUSTOMER | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column71
China | Shanghai MobileTek Communication Ltd. | 4-Silver |  |  | T100 |  | Wireless Device | Telematics | a0D3A00000Oe7w6 | Lykan | MDM9628 | Shanghai |  |  | PMD9607 | WTR2965 |  | QFE2101 | Third Party | None | No WLAN | No BT | 256MB |  |  |  |  | Linux Other |  | MDM9607.LE.2.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-07-27 | 2018-10-16 | 2018-11-16 | [8 empty] | 2019-01-02 | 2019-01-02 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *Mobiletek Telematics Project. *General case support. | Li Wang | 2018-11-19 | [20 empty] | Staffed/In progress | 2015-09-25 | [63 empty] | liw@qct.qualcomm.com ; 2018-06-11 09:36:56Z | [11 empty] | NA |  |  | Automotive |  |  | China | Other | No NFC | None |  | FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column24: PVT; 2019-01-01 Column71: TA
China | Fibocom Wireless Inc. | 3-Gold |  |  | NL668-AM |  | Wireless Device | M2M Module | a0D3A00000OH6U2 | Lykan | MDM9607 | Shenzhen |  |  | PMD9607 | WTR2965 |  | None | None;Third Party | None | No WLAN | No BT | 256MB |  |  |  | 5M | Linux Other |  | MDM9607.LE.2.0 | SB4 |  | Existing design to a different carrier |  | Design/Development | ROW - Open Market | [11 empty] | 2018-11-30 | 2019-01-05 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * Module project for AM,LA market. * Finished the L3 phase, and plan to finished L4 phase in this week . | Xiangkui Liu | 2018-12-16 | [85 empty] | xiangkui@qct.qualcomm.com ; 2018-12-24 01:40:44Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | Latin America (LA); Rest of World (ROW) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B34 (TDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | bar: 2019-01-01 Column74
China | Wind | 2-Platinum |  |  | P118F |  | Wireless Device | Tablet | a0D3A00000Odekw | Jacala | SDA450 | Shanghai |  |  | Other | Other |  | Other | Other | Other | WCN3680B | WCN3680B | 3GB |  | 10.1’FHD 1920*1200 |  | 8M | Android O |  | SDM450.LA.3.0.1 | SB4 | ODM for BQ as Bardock | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-05-23 | 2018-06-17 | 2018-07-18 | [8 empty] | 2019-01-07 | 2019-01-07 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *iFlytek pull in schedule and plan to produce 1K pcs before the middle of Jan. *the project is in system test and debugging stage, plan to do PVT in Jan.2019 | Qiang Liu | 2018-12-16 | [85 empty] | qiangliu@qct.qualcomm.com ; 2018-12-03 06:15:00Z | [11 empty] | WCD9335 |  |  | Compute |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column76
China | Wind | 2-Platinum |  |  | A308 |  | Wireless Device | SmartPhone | a0D3A00000ORU8N | Feero | MSM8940 | Shanghai |  |  | PM8940;PMI8940 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3615 | WCN3615 | 1GB | 2800 | 5.2 |  | 8M | Android O |  | MSM8940.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | EE - Open Market | 2018-08-27 | 2018-09-24 | 2018-10-29 | [8 empty] | 2019-01-07 | 2019-01-07 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *All CTS issues were clarified, customer is preparing CTS report *ASUS smart phone project for oversea market, TA: Jan'19 | Qiang Liu | 2018-12-16 |  |  |  |  | tzhou@qct.qualcomm.com ; 2016-09-12 00:38:52Z | [80 empty] | qiangliu@qct.qualcomm.com ; 2018-12-03 06:16:30Z | [11 empty] | PM8937 |  |  | Mobile |  |  | Eastern Europe (EE) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B38 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column6: PVT; 2019-01-01 Column76: TA
China | Wingtech | 2-Platinum |  |  | S88567AC1-O upgrade | Xiaomi D1 | Wireless Device | SmartPhone | a0D3A00000OSnYR | Jacala | SDM450 | Shanghai |  |  | PM8953;Other | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3615 | Undecided | 3GB | 3000 | 5.2 |  | 12M | Android O | Snapdragon_High_Med_2016.SPF.1.0-05000-STD.PROD-1.60957.1 | SDM450.LA.3.1.1 | SB4 |  | MR - Updated OS | D1 | Design/Development | China - Open Market | 2016-01-28 | 2016-04-18 | 2016-05-27 | [8 empty] | 2019-01-08 | 2019-01-08 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * O upgrade | Tian Zhou | 2018-11-07 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [23 empty] | 4 | [11 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-11-07 08:36:13Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note: (11/23/2018) Upgrading project, leverage Xiaomi D1/S88567AA1, change owner to customer] |  |  |  | (11/23/2018) Upgrading project, leverage Xiaomi D1/S88567AA1, change owner to customer | [22 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column77
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | Wichita_Navigation |  | Wireless Device | Robotics | a0D3A00000OCtun | Cheel | APQ8009 | Beijing |  |  | PM8909;Other | Other |  | None | None | None | QCA6174A-3 | QCA6174A-3 | TBD/Unknown |  |  |  |  | Linux Other | APQ8009.LE.1.0.2 | APQ8009.LE.1.0.2 | SB4 | iRobot ODM , volume project, grass cutting robot | ODM or partner CP associated with an indirect account | iRobot-APQ8009-Wichita | Design/Development | [12 empty] | 2019-01-10 | 2019-01-10 |  | Tianhao Fei |  | 1 | 1 |  |  |  | Robot grass cutting, ODM project on APQ8909 Kick off from April, and plan to launch on Dec of 2018. P0 plan to be back on June. | Tianhao Fei | 2017-07-02 | [85 empty] | tfei@qct.qualcomm.com ; 2018-08-31 03:58:22Z | [11 empty] | PM8916 |  |  | IoT Robotics | Direct OEM Support |  |  | Other | No NFC | None |  | No |  | No | [32 empty] | Mandatory Filed: Operator1 : Empty Target Region : Empty Strongly Requested Filed: Device Official Name : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column79
China | Wingtech | 2-Platinum |  |  | S88505BC1- O upgrade | Xiaomi C3B | Wireless Device | SmartPhone | a0D3A00000OSnYH | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | None | None | None | WCN3615 | WCN3615 | 2GB | 3000 | 5 |  | 13M | Android O | Snapdragon_High_Med_2016.SPF.1.0-05000-STD.PROD-1 | MSM8917.LA.3.1.1 | SB4 |  | MR - Updated OS | C3B | Design/Development | China - Open Market | 2017-04-21 | 2017-05-20 | 2017-06-15 | [8 empty] | 2019-01-11 | 2019-01-11 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * O upgrade | Tian Zhou | 2018-11-07 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-11-07 08:36:34Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 |  | ODM： Xiaomi C3B] [CCB Note: (11/23/2018) Upgrading project, leverage Xiaomi C3B/S88505AA1, change owner to customer] |  |  |  | (11/23/2018) Upgrading project, leverage Xiaomi C3B/S88505AA1, change owner to customer | [22 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column80
China | Wingtech | 2-Platinum |  |  | Q88660A1 |  | Wireless Device | IOT Media Box | a0D3A00000OeCi8 | Starlord | SDM660 | Shanghai |  |  | PM660L;PM660 | None |  | None | None | None | WCN3980 | WCN3980 BT | 3GB |  | 5.5 |  | 24M | Android O |  | SDM660.LA.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-05-17 | 2018-09-17 | 2018-10-17 | [8 empty] | 2019-01-11 | 2019-01-11 |  | Andy Li |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Smart Projector for Tencent | Andy Li | 2018-06-14 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [35 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | junjiel@qct.qualcomm.com ; 2018-06-15 02:24:51Z | [11 empty] | PM660 |  |  | IoT Media/TV | Direct OEM Support |  | China | Other | No NFC | None |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column80
China | Wingtech | 2-Platinum |  |  | S88619AA1 | Moto | Wireless Device | SmartPhone | a0D3A00000OdT9S | Shanti | SDM632 | Shanghai |  |  | PM8953 | WTR3925 |  | QET4101 | Third Party | QAT3550 (x2) | WCN3615 | WCN3615 | 3GB | 3000 | 6.2 |  | 12M | Android O |  | SDM632.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-06-17 | 2018-08-17 | 2018-10-17 | [8 empty] | 2019-01-11 | 2019-01-11 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Similiar as S88618AA1, has different bands | Tian Zhou | 2018-08-22 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [35 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-12-16 11:40:21Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column80
China | Xiaomi | 1-Diamond |  |  | C3G | Xiaomi C3G | Wireless Device | SmartPhone | a0D3A00000ORuOQ | Feero Lite | MSM8917 | Shanghai |  |  | None | WTR2965 |  | None | None | None | WCN3615 | WCN3615 | 1GB | 3000 | 5 |  | 8M | Android O |  | MSM8917.LA.3.0.1 | SB3 | It is an Android O GO project with tough schedule, may have risks on performance and memory | Parent CP for Original design (OEM) | S88508AA1 | Design/Development | India - Open Market | 2018-09-07 | 2018-09-28 | 2018-10-26 | [8 empty] | 2019-01-11 | 2019-01-11 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Charger: BQ25601+CW2017 * Develop ongoing o MPSS CPL is locked, did the first release last week o FT in LA, Africa and India, many issues were reported, followed by many cases o Prepare for TA | Tian Zhou | 2018-12-23 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-12-16 11:39:35Z | [11 empty] | PM8937 |  |  | Mobile |  |  | India | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 |  | [CCB Note:[9/28/2018] ODM project: Wingtech S88508AA1] |  |  |  | [9/28/2018 | [22 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty |  | Column3: PVT; 2019-01-01 Column80: TA
China | Wingtech | 2-Platinum |  |  | P86255 | Lenovo PAD | Wireless Device | SmartPhone | a0D3A00000OekmO | Jacala | SDM450 | Xi'an |  |  | Other | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3660B | WCN3660B | 3GB | 4200 | 7 |  | 13M | Android P | Snapdragon_High_Med_2016.SPF.1.0-05000-STD.PROD-1.60957.1 | SDM450.LA.3.2.C1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-07-25 | 2018-08-24 | 2018-10-26 | [8 empty] | 2019-01-11 | 2019-01-11 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * PAD | Tian Zhou | 2018-12-09 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [23 empty] | 4 | [11 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-07-26 06:36:50Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Evaluation project: No need CPI audit |  | Column3: PVT; 2019-01-01 Column80: TA
China | Uniscope Technologies (Shanghai) Co., Ltd. | 3-Gold |  |  | H111 | TBD | Wireless Device | Robotics | a0D3A00000Odqd1 | Jacala | APQ8053 | Shanghai |  |  | PMI8952 | None |  | None | None | None | WCN3680B | WCN3680B | 1GB |  |  |  | 13M | Android O | TBD | APQ8053.LE.1.3 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-07-05 | 2018-08-30 | 2018-10-10 | 2018-09-10 |  | 2018-09-10 | [5 empty] | 2018-11-19 | 2019-01-14 |  | Bill Li |  | 1 | 1 |  |  |  | * Still looking for customers. * Customer downloaded it APQ8953.LE.1.3, customer finished bring-up. * Front camera driver need to be integrated. * EVT is back, bring-up is done, wait for real order. * New Robotic project with vlsam | Bill Li | 2018-12-16 |  |  |  |  | c_vingut@qct.qualcomm.com ; 2017-02-27 18:54:14Z | [80 empty] | binli@qct.qualcomm.com ; 2018-12-17 07:25:17Z | [11 empty] | PM8952 |  |  | IoT Robotics | Direct OEM Support |  | China | NA | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column83
China | Uniscope Technologies (Shanghai) Co., Ltd. | 3-Gold |  | PCBA OEM | H898 | H898 | Wireless Device | SmartPhone | a0D3A00000OGtHV | Jacala | SDM450 | Shanghai |  |  | PM8953;PMI8952 | WTR3925 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 2GB | 3200 | 5.7" |  | 16M | Android O | TBD | SDM450.LA.3.1.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | LA - Open Market | 2018-04-23 | 2018-06-27 | 2018-07-11 | 2018-05-17 |  | 2018-05-17 | [5 empty] | 2018-07-23 | 2019-01-14 |  | Bill Li |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Schematics Review; Layout Review; System Design Review |  |  | * CTS test passed, wait for order/payment. * Trial production done. * EVT is back, RF performance is not good enough, still need to optimize HW. | Bill Li | 2018-12-16 | [24 empty] | qingweil@qct.qualcomm.com ; 2015-08-20 23:50:58Z | [60 empty] | binli@qct.qualcomm.com ; 2018-12-17 07:25:40Z | [11 empty] | PM8953 |  |  | Mobile |  |  | Latin America (LA) | Integrated | Other | WCN |  | TDD/FDD | B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B17 (FDD); B38 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column83
China | ZTE | 1-Diamond |  |  | Z559CC | Z559DL | Wireless Device | SmartPhone | a0D3A00000OSu64 | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 2GB | 2200 | 5.0" FWVGA |  | 5M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Under Acceptance | NA - Open Market | 2018-01-05 | 2018-03-02 | 2018-03-26 |  |  | 2018-11-16 |  | 2018-03-12 |  | 2018-05-21 |  | 2018-12-24 | 2019-01-14 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE-NA 8909 Android O project for Consumer Cellular based on LA 3.0.1 PL. * Leverage the same HW as Z559DL. * Project status: confirmed, target TA by end of Dec 2018. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-12-24 05:53:28Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | Other | None |  | FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B13 (FDD) | No |  | 2 Medium: Case by Case Support On Demand |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column83
China | Uniscope Technologies (Shanghai) Co., Ltd. | 3-Gold |  | PCBA OEM | H18 | H18 | Wireless Device | SmartPhone | a0D3A00000OdHBE | Jacala | MSM8953 | Shanghai |  |  | PM8953;PMI8952 | WTR2965 |  | None | Third Party | None | WCN3680B | WCN3680B | 3GB | 5200 | 4.7" |  | 13M | Android O | TBD | MSM8953.LA.3.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-06-06 | 2018-07-10 | 2018-08-10 | 2018-07-10 |  | 2018-07-10 | [5 empty] | 2018-09-03 | 2019-01-14 |  | Bill Li |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Schematics Review; Layout Review; System Design Review |  |  | * Provided trial production HW to their customer, wait for further orders. Their customers are still testing. * DVT done. * EVT is back on Jun.7, bring-up is almost done. Third party is debugging some features related to interphone. * new 8953 project. EVT has been gerber out. | Bill Li | 2018-12-16 | [85 empty] | binli@qct.qualcomm.com ; 2018-12-17 07:26:12Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column83
China | Uniscope Technologies (Shanghai) Co., Ltd. | 3-Gold |  | PCBA OEM | H890 |  | Wireless Device | SmartPhone | a0D3A00000OdHB9 | Jacala | MSM8953 | Shanghai |  |  | PM8953;PMI8952 | WTR2965 |  | None | Third Party | Third Party | WCN3680B | WCN3680B | 3GB | 2600 | 5.7" |  | 13M | Android O | TBD | MSM8953.LA.3.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-05-25 | 2018-06-15 | 2018-07-20 | 2018-06-15 |  | 2018-06-15 | [5 empty] | 2018-08-20 | 2019-01-14 |  | Bill Li |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Schematics Review; Layout Review; System Design Review |  |  | * DVT will gerber out after EVT full verified, around middle of Jan. * EVT BB bring-up done, customer is optimizing RF. * New 8953 project. Will gerber out EVT after ID confirmation. ID/MD hasn't been confirmed yet | Bill Li | 2018-12-16 | [85 empty] | binli@qct.qualcomm.com ; 2018-12-10 07:46:16Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B9 (FDD); B12 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B26 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column83
China | Hisense | 2-Platinum |  |  | HLTE215E | HLTE215E | Wireless Device | SmartPhone | a0D3A00000OZmR3 | Hathi | SDM439 | Qingdao |  |  | PM439 | WTR2965 |  | None | Third Party | Third Party | WCN3680B | WCN3680B | 4GB | 4500 | 6.21 |  | 13M | Android O | TBD | SDM439.LA.1.0.1 | SB4 | It is Hisense first 439 project. | Parent CP for Original design (OEM) |  | Design/Development | LA - Nextel (Mexico) | 2018-09-04 | 2018-09-23 | 2018-10-05 | 2018-09-27 |  | 2018-09-28 | [5 empty] | 2019-01-14 | 2019-01-14 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * target for AT&T in Mexico | Weizheng Lv | 2018-12-18 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-19 07:21:55Z | [11 empty] | NA |  |  | Mobile | Direct OEM Support |  | China; Latin America (LA) | Other | No NFC | None |  |  |  | No |  |  | Customer | [29 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column83
China | Sony | 1-Diamond |  |  | Yoshino_Android_P_Upgrade_KDDI | Maple Gina Xperia XZ Premium PF11 | Wireless Device | SmartPhone | a0D3A00000OeTra | Nazgul | MSM8998 | Beijing |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | S001 TDK LB PAMiD | None | WCN3990 | WCN3990 BT | 4GB | 3230 | 5.5 |  | 19MP | Android P | MSM8998.LA.1.1.c2-00022-STD.PROD-1 | MSM8998.LA.1.1.c2 | SB4 |  | Existing design to a different carrier | Yoshino_Android_P_Upgrade | Design/Development | Japan - KDDI | 2016-11-01 | 2016-12-02 | 2017-01-21 |  |  | 2019-01-14 | [5 empty] | 2019-01-15 | 2019-01-15 |  | Huize Wang | Min-Ho Byun | 1 | 1 |  |  |  | * Yoshino P OTA for KDDI * Follow Yoshino P * Launch @week2, 2019 * No blocker issues. | Huize Wang | 2018-12-16 | Completed |  |  |  | tushiki@qct.qualcomm.com ; 2017-01-24 17:37:30Z | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | huizew@qct.qualcomm.com ; 2018-11-13 03:47:15Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China; Eastern Europe (EE); India; Korea; Latin America (LA); Middle East & Africa (MEA); North America (NA); Rest of World (ROW); South East Asia (SEA); Western Europe (WE) | WSA8810 x2 (Stereo) | Other | None |  |  |  | No |  |  |  | LPDDR4 | [28 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column84
China | Sony | 1-Diamond |  |  | Yoshino_Android_P_Upgrade_Softbank | Maple Gina Xperia XZ Premium PF11 | Wireless Device | SmartPhone | a0D3A00000OeTrf | Nazgul | MSM8998 | Beijing |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | S001 TDK LB PAMiD | None | WCN3990 | WCN3990 BT | 4GB | 3230 | 5.5 |  | 19MP | Android P | MSM8998.LA.1.1.c2-00022-STD.PROD-1 | MSM8998.LA.1.1.c2 | SB4 |  | Existing design to a different carrier | Yoshino_Android_P_Upgrade | Design/Development | Japan - SoftBank Mobile | 2016-11-01 | 2016-12-02 | 2017-01-21 |  |  | 2019-01-14 | [5 empty] | 2019-01-15 | 2019-01-15 |  | Huize Wang | Min-Ho Byun | 1 | 1 |  |  |  | * Yoshino P OTA for Softbank * Follow Yoshino P * OTA launch in Jan 2019 * No blocker issues. | Huize Wang | 2018-12-16 | Completed |  |  |  | tushiki@qct.qualcomm.com ; 2017-01-24 17:37:30Z | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | huizew@qct.qualcomm.com ; 2018-11-13 03:48:16Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China; Eastern Europe (EE); India; Korea; Latin America (LA); Middle East & Africa (MEA); North America (NA); Rest of World (ROW); South East Asia (SEA); Western Europe (WE) | WSA8810 x2 (Stereo) | Other | None |  |  |  | No |  |  |  | LPDDR4 | [28 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column84
China | Sony | 1-Diamond |  |  | Yoshino_Android_P_Upgrade_DCM | Maple Gina Xperia XZ Premium PF11 | Wireless Device | SmartPhone | a0D3A00000OeTrV | Nazgul | MSM8998 | Beijing |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | S001 TDK LB PAMiD | None | WCN3990 | WCN3990 BT | 4GB | 3230 | 5.5 |  | 19MP | Android P | MSM8998.LA.1.1.c2-00022-STD.PROD-1 | MSM8998.LA.1.1.c2 | SB4 |  | Existing design to a different carrier | Yoshino_Android_P_Upgrade | Design/Development | Japan - NTT DoCoMo | 2016-11-01 | 2016-12-02 | 2017-01-21 |  |  | 2019-01-14 | [5 empty] | 2019-01-15 | 2019-01-15 |  | Huize Wang | Min-Ho Byun | 1 | 1 |  |  |  | * Yoshino P OTA for DCM * Follow Yoshino P * Launch in Jan 2019 * No blocker issues. | Huize Wang | 2018-12-16 | Completed |  |  |  | tushiki@qct.qualcomm.com ; 2017-01-24 17:37:30Z | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | huizew@qct.qualcomm.com ; 2018-11-13 03:48:49Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China; Eastern Europe (EE); India; Korea; Latin America (LA); Middle East & Africa (MEA); North America (NA); Rest of World (ROW); South East Asia (SEA); Western Europe (WE) | WSA8810 x2 (Stereo) | Other | None |  |  |  | No |  |  |  | LPDDR4 | [28 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column84
China | FIH | 1-Diamond |  | Private Brand - Other | PLT_Android_P_Upgrade |  | Wireless Device | SmartPhone | a0D3A00000ORpV4 | Feero | MSM8937 | Zhengzhou |  |  | PM8937;PMI8952 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660B | WCN3660B | 3GB | 3000 |  |  | 16M | Android P |  | MSM8937.LA.3.1.2 | SB4 |  | MR - Updated OS | PLT | Design/Development | ROW - Open Market | 2016-12-16 | 2017-02-07 | 2017-03-26 | [8 empty] | 2019-01-15 | 2019-01-15 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review |  |  | * Android P upgrade for Nokia 6 * OTA launch in Jan 2019. * No critical issues so far | Huize Wang | 2018-12-02 |  |  |  |  | huizew@qct.qualcomm.com ; 2016-11-30 01:10:44Z | [80 empty] | huizew@qct.qualcomm.com ; 2018-12-02 14:45:57Z | [11 empty] | PM8937 |  |  | Mobile | Parallel Support |  | Rest of World (ROW) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | bar: 2019-01-01 Column84
China | Shenzhen Hipad Telecommunication Technology Co., Ltd. | 3-Gold |  |  | MI28A81 |  | Wireless Device | SmartPhone | a0D3A00000OHB7H | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3610 | WCN3610 (BT) | 512MB | 2000 | 4" |  | 8M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | [11 empty] | 2018-12-14 | 2019-01-15 | Waiting for market feedback of MI28A71 which using same ID | Jiaqi Fan |  | 1 | 1 | Access to Case granted; Schematics Review; Layout Review; Qualification: CDG |  |  | *Same ID as MI28A71_China project. use 8909 to enable CDMA user. *Launch for China market first. *Certification: CTA only *Status: DVT returned, Customer reschedule CTA plan, to decide CTA date after 8905 project with same ID launch.still waiting for Zimi's decide base on market feedback of MI28A71 which using same ID | Jiaqi Fan | 2018-12-16 | [85 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-17 03:36:07Z | [11 empty] | PM8909 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty | bar: 2019-01-01 Column84
China | Sony | 1-Diamond |  |  | Yoshino_Android_P_Upgrade_Momo | Maple Momo | Wireless Device | SmartPhone | a0D3A00000OSyXD | Nazgul | MSM8998 | Beijing |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | S001 TDK LB PAMiD | None | WCN3990 | WCN3990 BT | 4GB | 3230 | 5.5 |  | 19MP | Android P | MSM8998.LA.1.1.c2-00022-STD.PROD-1 | MSM8998.LA.1.1.c2 | SB4 |  | Existing design to a different carrier | Yoshino_Android_P_Upgrade | Design/Development | Japan - Open Market | 2016-11-01 | 2016-12-02 | 2017-01-21 |  |  | 2019-01-14 | [5 empty] | 2019-01-15 | 2019-01-15 |  | Huize Wang | Min-Ho Byun | 1 | 1 |  |  |  | * Yoshino P OTA for Momo * Follow Yoshino P. New variant. * Launch in Jan 2019 | Huize Wang | 2018-12-23 | Completed |  |  |  | tushiki@qct.qualcomm.com ; 2017-01-24 17:37:30Z | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Completed |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | huizew@qct.qualcomm.com ; 2018-11-19 01:50:27Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China; Eastern Europe (EE); India; Korea; Latin America (LA); Middle East & Africa (MEA); North America (NA); Rest of World (ROW); South East Asia (SEA); Western Europe (WE) | WSA8810 x2 (Stereo) | Other | None |  |  |  | No |  |  |  | LPDDR4 | [28 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column84
China | BBK | 1-Diamond |  |  | PD1730_TA3.0 update | Y85 | Wireless Device | SmartPhone | a0D3A00000OdPPW | Jacala | SDM450 | Shenzhen |  |  | PM8953;PMI8952 | WTR3925 |  | QFE2101 | Third Party | None | WCN3660B | WCN3660B | 4GB | 3150 |  |  | 16MP | Android O | TBD | SDM450.LA.3.1.1.c2 | SB4 |  | Updated design | PD1730 | Design/Development | China - Open Market | 2018-01-31 | 2018-02-28 | 2018-03-31 | [8 empty] | 2018-09-20 | 2019-01-16 |  | Hongtao Dong | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | *Representative CP of TA3.0 upgrade for Y85 and several TA2.3.c13 based 450/8953/8953pro model; *Upgraded to LA 3.1.1/TA.3.0 image status to get L+L; *Vivo has done the L+L field testing on pilot model, and all main issues have been addressed well. Vivo is preparing an OTA upgrade to market devices by e/Dec.2018; *Vivo expect a TA3.0 cPL on TA.3.0.c1 #202 build->MPSS cPL TA3.0.c8 created and released; *Few TA3.0 L+L new escalations under priority triage on vivo following OTA models | Hongtao Dong | 2018-12-23 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-09-02 00:16:33Z | [35 empty] | Staffed/In progress | 2017-06-01 |  |  |  | Staffed/In progress | 2017-06-01 |  |  |  | Staffed/In progress | 2016-09-01 | [33 empty] | hongtaod@qct.qualcomm.com ; 2018-12-24 01:29:54Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | [CCB Note:(05/25/2018) Upgrade project] [DRI/PoC:Weitao Lin/Chenlin Wang] | Weitao Lin/Chenlin Wang |  |  | (05/25/2018) Upgrade project | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column85
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | KC_MID |  | Wireless Device | SmartPhone | a0D3A00000OH88D | Starhawk | SDM630 | Shanghai |  |  | PM660;PM660L | SDR660 |  | QET4101 | Third Party | QAT3514;QAT3550;None | WCN3680B | WCN3980 BT | 3GB | 0 | 5" |  |  | Android O | SDM630.LA.2.1 | SDM630.LA.2.1 | SB4 | Kyocera ODM | ODM or partner CP associated with an indirect account |  | Design/Development | Japan - Open Market | 2015-12-30 | 2016-01-31 | 2016-03-30 | [8 empty] | 2019-01-16 | 2019-01-16 |  | Tianhao Fei |  | 1 | 1 |  |  |  | yocera ODM project | Tianhao Fei | 2018-03-29 | [40 empty] | Staffed/In progress | 2016-07-29 | 2016-07-29 | [10/14] No critical issue so far [09/30] No critical issue so far [09/23] RBSC is 3mA, a bit higher than QRD reference. Will do GPIO dump comparison then. [09/09] No critical issue so far [09/03] No critical issues so far. [08/26] No critical issues so far. [08/19] No critical issue so far. already provide customer the detailed analysis. [8/12]1.Power DB: No critical issue so far. already provide customer the detailed analysis. 2.Thermal DB: Waiting for New HW board after thermal optimization to perform another test. [8/6]1.Power DB: Their software version has changed to disable fingerprint and magnetism, just get their latest board. Now the RBSC has decreased to 2.6mA. For the static image display current, need to debug further. 2.Thermal: Their DVT0 board didn’t review thermal hardware design with our engineer. It’s not surprising that the TPE test result is so poor. Liu Gang is doing reviewing and simulation together with BYD. [7/31] 1.RBSC is 8.32 (ref 1.67) and can be decreased to 4-5 by disable fingerprint 2. Static image display is 141.43 (ref 107.24) , Seems the gap of most failed cases are closed to the gap of static image display | yifeiz@qct.qualcomm.com ; 2016-10-14 01:39:16Z | Staffed/In progress | 2016-07-29 | 2016-07-29 | [10/14] No critical issue so far [09/30] No critical issue so far [09/23] Need customer check if any power saving changes can be done from FPS, sensoroutput, etc. [09/09] Cam recording temp is high, need do further thermal tunning [09/03] Need BYD capture tsens log to analyze hotspot [7/31] TPE test result seems not so good, need further tunning | yifeiz@qct.qualcomm.com ; 2016-10-14 01:39:16Z | Staffed/In progress | 2016-07-21 | 2016-07-21 | [08/26] No critical issues so far. [08/19] No critical issues so far. [08/12] No critical issues so far. already provide customer the detailed analysis. [08/05] detailed analysis is on-going, plan to release to customer at 08/10 [8/01] 1st round of ppt performance testing is finished and released to customer, detailed analysis is on-going. [7/22] 1st round of PPT performance profiling is on-going. For now, the data is not as good as expected. | yunguo@qct.qualcomm.com ; 2016-08-28 19:39:52Z | [30 empty] | tfei@qct.qualcomm.com ; 2018-03-29 11:42:23Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | Japan | Integrated | Other | WCN |  | TDD/FDD | B3 (FDD); B5 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column85
China | ZTE | 1-Diamond |  |  | SW1001 |  | IOT | IOT Kids watch | a0D3A00000OedEZ | Cheel | MSM8909W | Shanghai |  |  | PM8916-1 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3610 | WCN3620 | 1GB | 2200 | 5" |  | 8M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-07-16 | 2018-08-15 | 2018-09-05 |  |  | 2018-02-26 | [5 empty] | 2019-01-10 | 2019-01-17 |  | Xiangkui Liu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * MSM8909W wearable project . * EVT pahse, as HW change , so the project will be delayed to end of Feb to TA. * Curently SW still do the function debugging the APP debugging * Don't do CTS for this project, and CTA on going . The first round field trail in 1/16. * Plan to MP in end of 2/2019 | Xiangkui Liu | 2018-12-23 | [85 empty] | xiangkui@qct.qualcomm.com ; 2018-10-09 07:27:13Z | [11 empty] | NA |  |  | IoT Wearable | Direct OEM Support |  | China | NA | No NFC | WCN |  | TDD/FDD | B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 |  | [CCB Assignment:Neo Zha] [CCB Support Type:DRI] [CCB Note:] [CCB Support Level:Low] [CCB Score:20] [DRI/PoC:Neo Zha] | Neo Zha | 20 | Low |  | DRI | Neo Zha | [20 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column86
China | Wingtech | 2-Platinum |  |  | T89571 | Nokia N3 - Panther | Wireless Device | SmartPhone | a0D3A00000ORXGo | Hathi | SDM439 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | Third Party | Third Party | None | WCN3615 | WCN3615 | 2GB | 3000 | 5 |  | 13M | Android P | Snapdragon_High_Med_2016.SPF.1.0-05000-STD.PROD-1 | SDM439.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-08-31 | 2018-09-21 | 2018-10-12 | [8 empty] | 2019-01-18 | 2019-01-18 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Bring up ongoing, nearly finished o Camera issue SR03748634 was fixed by onsite help o Will do Google's Android one test | Tian Zhou | 2018-11-25 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-11-28 03:31:45Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 |  | [CCB Assignment:Zhiqiang Jin, Gary Ge(Lab)] [CCB Support Type:DRI, Service Lab] [CCB Note:(8/22) Gary Ge(Lab): 8/24-8/31, ISP(1) ODM： Xiaomi C3B] [CCB Support Level:Mid] [CCB Score:26] [DRI/PoC:Zhiqiang Jin] | Zhiqiang Jin | 26 | Mid | (8/22) Gary Ge(Lab): 8/24-8/31, ISP(1) ODM： Xiaomi C3B | DRI, Service Lab | Zhiqiang Jin, Gary Ge(Lab) | [20 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column87
China | MeiG Smart Technology Co., Ltd. | 3-Gold |  |  | SLT183 | Tornado | Wireless Device | Tracking Device | a0D3A00000OeCqI | Lykan | MDM9206 | Xi'an |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | Other | No BT | 128MB |  |  |  |  | ThreadX | MDM9206.LE.2.0-00126-STD.PROD-1 | MDM9206.LE.2.0 | SB4 |  | Updated design |  | Design/Development | NA - Open Market | 2018-06-20 | 2018-08-10 | 2018-09-06 |  |  | 2018-08-03 | [5 empty] | 2018-12-21 | 2019-01-18 |  | Nicholas Chen |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * GCF test is ongoing on Sept/Oct'18, daily meeting arranged to expedite the process since mid of Sept'18. * MeiG froze SW on r00126, plan to upgrade to tip by Dec'18 * MeiG NB-IoT&eMTC tracker on MDM9206 + RTL8189 | Nicholas Chen | 2018-10-07 | [85 empty] | jic@qct.qualcomm.com ; 2018-12-17 09:11:28Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | North America (NA) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B26 (FDD); B28 (FDD); B39 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | bar: 2019-01-01 Column87
China | Shenzhen Hipad Telecommunication Technology Co., Ltd. | 3-Gold |  |  | QS5850 |  | Wireless Device | SmartPhone | a0D3A00000ODxht | Jacala | SDM450 | Shenzhen |  |  | PMI8952 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3660B | WCN3660B | 4GB | 3500 | 5.85 |  | 13M | Android O | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | EE - Open Market | [11 empty] | 2018-12-18 | 2019-01-18 | Customer reschedule project plan | Jiaqi Fan |  | 1 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review |  |  | * Smartphone, target market EU and LA, open market. * Certification: CE/FCC. * Status: EVT returned. Access of submitting SDM450 cases disable , contract colleagues notified that Hipad's commercial agreement did not include case support for SDM450. syncup with customer. sales colleague is helping on it. | Jiaqi Fan | 2018-08-06 |  |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [23 empty] | 4 | [56 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-24 05:13:13Z | [11 empty] | PM8953 |  |  | Mobile |  |  | Eastern Europe (EE); Latin America (LA) |  | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column87
China | Yulong | 2-Platinum |  |  | 301A |  | Wireless Device | Wearable | a0D3A00000OeJAa | Cheel | MSM8909W | Shenzhen |  |  | None | WTR2965 |  | QFE2101 | Third Party | None | WCN3620 | WCN3620 | 512MB |  |  |  |  | Android N |  | MSM8909W.LAW.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | [11 empty] | 2018-09-17 | 2019-01-18 |  | Min Fang |  | 1 | 1 |  |  |  | * Yulong wearable project for NA open; HW is same as Zeusis Grover; SW V1: 6/21; V2: 7/20; V3: 8/6; V4: 8/21; SW TA 12/21 * 3rd Server function on debugging. Yulong is pushing. | Min Fang | 2018-12-13 | [85 empty] | mfang@qct.qualcomm.com ; 2018-12-14 06:50:53Z | [11 empty] | PM8916 |  |  | IoT Wearable | Direct OEM Support |  |  |  | No NFC | None |  |  | B2 (FDD); B4 (FDD) | No | [32 empty] | Mandatory Filed: Target Region : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column87
China | Shadow Creator Information Technology Co., Ltd. | 4-Silver |  |  | A32 |  | Wireless Device | IOT AR | a0D3A00000OelDN | Napali | SDM845 | Shanghai |  |  | PM845;PMI8998 | None |  | None | None | None | WCN3990 | WCN3990 BT | 6GB |  |  |  |  | Android O |  | SDM845.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | [12 empty] | 2019-01-18 | 2019-01-18 |  | Andy Li |  | 1 | 1 |  |  |  | * AR glass device based on SDM845 | Andy Li | 2018-07-24 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-07-25 01:56:50Z | [11 empty] | WCD9340 |  |  | IoT VR/AR | Direct OEM Support |  | China |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Operator1 : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column87
China | Xiaomi | 1-Diamond |  |  | F1 | MI9 | Wireless Device | SmartPhone | a0D3A00000OM0ZC | Hana | SM8150 | Beijing |  |  | PM8150A;PM8150;PM8150B | SDR8150 |  | QET5100 | Third Party | Third Party | WCN3998 | WCN3998 | >4GB |  |  |  | 48M + 12M + 16M | Android P |  | SM8150.LA.1.0 | SB1 | XiaoMi 855 leading project | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-05-22 | 2018-07-19 | 2018-11-22 | [8 empty] | 2019-01-06 | 2019-01-20 |  | Wilson Fu | Michael Liu | 1 | 1 | Access to documentation granted; Access to Case granted; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | * XiaoMI first 855 project, target to trigger MP 1/4. * preMP @ 12/24, postcs5 upgrade done. * SW stable verison branch out @ 12/20, SW freeze @ 1/20, production line packaging @ 1/31 * Camera: 9 L1 camera cases; SD camp start & SHRD+CE support holiday; DXO 1st round result: photo=96. * * 2 L0 issues: SR#3785066 (Hynix low temperature)/ SR#3791573 (system hang) * 2DFA : camp arranged @ 12/25~29. * Launch event will be at MWC @ late of Feb. | Wilson Fu | 2018-12-23 | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:33:46Z | [5 empty] | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:25:47Z | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:30:41Z | [5 empty] | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:30:41Z | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:25:47Z | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:30:41Z | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:30:41Z | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:30:41Z | Staffed/In progress | 2018-10-08 |  |  | yunguo@qct.qualcomm.com ; 2018-11-04 23:48:30Z | [25 empty] | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:25:47Z | wilsonf@qct.qualcomm.com ; 2018-09-19 06:18:26Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | China | Other | SN100U | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm |  |  | [CCB Assignment: Mingchen Gao/Monkey Hou] [CCB Support Type: DRI] [CCB Note: (5/26/2018) Xiaomi next flagship, features under discussion] [CCB Support Level: High] [CCB Score: 34] [CCB Project Info: Project: F1, ID: a0D3A00000OM0ZC] [DRI/POC: Mingchen Gao/Monkey Hou] | Mingchen Gao/Monkey Hou | 34 | High | (5/26/2018) Xiaomi next flagship, features under discussion | DRI | Mingchen Gao/Monkey Hou | [20 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column30: PVT; 2019-01-01 Column89: TA
China | Shenzhen Kingsun Technology Co., Ltd. | 4-Silver |  | Private Brand - Jalasoft | H150 | H150 | Wireless Device | SmartPhone | a0D3A00000OSomL | Cheel | MSM8909 | Hangzhou |  |  | PM8909 | WTR4905 |  | None | Third Party | Third Party | WCN3610 | WCN3610 (BT) | 2GB | 2500 | 5 |  | 8M | Android N | MSM8909.LA.3.0-00030-STD.PROD-1 | MSM8909.LA.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-03-14 | 2017-04-20 | 2017-06-01 |  |  | 2017-04-30 |  | 2017-05-15 |  |  |  | 2018-02-26 | 2019-01-21 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * Derived 8909 project。 | Weizheng Lv | 2018-12-17 | [20 empty] | Completed | [64 empty] | wlv@qct.qualcomm.com ; 2018-11-08 07:47:57Z | [11 empty] | NA |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column90
China | Huaqin | 2-Platinum |  |  | QL1856-Asus |  | Wireless Device | SmartPhone | a0D3A00000OSDqd | Starlord | SDM660 | Shanghai |  |  | PM660L | SDR660 |  | QET4101 | Third Party | None | WCN3980 | WCN3980 BT | 4GB | 5000 | 6.3 |  | 12M | Android P | tbd | SDM660.LA.3.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | ROW - Open Market | 2018-11-10 | 2018-11-27 | 2018-12-29 | [8 empty] | 2019-01-21 | 2019-01-21 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | *it's pended by customer *Customer is still doing hardware design. Software development will start soon. * New 660-3 project | Qiang Liu | 2018-12-16 |  |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [80 empty] | binli@qct.qualcomm.com ; 2018-09-30 04:11:29Z | [11 empty] | PM660 |  |  | Mobile |  |  | India; Rest of World (ROW); South East Asia (SEA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR4X | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column18: EVT; 2018-11-01 Column35: DVT; 2018-12-01 Column67: PVT; 2019-01-01 Column90: TA
China | ZTE | 1-Diamond |  |  | P809V52 | Joker | Wireless Device | SmartPhone | a0D3A00000OLGAT | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR4905 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2200 | 5" | FWVGA (854x480) | 8M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 | ZTE Blade Center's key 8909 project with Android Go. | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2017-11-15 | 2017-12-18 | 2018-07-23 |  |  | 2018-02-26 | [5 empty] | 2019-01-22 | 2019-01-22 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * 8909 Android Go model with 5.0" FWVGA; * Turned to ROW Open Market. | Baoming Zhang | 2018-10-15 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-10-15 07:22:47Z | [11 empty] | PM8909 |  |  | Mobile |  |  | Rest of World (ROW) | NA | No NFC | WCN |  | TDD/FDD | B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 |  | [CCB Note:[7/26/2018] 8909 project support case by case] |  |  |  | [7/26/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column91
China | TCL | 2-Platinum |  |  | Watt US | Watt US | Wireless Device | SmartPhone | a0D3A00000Odb4I | Jacala | SDM450 | Shenzhen |  |  | PM8953 | WTR3925 |  | Third Party | Third Party | None | WCN3680B | WCN3680B | 3GB |  | 5.94inch HD+ notch/720X1560 |  | 8M FF | Android O | SDM450.LA.3.0.1 0.0.009.0 | SDM450.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-06-14 |  |  |  | 2018-08-08 | 2018-09-05 | [5 empty] | 2019-01-24 | 2019-01-24 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *new project android P designed by Huizhou team *Testing 1st HW version | Haijun Wang | 2018-12-03 | [28 empty] | 2 | [56 empty] | haijunw@qct.qualcomm.com ; 2018-07-19 03:45:39Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B6 (FDD); B8 (FDD); B19 (FDD); B38 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | OV12A(12M) +GC2375(2M ) | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column93
China | TCL | 2-Platinum |  |  | Gflip2 VZW |  | Wireless Device | FeaturePhone | a0D3A00000ORvSM | Cheel | MSM8909 | Ningbo |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 512MB | 1350 | 2.4 |  | 2M | Android O | MSM8909 | MSM8909.LA.3.1.1 | SB4 | It’s low entry feature phone for NA project launch | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless | 2018-10-16 | 2018-11-13 | 2018-12-26 | [8 empty] | 2019-01-24 | 2019-01-24 |  | Haijun Wang |  | 1 | 1 |  |  |  | *1st NA project MSM8909 with android Go * NRE agreement has been completed. *considering to support B71 for TMO new project.TA at end of September *Doing AT&T pre-cert LE *follow up some critical issues. | Haijun Wang | 2018-12-03 | [85 empty] | haijunw@qct.qualcomm.com ; 2018-09-11 03:20:41Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Integrated | No NFC | None |  | TDD/FDD | B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B25 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column21: DVT; 2018-12-01 Column64: PVT; 2019-01-01 Column93: TA
China | TCL | 2-Platinum |  |  | Edison | Edison——US | Wireless Device | SmartPhone | a0D3A00000Odj0X | Feero Lite | MSM8917 | Shenzhen |  |  | PM8937 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3615 | WCN3615 | 3GB |  | 5.5 HD+ 18:9, 720x1440 |  | 8M FF | Android O |  | MSM8917.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-06-14 |  |  |  | 2018-08-08 | 2018-09-05 | [5 empty] | 2019-01-24 | 2019-01-24 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *new project with android P designed by Huizhou team *Doing SW test and no critical issue until now *Returned 2st HW version this week. | Haijun Wang | 2018-12-03 | [28 empty] | 2 | [56 empty] | haijunw@qct.qualcomm.com ; 2018-07-23 05:55:16Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B6 (FDD); B8 (FDD); B19 (FDD); B38 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | OV12A(12M) +GC2375(2M ) | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column93
China | Shenzhen Kerun Visual Technology Co., Ltd. | 4-Silver |  |  | KR0820 |  | Wireless Device | IOT Robots | a0D3A00000OewSb | Istari | APQ8096 | Shenzhen |  |  | PM8996 | None |  | None | None | None | QCA6174A-1 | QCA6174A-1 | 4GB |  |  |  |  | Android M | tbd | MSM8996.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-10-16 | 2018-11-20 | 2019-01-10 | [8 empty] | 2019-01-25 | 2019-01-25 |  | Jiechu Gui |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | mart desk based on APQ8096 as APQ8076 will be EOL soon | Jiechu Gui | 2018-08-06 | [85 empty] | jgui@qct.qualcomm.com ; 2018-08-07 07:08:56Z | [11 empty] | WCD9335 |  |  | IoT Robotics | Direct OEM Support |  | North America (NA) | Other | No NFC | WCN |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column28: DVT; 2019-01-01 Column79: PVT; 2019-01-01 Column94: TA
China | Yulong | 2-Platinum |  |  | 3311A | Roadie | Wireless Device | SmartPhone | a0D3A00000OdUuR | Cheel | MSM8909 | Nanjing |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3610 | WCN3610 (BT) | 512MB | 1390 |  |  | 2M | Android O | MSM8909.LA.3.0.1-00032-STD.PROD-2 | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - T-Mobile (USA) | 2018-06-18 | 2018-07-20 | 2018-09-10 |  |  | 2018-09-26 |  | 2018-07-15 |  | 2018-08-15 |  | 2018-10-10 | 2019-01-25 | Wait for TMO Resource. | Min Fang |  | 1 | 1 |  |  |  | * Coolpad SZ 1st MSM8909 Project for NA TMO, Android GO; Support Band66+B71. * PVT phase. * RC2 Submission on 12/5 but yet to start test as wait in line, possibly 1/2. * SR#03761881 WFC power isseue need to soon be solved, 300ms verified in TMO lab. | Min Fang | 2018-12-20 | [85 empty] | mfang@qct.qualcomm.com ; 2018-12-17 06:42:53Z | [11 empty] | PM8909 |  |  | Mobile | Direct OEM Support | PA: SKY77643-61; Tuner: AW9304;switch: AW9106A |  | Other | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD) | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column94
China | Wingtech | 2-Platinum |  |  | S88770AA1 | AWS | Wireless Device | SmartPhone | a0D3A00000OSgSb | Blackbolt | SDM636 | Shanghai |  |  | PM660 | SDR660 |  | None | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 5.5 |  | 16M | Android O |  | SDM660.LA.2.1 | SB4 |  | Parent CP for Original design (OEM) | K9 Note | Design/Development | China - Open Market | 2018-10-31 | 2018-11-16 | 2018-12-14 | [8 empty] | 2019-01-25 | 2019-01-25 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Kick off | Tian Zhou | 2018-10-31 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [35 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-10-31 07:57:50Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column8: EVT; 2018-11-01 Column24: DVT; 2018-12-01 Column52: PVT; 2019-01-01 Column94: TA
China | Shenzhen Mobile CarLink Technology Inc. | 4-Silver |  |  | Z1702 |  | Automotive | Auto Infotainment | a0D3A00000OZOG0 | Feero | MSM8937 | Shanghai |  |  | PM8937 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3680B | WCN3680B | 2GB | 4000 |  |  |  | Android N | msm8937.LA.2.0.1 | MSM8937.LA.2.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | [11 empty] | 2019-01-28 | 2019-01-28 |  | Vivian Liu | Hongye Liu | 1 | 1 |  |  |  | * | Vivian Liu | 2018-03-06 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-09-13 03:41:23Z | [11 empty] | PM8937 |  |  | Automotive |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column97
China | Linkchip | 1-Diamond |  |  | Q5001(Teelepoch)-Reseller | L50 | Wireless Device | SmartPhone | a0D3A00000OTEBm | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2000 | 5 |  |  | Android O |  | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Under Acceptance | NA - T-Mobile (USA) | 2018-04-14 | 2018-05-16 |  |  |  | 2018-03-18 | [5 empty] | 2019-01-28 | 2019-01-28 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Schematics Review; Layout Review |  |  | *MSM8909 Reseller Project to Teleepoch for TMO *Base on Q4501, upgrade LCD to 5',8909-3 + 2965-1, 16+16,android O, SP,TF/TMO,in-stock *PTCRB ongoing. | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-12-03 15:56:42Z | [11 empty] | PM8909 |  |  | Mobile | JV's Reference Design |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column97
China | Wind | 2-Platinum |  |  | M500 |  | IOT | IOT Media Box | a0D3A00000OegUo | Warlock | SDA670 | Shanghai |  |  | PM670 | None |  | None | None | None | WCN3680B | WCN3680B | 4GB |  | 15.6(eDP)+10.1(Mipi) |  |  | Android N |  | SDM670.LA.1.0 | SB4 | ODM for BQ | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-07-30 | 2018-08-10 | 2018-09-17 | [8 empty] | 2019-01-28 | 2019-01-28 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *Customer is working with dingding on Adaptive display resolution requirement, plan to finalize TA SW by the end of Dec * It's a video conference system for Dingding team of Alibaba. The equipment is based on SDA 670, with USB camera and HDMI audio | Qiang Liu | 2018-12-16 | [85 empty] | qiangliu@qct.qualcomm.com ; 2018-11-26 07:27:27Z | [11 empty] | Other |  |  | IoT Media/TV | Direct OEM Support |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column97
China | Quectel | 2-Platinum |  |  | EC25-AF | Firstnet,CradlePoint | Wireless Device | Embedded Module | a0D3A00000OSybK | Lykan | MDM9607 | Shanghai |  |  | PMD9607 | WTR2965 |  | QFE2101 | Third Party | None | No WLAN | No BT | 256MB |  |  |  |  | Linux Other |  | MDM9607.LE.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | [11 empty] | 2019-01-28 | 2019-01-28 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Quectel MDM9x07 module project for NA Operator market on LE2.0 baseline *The OEM behind is FirstNet and Cradlepoint. *Support B71, B66 and B14 on HW. *Raised FRs on IMS feature backporting to LE2.0 to complaint with latest TMO and ATT spec << FR/CR porting will be all finished on 12/31 release and PDM reject Quectel to maintain a long life CPL but only shorter one and shift back to mainline after validation done. | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-11-28 06:19:31Z | [11 empty] | NA |  |  | Mobile |  |  | North America (NA) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column97
China | TCL | 2-Platinum |  |  | Minerva |  | Wireless Device | SmartPhone | a0D3A00000OdU9e | Blackbolt | SDM636 | Ningbo |  |  | PM660L;PM660 | SDR660 |  | QET4101 | Third Party | QAT3518;QAT3550 | WCN3980 | WCN3980 BT | 4GB |  | 5.99 inch |  | 12M+5M | Android O | SDM660.LA.2.1-21111-STD.PROD-1 | SDM636.LA.2.1 | SB4 | 2nd SDM636 project, ODM for Blackberry | Parent CP for Original design (OEM) |  | Design/Development | NA - AT&T Wireless | 2018-08-15 | 2018-12-18 | 2019-02-13 |  |  | 2018-08-29 | 2018-09-13 |  |  |  |  | 2019-01-29 | 2019-01-29 |  | Haijun Wang | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * SDM636 Smartphone for Blackberry, target for 1) CN, TW, HK open market 2)'NA(CA), Latam 3)EMEA&APEC *Doing SW&HW testing.HW returned back last week *No critical issue. | Haijun Wang | 2018-12-03 | [60 empty] | Planning | 2018-01-04 |  |  |  | Planning | 2018-02-21 | [18 empty] | haijunw@qct.qualcomm.com ; 2018-05-08 08:50:24Z | [11 empty] | PM660 |  |  | Mobile |  | NQ310 | North America (NA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B19 (FDD); B20 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD); B41-XGP (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | Main 12M AF(S5K2L8) +5M FF (Hi556) Sub 8M（S54H7） | [26 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column56: DVT; 2019-01-01 Column98: TA | [13 empty] | PVT
China | Lenovo | 1-Diamond |  |  | Rugby Go | Moto E | Wireless Device | SmartPhone | a0D3A00000OerZP | Feero Lite | MSM8917 | Nanjing |  |  | PM8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 3GB | 5000 | 6'' |  | 16M | Android P | MSM8937.LA.3.0 | MSM8940.LA.3.0.1.c1 | SB4 | *Next generation Moto E | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2017-09-09 | 2017-10-12 | 2018-01-24 |  |  | 2018-03-19 | [5 empty] | 2019-01-30 | 2019-01-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *Rugby 1G SKU, with Andorid Go *Android Go 1G RAM device | Gavin Song | 2018-08-01 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-10-08 02:37:53Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note:[9/28/2018] 8917 project, customer to handle by themselves] |  |  |  | [9/28/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column99
China | Lenovo | 1-Diamond |  |  | Zap Andorid P upgrade | TBD | Wireless Device | SmartPhone | a0D3A00000OSZo4 | Warlock | SDM710 | Beijing |  |  | PM670 | SDR660 |  | Third Party | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 24MP | Android P |  | SDM710.LA.1.0 | SB4 | Lenovo China BU 1st in house project | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2016-03-07 | 2016-04-11 | 2016-07-25 | 2016-06-15 |  | 2016-06-15 | [5 empty] | 2019-01-30 | 2019-01-30 |  | Gavin Song |  | 0 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *PVT SMT on-going *DXO 3rd round on-going *3rd party audio codec get critical issue, that no audio happen frequently *PPT done *FT1 on-going *DVT1B SMT done *System testing start *EVT2 SMT done *Bring up done. *EVB back *ZUK SDM710 project | Gavin Song | 2018-10-23 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-10-24 06:13:54Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note: (10/31/2018) Upgrading project. changed to CUSTOMER] |  |  |  | (10/31/2018) Upgrading project. changed to CUSTOMER | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column99
China | Lenovo | 1-Diamond |  |  | Lake EMEA | Moto G | Wireless Device | SmartPhone | a0D3A00000OSZoE | Blackbolt | SDM636 | XiaMen |  |  | PM660 | SDR660 |  | None | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 5MP | Android N | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SDM636.LA.2.1 | SB4 | *Next generation Moto G, high volume expected | Parent CP for Original design (OEM) |  | Design/Development | MEA - Open Market | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-04-15 |  | 2018-04-15 | [5 empty] | 2019-01-30 | 2019-01-30 |  | Gavin Song |  | 0 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *PVT on-going *Target freeze QC SW baseline on the 10/26 release *ADR on-final stage, pending on FR35486 to pass the NFC section *CTS/VTS pre-test going smooth. *System testing on-going. *Provided AI training to Lenovo *Lenovo no longer consider change platform. *Lenovo working on P early access SW *Bring up on-going, system brought up *EVB back at 5/24 *SDM636 ,Moto G | Gavin Song | 2018-10-23 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2017-08-17 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-10-24 06:16:57Z | [11 empty] | Other |  |  | Mobile |  |  | Middle East & Africa (MEA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note: (11/1/2018) Leverage Lake LTA. changed to CUSTOMER] |  |  |  | (11/1/2018) Leverage Lake LTA. changed to CUSTOMER | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column99
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_SDM660_NG521 |  | Wireless Device | SmartPhone | a0D3A00000OT1e7 | Starlord | SDM660 | Shanghai |  |  | PM660;PM660L | SDR660 |  | QET4101 | Third Party | None | WCN3990 | WCN3990 BT | 6GB | 4000 |  |  | 16MP | Android O |  | SDM660.LA.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2018-05-21 | 2018-08-30 | 2018-12-20 | [8 empty] | 2019-01-30 | 2019-01-30 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Concept review; Kickoff meeting; Schematics Review; Layout Review |  |  | * SIM Shanghai project . * PL: zuo hongyan 18121093752 | Jiuyao Shu | 2018-12-23 | [85 empty] | jshu@qct.qualcomm.com ; 2018-11-22 08:10:32Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China | WSA8815 | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column58: PVT; 2019-01-01 Column99: TA
China | Quli Information Technology Co., Ltd. dba Movision Tech | 4-Silver |  |  | A2_3Glass |  | Wireless Device | IOT AIO VR | a0D3A00000OSsH4 | Kingsman | SXR1130 |  |  |  | PM670 | None |  | None | None | None | WCN3990 | WCN3990 BT | 3GB |  |  |  |  | Android O |  | SXR1130.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | [12 empty] | 2019-01-30 | 2019-01-30 |  | Andy Li |  | 1 | 1 |  |  |  | * SXR1130 discrete VR device for 3Glass | Andy Li | 2018-11-11 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-11-12 05:51:41Z | [11 empty] | NA |  |  | IoT VR/AR | Direct OEM Support |  |  |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Operator1 : Empty Target Region : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | bar: 2019-01-01 Column99
China | Lenovo | 1-Diamond |  |  | JD19 | TBD | Wireless Device | SmartPhone | a0D3A00000OeSpx | Warlock | SDM710 | Beijing |  |  | PM670 | SDR660 |  | Third Party | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 24MP | Android P |  | SDM710.LA.1.0 | SB4 | Lenovo China BU 1st in house project | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2016-03-07 | 2016-04-11 | 2016-07-25 | 2016-06-15 |  | 2016-06-15 | [5 empty] | 2019-01-30 | 2019-01-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *Change from ODM to in house | Gavin Song | 2018-07-03 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-08-15 07:06:30Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note:ODM project: Huaqin QL1822- Lenovo] |  |  |  | ODM project: Huaqin QL1822- Lenovo | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | bar: 2019-01-01 Column99
China | OnTim | 3-Gold |  |  | (QSIP)ZB634KL |  | Wireless Device | SmartPhone | a0D3A00000OS3JZ | Jacala | SDM450 | Beijing |  |  | PMI632;PMI8952 | None |  | QFE2101 | QFE2340 | Third Party | WCN3980 | WCN3980 BT | 4GB | 3400 | 5.65 | FHD (1920x1080) | 13MP | Android P |  | SDM450.LA.3.1.1 | SB3 | *QSIP project for Asus. *Target market is Brazil | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | [11 empty] | 2019-01-30 | 2019-01-30 |  | Xiaoping Shi | Karnakoti Narayana | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | * QSIP project for Asus. * Target market is Brazil * OnTim/Asus didn't agree to use PMI632. Will launch it with PMI8952 and Android O. * EVT(Started from 10/15). Done. * Next milestone is DVT1.(11/23). * Pre CTS done. * Switch HAL3 to HAL1. * It is on tracking. | Xiaoping Shi | 2018-12-23 | [85 empty] | fmitkus@qct.qualcomm.com ; 2018-10-16 13:25:22Z | [11 empty] | PM8952 |  |  | Mobile |  |  | Latin America (LA) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | bar: 2019-01-01 Column99
China | OPPO | 1-Diamond |  |  | TD11860_mmW |  | Wireless Device | SmartPhone | a0D3A00000ORj9i | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | Third Party | QPA2625;QPM4620;QPM4630;QPM4641;QPM5650 | Third Party | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | [SM8150.LA.1.5 + SDX50M.TN.2.0].r1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-11-23 | 2019-01-07 | 2019-01-22 | [8 empty] | 2019-01-31 | 2019-01-31 |  | Magic Wang |  | 1 | 1 |  |  |  | * This project is just for mmW evaluaiton, with R17 HW ID | Magic Wang | 2018-08-27 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-08-27 08:36:56Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Evaluation project: No need CPI audit |  | 2018-11-01 Column31: EVT; 2019-01-01 Column76: DVT; 2019-01-01 Column91: PVT | TA
China | OPPO | 1-Diamond |  |  | TD11870 |  | Wireless Device | SmartPhone | a0D3A00000ORj9Y | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | QPM6580;QPM5651;QPM4620;QPM5650 | Third Party | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | [SM8150.LA.1.5 + SDX50M.TN.2.0].r1 | SB3 | This project need to support n41/n78/n79, it is for 2019 MWC demo and 3 China operators demo. | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-11-07 | 2018-12-21 | 2019-01-11 | [8 empty] | 2019-01-31 | 2019-01-31 |  | Magic Wang |  | 1 | 1 |  |  |  | * This project is China 3 operators demo, with Find X HW ID. * Need to support 5G 3 bands n41/n78/n79 * No blocking issues | Magic Wang | 2018-12-23 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-09-10 08:03:48Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Evaluation project: No need CPI audit |  | 2018-11-01 Column15: EVT; 2018-12-01 Column59: DVT; 2019-01-01 Column80: PVT | TA
China | OPPO | 1-Diamond |  |  | TD11803 |  | Wireless Device | SmartPhone | a0D3A00000OSZqU | Napali | SDM845 | Shenzhen |  |  | PM8005;PM845;PM8998 | SDR845 |  | QET4100 | Third Party | None | WCN3990 | WCN3990 BT | 8GB | 3500 | 7.7 & 5.45 |  | tbd | Android O |  | SDM845.LA.1.0.1.c4 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-08-25 | 2018-10-13 | 2018-11-10 | [8 empty] | 2019-01-31 | 2019-01-31 |  | Magic Wang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Schematics Review; Layout Review; SW architecture review |  |  | * This is Eval project for display dual panel. * project target is for MWC 2019 demo | Magic Wang | 2018-10-24 | [85 empty] | qiw@qct.qualcomm.com ; 2018-10-24 08:41:04Z | [11 empty] | WCD9341 |  |  | Mobile | Direct OEM Support |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B14 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B29 (FDD); B30 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR4X |  | Dual PD or Optical Zoom not fixed | [26 empty] | Evaluation project: No need CPI audit |  | 2018-11-01 Column18: PVT | TA
China | GoerTek Inc. | 4-Silver |  |  | Air_camera_Pico |  | Wireless Device | Connected Camera | a0D3A00000Odldh | RedDragon | QCS605 | Beijing |  |  | PM670 | None |  | None | None | None | WCN3990 | WCN3990 BT | 4GB |  |  |  |  | Android O |  | QCS605.LA.1.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | [11 empty] | 2019-01-31 | 2019-01-31 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Pico's VR camera project * Launch in Jan 2019 | Huize Wang | 2018-12-23 | [85 empty] | huizew@qct.qualcomm.com ; 2018-11-09 02:18:32Z | [11 empty] | PM660 |  |  | IoT Connected Camera | Direct OEM Support |  | China |  | No NFC | None |  | No |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [100 empty] | TA
China | GoerTek Inc. | 4-Silver |  |  | Air_Light_Pico |  | Wireless Device | Media | a0D3A00000OSqhk | RedDragon | QCS605 | Beijing |  |  | PM670 | None |  | None | None | None | WCN3990 | WCN3990 BT | 4GB |  |  |  |  | Android O |  | QCS605.LA.1.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | [11 empty] | 2019-01-31 | 2019-01-31 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Pico's smart projector project * Launch in Jan 2019. * Demo in CES 2019. | Huize Wang | 2018-12-23 | [85 empty] | huizew@qct.qualcomm.com ; 2018-11-09 03:09:56Z | [11 empty] | PM660 |  |  | IoT Media/TV | Direct OEM Support |  | China |  | No NFC | None |  | No |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [100 empty] | TA
China | Shenzhen Yuantongcheng Technology Co., Ltd. | 4-Silver |  |  | QRD-A8017M |  | Wireless Device | Tablet | a0D3A00000OMMyL | Feero Lite | APQ8017 | Shenzhen |  |  | PM8937 | None |  | None | None | None;Third Party | WCN3615 | WCN3615 | 3GB |  |  | FHD (1920x1080) | 16MP | Android N |  | APQ8017.LE.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2018-12-14 | 2019-01-31 | Change to U-BLOX GPS since final customer request high GPS performance(SAP/10Hz), | Jiaqi Fan |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | *Tablet without modem. *APQ8017.LE.1.1. | Xiaoping Shi | 2018-04-22 | [85 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-17 03:07:30Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | NA | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0; C1900 BC1 | 1 High: Full QTI Support Required |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty Display Physical Size (inches) : Empty | [100 empty] | TA | [502 empty] | TA
China | Lenovo | 1-Diamond |  |  | Heart | Heart | Wireless Device | SmartPhone | a0D3A00000OeRwW | Hana | SM8150 | Beijing |  |  | PM8150 | SDR8150 |  | None | Third Party | QAT3550 | WCN3998 | WCN3998 | 3GB | 3000 | 6'' |  | 16MP + 24MP | Android P |  | SM8150.LA.1.0 | SB3 | China BU SDM855 product | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-03 | 2018-10-14 | 2018-11-15 | 2016-06-15 |  | 2018-11-15 | [5 empty] | 2018-12-30 | 2019-01-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *Product announced at 18th Dec, 1st shipment target at 24th Jan. *SW target freeze at 10th Jan. *User trial start. *PVT tape out *CTA on-going *ST on-going *SW development behind schedule, engineering resource impacted by 710 projects *Lenovo China BU SDM8150 project *Very aggressive schedule *DVT devices back *EVT bring up done | Gavin Song | 2018-12-18 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-12-19 06:23:29Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column23: PVT | TA | [503 empty] | TA
China | OPPO | 1-Diamond |  |  | AD066 |  | Wireless Device | SmartPhone | a0D3A00000OSSJQ | Warlock | SDM710 | Shenzhen |  |  | PM670;PM670A | SDR660 |  | QET4101 | Third Party | QAT3518 | WCN3990 | WCN3990 BT | 8GB | 3000 | 6" |  | 16M + 5M | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SDM710.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-15 | 2018-12-15 | 2019-01-18 | [8 empty] | 2019-01-31 | 2019-01-31 |  | Magic Wang | Nikhil Shevade | 1 | 1 |  |  |  | * SDM710 project | Magic Wang | 2018-10-16 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [45 empty] | Staffed/In progress | 2018-01-04 | [33 empty] | ezhao@qct.qualcomm.com ; 2018-10-30 02:01:08Z | [11 empty] | NA |  |  | Mobile |  | QDM2305 | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B10 (FDD); B18 (FDD); B19 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column23: EVT; 2018-12-01 Column53: DVT; 2019-01-01 Column87: PVT | TA
China | Fibocom Wireless Inc. | 3-Gold |  |  | NL678-LA |  | Wireless Device | Embedded Module | a0D3A00000OH6U7 | Tesla | MDM9640 | Shenzhen |  |  | PMD9645 | WTR3925 |  | QFE3100 | Third Party | None | No WLAN | No BT | 512MB |  |  |  |  | Linux Other |  | MDM9640.LE.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2018-04-09 | 2018-06-18 | 2018-09-30 |  |  | 2018-09-01 | 2018-12-01 |  |  |  |  | 2019-01-31 | 2019-01-31 |  | Xiangkui Liu |  | 0 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schedule review |  |  | * Module project for LA market. * Evaluation phase, Still ongoing the end customer project requirement and project related evaluation | Xiangkui Liu | 2018-12-02 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-06-05 03:45:46Z | [11 empty] | NA |  |  | Mobile | Direct OEM Support |  | Latin America (LA) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [100 empty] | TA
China | GoerTek Inc. | 4-Silver |  |  | Muses |  | Wireless Device | VR/AR | a0D3A00000OCzxC | Nazgul | APQ8098 | Qingdao |  |  | PM8005;PM8998;PMI8998 | None |  | None | None | None | WCN3990 | WCN3990 BT | 4GB |  |  |  |  | Android N |  | MSM8998.LA.2.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-04-12 | 2018-06-26 | 2018-08-05 | [8 empty] | 2018-12-28 | 2019-01-31 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference |  |  | * AR project for Realmax * Start WS build on 11/11. * They change to APQ8098 * MP plan in Jan 2019. * The prototype performance is not good. Sync with GoerTek. | Huize Wang | 2018-12-23 |  |  |  | Transparent OEM Support | c_vingut@qct.qualcomm.com ; 2017-02-27 19:49:07Z | [80 empty] | huizew@qct.qualcomm.com ; 2018-12-10 08:37:38Z | [11 empty] | WCD9335 |  |  | IoT VR/AR | Direct OEM Support |  | China | NA | No NFC | None |  | No |  | No |  |  |  | LPDDR4 | [28 empty] | VR/AR Project: No need CPI audit | [100 empty] | TA
China | Huaqin | 2-Platinum |  |  | QL1686(NA)-Lenovo | Moto E OSLO M | Wireless Device | SmartPhone | a0D3A00000OKydJ | Shanti | SDM632 | Xi'an |  |  | PM8953;PMI632 | WTR3925 |  | QET4101 | Third Party | QAT3550 (x2) | WCN3615 | WCN3615 | 2GB | 3000 | 5.69” HD+ Notch 2.5D | HD (1280x720) | 12M | Android O |  | SDM632.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-06-18 | 2018-07-17 | 2018-10-14 | 2018-11-05 |  | 2018-11-05 | [5 empty] | 2019-02-01 | 2019-02-01 |  | Yizhen Yang |  | 1 | 1 |  |  |  | *JDM with Lenovo. Target NA market. CA, use QCOM antenna tuner(QAT3550). *Huaqin are preparing PVT. *Huaqin highlighted Audio tuning issue 03786404/03786955. | Yizhen Yang | 2018-12-07 | [29 empty] | yizheny@qct.qualcomm.com ; 2018-05-01 20:14:22Z | [14 empty] | jiugangg@qct.qualcomm.com ; 2016-03-14 22:45:51Z |  |  |  |  | jiugangg@qct.qualcomm.com ; 2016-03-14 22:45:51Z |  |  |  |  | yigenz@qct.qualcomm.com ; 2016-03-04 01:53:26Z | [30 empty] | yizheny@qct.qualcomm.com ; 2018-05-17 03:05:40Z | [11 empty] | PM8953 |  |  | Mobile |  |  | North America (NA) | Integrated | Other | WCN |  | TDD/FDD | B3 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note: [07/11/2018] tuning request change to "Customer". Remove DRI - Zhiqiang Jin (5/26/2018) TA changed to 2/1/2019 [5/13/2018] Name changed from QL1579-Lenovo; chipset change from MSM8917 (12/28/2017)8917 project, low risk] [CCB Score: 20] [CCB Project Info: Project: QL1686(NA)-Lenovo, ID: a0D3A00000OKydJ] [DRI/POC: Zhiqiang Jin] | Zhiqiang Jin | 20 |  | [07/11/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | [101 empty] | TA
China | BBK | 1-Diamond |  |  | PD1832F_EX | next V | Wireless Device | SmartPhone | a0D3A00000OS5jg | Talos | SM6150 | Shenzhen |  |  | None | Other |  | Third Party | None | Third Party | WCN3980 | WCN3980 BT | 6GB | 3400 | 6.28’ |  | 12M+ 5M | Android P | TBD | SM6150.LA.1.0.c1 | SB1 | Vivo 1st SM6150 project for CNY window,with big volume forecast. It would be the leading SM6150 project. | Parent CP for Original design (OEM) |  | Design/Development | SEA - Open Market | 2018-11-17 | 2018-12-30 | 2019-01-26 | [8 empty] | 2019-01-26 | 2019-02-01 |  | Hongtao Dong | Karthik Koneru | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | *Leading SM6150,-AB SKU,for overseas, 6+64/128GB eMCP; *~3K DVT1 ready with V1.1 CS chipsets, start Stability testing on ~500 devices; *Stability testing on ~400 DVT1 HW + post-CS1 SW, MPSS.AT.4.3.c1 created on 12/14 SW; *4 vivo guys and Shan arrived QIPL on 12/17 and starts Camera joint-lab; *Vivo SM6150 JFT with QC planned in Delhi (2018/12/24~2019/1/12); *QIPL Stability experts to on-site support vivo asap,and other key areas with visa ready | Hongtao Dong | 2018-12-23 | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2016-12-04 20:23:01Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2017-03-20 |  |  |  | Planning |  |  |  |  | Planning | [19 empty] | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | hongtaod@qct.qualcomm.com ; 2018-12-21 10:35:49Z | [11 empty] | WCD9370 |  |  | Mobile |  | QLN 4640 PRx | South East Asia (SEA) | Other | Other | WCN |  | TDD | B1 (FDD); B3 (FDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column25: EVT; 2018-12-01 Column68: DVT; 2019-01-01 Column95: PVT |  | TA
China | Beijing Weipass Panorama Information Technology Co., Ltd. | 4-Silver |  |  | GPOS750 | GPOS750 | IOT | IOT Smart POS | a0D3A00000ODr1M | Bagheera | MSM8916 |  | MSM8916-1 |  | PM8916 | WTR4905 |  | Third Party | Third Party | None | WCN3660 | WCN3660 | 8GB |  | 5 |  | NA | Android L |  | MSM8939.LA.2.0.2.7 | SB4 |  | Existing design to a different carrier | WMini-CMCC | Design/Development | LA - Open Market | [11 empty] | 2018-07-30 | 2019-02-08 |  | Francisco Mitkus |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review; Schedule review |  |  | efresh product for existing launched product for Gertec company in Brazil. Customer reported delays on ABECS and EMV-CO L1 certifications. TA postponed for September. New delay due contactless certifications. change in priority as well, so customer posponed to February 2019. | Francisco Mitkus | 2018-09-27 | [85 empty] | fmitkus@qct.qualcomm.com ; 2018-09-27 13:46:34Z | [11 empty] | PM8916 |  |  | IoT Smart-Cities | Direct OEM Support |  | Latin America (LA) |  | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B38 (TDD) | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | [108 empty] | TA
China | ZTE | 1-Diamond |  |  | TP1803 |  | Wireless Device | SmartPhone | a0D3A00000OS7w1 | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | QPM5650;QPM5651 | QAT5516 | WCN3998 | WCN3998 | 6GB | 4000 | 2340x1080 |  | 12M | Android P |  | SM8150.LA.1.5 | SB4 |  | Unknown |  | Evaluation | China - Open Market | 2018-11-07 | 2019-02-14 | 2019-02-14 | 2019-01-11 | [7 empty] | 2019-02-08 | 2019-02-08 |  | Xiangkui Liu |  | 1 | 1 |  |  |  | * Nubia 1st SM8150+X50 evaluating project. * The second version schematic review on going. Plan to tape out the 2nd board recently. * Finished the EVT board bring up already. Now still do the external function on debugging. | Xiangkui Liu | 2018-12-23 | [85 empty] | xiangkui@qct.qualcomm.com ; 2018-11-06 03:10:00Z | [11 empty] | WCD9341 |  |  | Mobile | Direct OEM Support | QM77033 QM77011 QM13126(TBD) | China |  | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Evaluation project: No need CPI audit |  | 2018-11-01 Column15: EVT | [8 empty] | TA | [5 empty] | PVT
China | Shenzhen Unicair Communication Technology Co., Ltd. | 4-Silver |  |  | Unicair_8909_K2 |  | Wireless Device | SmartPhone | a0D3A00000OM4dg | Cheel | MSM8909 | Shenzhen |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | Third Party;None | WCN3610 | WCN3610 (BT) | 1GB |  | 5" | QVGA (320x240) |  | Android O |  | MSM8909.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-03-05 | 2018-05-07 | 2018-09-10 | [8 empty] | 2019-02-11 | 2019-02-11 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * NA-open project. * Pl: Xue Baofeng: 13305350120. * No update this week. | Jiuyao Shu | 2018-12-23 | [23 empty] | [QPA-1218] have already finished the matchings, over temp PA char, customer also finished the verification. | wuz@qct.qualcomm.com ; 2015-12-18 06:11:19Z | [60 empty] | jshu@qct.qualcomm.com ; 2018-01-15 10:56:18Z | [11 empty] | Other |  |  | Mobile |  |  | North America (NA) | Other | Other | None |  | FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B26 (FDD); B30 (FDD) | No | C850 BC0 | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty RAM Type/technology : Empty | [111 empty] | TA
China | Yulong | 2-Platinum |  |  | 3705A | lithiem | Wireless Device | SmartPhone | a0D3A00000OeTlX | Jacala | SDM450 | Nanjing |  |  | PMI632;PM8953 | WTR3925 |  | QFE2101 | QPA4360 | None | WCN3660B | WCN3660B | 3GB | 4000 | 1080P |  | 16M+5M | Android P | SDM450.LA.3.2.1-00010-STD.PROD-1 | SDM450.LA.3.2.1 | SB3 | It's Yulong's 1st SDM450 Android P project for TMO. Forecast 1Mu-3Mu. | Parent CP for Original design (OEM) |  | Design/Development | NA - T-Mobile (USA) | 2018-07-22 | 2018-09-04 | 2018-10-28 |  |  | 2018-10-01 |  | 2018-10-29 |  |  |  | 2019-01-17 | 2019-02-13 |  | Min Fang |  | 1 | 1 |  |  |  | * It's Yulong's 1st SDM450 Android P project for TMO, B66/71 needed. * B71+B2 CA configuration has been solved from SW by OEM himself. * Take O2 slave charger and if function issue, will take only PMI632. * Camera flash LED issue linked with OEM slave charger. * PDAF tuning in SH lab and progress well. HAL3 Aux camera open issue to check with priority. * Only 1 WFD certificated issue is open. * RC1 1/9, RC2 2/6 as NFA resource limitation. | Min Fang | 2018-12-21 | [85 empty] | mfang@qct.qualcomm.com ; 2018-11-21 06:14:44Z | [11 empty] | PM8952 |  |  | Mobile | Direct OEM Support | Ant switch: SK1119; | North America (NA) | Other | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD) | No |  |  | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | Column5: PVT | [13 empty] | TA
China | Yulong | 2-Platinum |  |  | 3312A | Ranger | Wireless Device | SmartPhone | a0D3A00000OeNsw | Cheel | MSM8909 | Nanjing |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3610 | WCN3610 (BT) | 512MB | 1400 | 2.8" |  |  | Android O | MSM8909.LA.3.1.1-r00031.1 | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Sprint | 2018-06-10 | 2018-07-10 | 2018-08-15 | 2018-10-15 |  | 2018-10-22 |  | 2018-11-15 |  | 2018-12-15 |  | 2019-01-05 | 2019-02-14 |  | Min Fang |  | 1 | 1 |  |  |  | * Coolpad NJ MSM8909 FP Project for NA Sprint, Android GO. lower price vs 3310 but 2 display, take VoLTE build for MR. * HW already freezed. * GCF/TCP test ongoing. * Sprint 12/3 start precert with 10/19 build, though VoLTE works but E911 many cases failed. * LE and start test. * Gate 1/2/3: 12/17, 1/14, 1/28. | Min Fang | 2018-12-20 | [85 empty] | mfang@qct.qualcomm.com ; 2018-08-26 01:02:25Z | [11 empty] | PM8909 |  |  | Mobile | Direct OEM Support | PA: QM56022; Tuner: AW9304;switch: VC1618 |  | Other | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B13 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | [114 empty] | TA
China | Huaqin | 2-Platinum |  |  | QP1665 | Sunmi V2 Pro US | Wireless Device | IOT Smart POS | a0D3A00000OSPdR | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | None | Third Party | None | WCN3660B | WCN3660B | 1GB | 4000 |  |  |  | Android N | Snapdragon_High_Med_2016.SPF.2.0 | MSM8917.LA.3.0 | SB4 | * ODM for ShangMi. Key POS project. * Volume forecast is about 500k | ODM or partner CP associated with an indirect account |  | Design/Development | NA - Open Market | 2018-01-02 | 2018-02-28 | 2018-04-27 | [8 empty] | 2019-04-01 | 2019-02-15 |  | Hongye Liu |  | 1 | 1 |  |  |  | * It is for US market. need FCC cert while no carrier TA requirement. * customer is working on FCC sample preparation | Hongye Liu | 2018-12-10 | [85 empty] | hongyel@qct.qualcomm.com ; 2018-12-11 02:35:08Z | [11 empty] | NA |  |  | IoT Smart-Cities | Direct OEM Support |  | North America (NA) | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [115 empty] | TA
China | OPPO | 1-Diamond |  |  | RA010 |  | Wireless Device | SmartPhone | a0D3A00000OSWMr | Warlock | SDM710 | Shenzhen |  |  | PM670L;PM670 | SDR660 |  | QET4101 | Third Party | Third Party | WCN3980 | WCN3980 BT | 4GB | 3000 | 6" |  | 13+2 | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SDM710.LA.2.0 | SB3 | * this is Realme's 1st self-develop project | Parent CP for Original design (OEM) |  | Design/Development | SEA - Open Market | 2018-12-01 | 2019-01-01 | 2019-02-01 | [8 empty] | 2019-02-15 | 2019-02-15 |  | Magic Wang | Nikhil Shevade | 1 | 1 |  |  |  | * Realme SDM710 project. * Android P CPL LA.2.0.c2 is postponed to 12/28 from original plan 12/21 due to regression on PDT. * No blocking issues this week. | Magic Wang | 2018-12-23 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [45 empty] | Staffed/In progress | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-11-29 08:42:46Z | [11 empty] | NA |  |  | Mobile |  | QLN1030 D/P, QLN1020 P | South East Asia (SEA) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column39: EVT; 2019-01-01 Column70: DVT |  | PVT | [13 empty] | TA
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | T11 | T11 | Wireless Device | Tablet | a0D3A00000OeTop | Eldarion | MSM8976 | Shanghai | MSM8976-1-AA |  | PM8004;PMI8952 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660B | WCN3680B | 3GB | 0 | 8" |  | 13M | Android M | MSM8976.LA.1.1.1 | MSM8976.LA.1.1.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2017-04-20 | 2017-06-15 | 2017-07-31 | [8 empty] | 2019-02-18 | 2019-02-18 |  | Tianhao Fei |  | 1 | 1 |  |  |  | renEben T10 ODM tablet project | Tianhao Fei | 2018-07-04 | [85 empty] | tfei@qct.qualcomm.com ; 2018-07-08 02:34:21Z | [11 empty] | WCD9335 |  |  | Compute |  |  | China | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B19 (FDD); B20 (FDD); B21 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B30 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD); B41-XGP (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Sensor Vendor | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [118 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV-APQ8096-Smart Piano |  | Wireless Device | IOT Media Box | a0D3A00000OSROP | Istari | APQ8096 | Beijing |  |  | PM8996;PMI8994 | Other |  | None | None | None | QCA6174A-1 | QCA6174A-1 | 4GB |  | Null |  | 8M | Android O |  | MSM8996.LA.2.0.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-04-09 | 2018-10-22 | 2018-12-10 | [8 empty] | 2019-02-18 | 2019-02-18 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | * Thundercomm APQ8096 Smart Piano project for Find Piano. * It is based on D820 SOM project. * PM Du Guoqiang 13810860379. * DVT is ready and testing. * No blocking issue is reported this week. | Jiuyao Shu | 2018-11-18 |  |  |  |  | junjiel@qct.qualcomm.com ; 2016-04-22 02:04:21Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-12-09 12:43:30Z | [11 empty] | NA |  |  | IoT Media/TV | Transparent OEM Support |  | China | NA | No NFC | None |  |  |  | No |  |  | Sensor Vendor | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column48: PVT | [18 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F6 | Xiaomi Redmi Note A | Wireless Device | SmartPhone | a0D3A00000OdFQM | Shanti | SDM632 | Shanghai |  |  | PM632;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3615 | WCN3615 | 3GB |  | 5.5" |  | 13MP | Android P |  | SDM632.LA.1.0.1 | SB3 | Longcheer's first SDM632 design ODM to Xiaomi as new series of Redmi Note. | Parent CP for Original design (OEM) | M5100 | Design/Development | China - Open Market | 2018-08-15 | 2018-10-31 | 2018-12-09 | [8 empty] | 2019-02-18 | 2019-02-18 |  | Li Wang | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * SDM632 Smartphone project ODM to Xiaomi Target TA Nov/18 ->Feb/19 * Display is 6.01" HD GFF(Notch) 19:9, 32M Quad FF. * SW baseline freeze on SPF1.0.1.2018.00012.0 build, code freeze in another 2 months. * P2 ongoing and reported FT Test low pass rate on production line reported. | Li Wang | 2018-12-17 | [28 empty] | 4 | [56 empty] | liw@qct.qualcomm.com ; 2018-07-16 14:42:33Z | [11 empty] | NA |  |  | Mobile |  |  | China | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | [CCB Note:(9/13) ODM project/Longcheer L6250(India)] |  |  |  | (9/13) ODM project/Longcheer L6250(India) | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column8: DVT; 2018-12-01 Column47: PVT | [18 empty] | TA
China | Fuzhou Wisbo Information Technology Co., Ltd. | 4-Silver |  |  | Wisbo_8953-WR06 |  | Wireless Device | IOT Smart POS | a0D3A00000ORjoS | Jacala | MSM8953 | XiaMen |  |  | PM8953 | WTR3925 |  | QFE2101 | Third Party | None | No WLAN | No BT | 2GB |  | 5" |  | 500W | Android O |  | MSM8953.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-04 | 2018-10-19 | 2018-11-19 | [8 empty] | 2019-02-20 | 2019-02-20 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Wisbo POS project in Xiamen * Just started GMS certification test. * No update for this project this week. | Jiuyao Shu | 2018-12-11 |  |  |  |  | sfranco@qct.qualcomm.com ; 2016-11-02 18:35:54Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-12-12 03:34:02Z | [11 empty] | PM8953 |  |  | IoT Smart-Cities | Direct OEM Support |  | China | Other | Other | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | [30 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column27: PVT | [20 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV_QCS603_Nile |  | Wireless Device | IOT Enterprise IP Security Camera | a0D3A00000ORlzz | RedDragon | QCS603 | Beijing |  |  | PM8005 | SDR660G |  | Third Party | None | None | WCN3980 | WCN3980 BT | TBD/Unknown |  |  |  |  | Android O |  | QCS605.LA.1.1 | SB3 | Leading project for QCS603. | Parent CP for Original design (OEM) |  | Design/Development | Japan - NTT DoCoMo | 2018-08-01 | 2018-10-12 | 2018-12-14 | [8 empty] | 2019-02-20 | 2019-02-20 |  | Jiuyao Shu | Andrew Poh | 1 | 1 |  |  |  | *TC project for JVC. * PL: Laijinhe 15600036081 * EVT bring up is done. * DVT will be ready in middle of Nov. * PVT will be in Jan, 2019. * sHDR tuning training done for TC and CE. | Jiuyao Shu | 2018-12-11 | [85 empty] | jshu@qct.qualcomm.com ; 2018-11-11 14:04:13Z | [11 empty] | WCD9340 |  |  | IoT Connected Camera | Transparent OEM Support |  | Japan | Other | Undecided | WCN |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column52: PVT | [20 empty] | TA
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_APQ8053_Kirk_Open_Android_O |  | Wireless Device | IOT Smart Assistant | a0D3A00000Odb4N | Jacala | APQ8053 | Beijing |  |  | PMI8952 | Other |  | None | None | None | WCN3680B | WCN3680B | 2GB |  | 3gb |  | Truly/16M | Android O | Snapdragon_High_Med_2016.SPF.1.0-16000-STD.PROD-1 | MSM8953.LA.3.0.1 | SB4 |  | MR - Updated OS | SIM_APQ8053_Kirk_Open | Design/Development | ROW - Open Market | 2016-08-30 | 2016-10-10 | 2017-03-20 | [8 empty] | 2019-02-20 | 2019-02-20 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | * SIM Beijing headset project for WearNext. * Android O upgrade base on SIM_APQ8053_Kirk_Open. * No more requirement from smartphone and Use the same baseline as smartphone. * PL: Wang Yu 13661304174. * TA date: 2019/2/20 | Jiuyao Shu | 2018-11-27 | [85 empty] | jshu@qct.qualcomm.com ; 2018-12-21 02:56:49Z | [11 empty] | WCD9335 |  |  | IoT Smart-Assistant |  |  | Rest of World (ROW) | WSA8810 | Other | None |  |  |  | No |  |  | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [120 empty] | TA
China | BBK | 1-Diamond |  |  | TD1804 (PD1824) 8150 4G |  | Wireless Device | SmartPhone | a0D3A00000Oeez2 | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100M | Third Party | Third Party | WCN3998 | WCN3998 | 6GB | 3500 |  |  | 12M+5M | Android P |  | SM8150.LA.1.0 | SB2 | BBK 1st SM8150+SDX50 4G project; ,big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2019-04-01 | 2019-06-01 | 2019-08-01 | [8 empty] | 2019-02-21 | 2019-02-21 |  | Hui Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * HW : DVT from 12/7 . * SW : 1st round system test is ongoing base on 11/30 Post CS4 , several reboot and monkey stability issues under tracking. * Camera: 10+ tuning critical issue and stability issues under tracking. * Field test : 1st round field test is going on Post CS4 * Power/Perf/DOU: not start yet until SW is stable enough. | Hui Zhang | 2018-12-21 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z | [20 empty] | Staffed/In progress | 2016-07-11 | [13 empty] | Staffed/In progress | 2016-07-11 |  |  |  | Planning | 2016-08-14 |  |  |  |  | 2017-10-08 | [28 empty] | Planning | 2016-02-20 |  |  |  | zhanghui@qct.qualcomm.com ; 2018-12-21 09:03:37Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B4 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR4X | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [121 empty] | TA | [38 empty] | EVT | [60 empty] | DVT | [60 empty] | PVT
China | Meizu | 2-Platinum |  |  | M1923 | Note9 | Wireless Device | SmartPhone | a0D3A00000ORjrb | Talos | SM6150 | Shanghai |  |  | PM6150;PM6150L | SDR660 |  | None | None | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 5.5 |  | 24M | Android P |  | SM6150.LA.1.0 | SB3 | Meizu and Wingtech's first SM6150 project, tough schedule | Parent CP for Original design (OEM) | K81923AA1 | Design/Development | China - Open Market | 2018-09-28 | 2018-11-20 | 2018-12-26 | [8 empty] | 2019-02-22 | 2019-02-22 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Develop ongoing o Wingtech plans to lock the SW on 12/14 release, due to the current status, suggest them to move to the 12/30 release o Monkey test result is not good o Tough schedule, plan to do FT o Factory line met some issues, which were debugged by Wingtech at first o Began to do CTS, many issues were reported o CTA test ongoing | Tian Zhou | 2018-12-23 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [35 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-09-03 06:35:39Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | [29 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column28: DVT; 2018-12-01 Column64: PVT | [22 empty] | TA
China | Quectel | 2-Platinum |  |  | SC60-module |  | Wireless Device | IOT Dash Camera | a0D3A00000OSO8a | Jacala | MSM8953 | Shanghai |  |  | PMI8952 | WTR3925 |  | QFE2101 | Third Party | None | WCN3680 | WCN3680 | 2GB |  | TBD |  | TBD | Android N |  | MSM8953.LA.2.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-04-20 | 2018-07-20 | 2018-12-20 | [8 empty] | 2019-02-22 | 2019-02-22 |  | Andy Li |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * 8953 Module Project for Smart Devices. To support specific feature requests for automotive user scenario. 1. support two camera working in the same time, and each camera can support dual-stream: 1080p /30fps H.265 storage+ 640 *480 /30fps H.265 UL. all the streams need audio and video together. 2.when powering on, Rearview camera preview in LCD in short time, 2S-5S +2 more month for MKT shipment, | Andy Li | 2018-10-10 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-12-03 03:47:15Z | [11 empty] | PM8953 |  |  | IoT Smart-Cities | Direct OEM Support |  | China | NA | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B34 (TDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | Other | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column58: PVT | [22 empty] | TA
China | Huaqin | 2-Platinum |  |  | QP1669 | Sunmi P2 Pro | Wireless Device | IOT Smart POS | a0D3A00000ODsoO | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | None | Third Party | None | WCN3660B | WCN3660B | 1GB | 4000 | 6 |  | 8M | Android N | Snapdragon_High_Med_2016.SPF.2.0 | MSM8917.LA.3.0 | SB4 | ODM for ShangMi. Key POS project. | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-01-02 | 2018-02-28 | 2018-04-27 | [8 empty] | 2019-02-22 | 2019-02-22 |  | Hongye Liu |  | 1 | 1 |  |  |  | * New POS project for ShangMi. conparing QP1168 it added a printer and display will be HD+; * Project is under DVT3 stage. * since it require more security certification, PVT will be end of Jan | Hongye Liu | 2018-12-10 | [85 empty] | hongyel@qct.qualcomm.com ; 2018-12-11 02:33:49Z | [11 empty] | NA |  |  | IoT Smart-Cities | Direct OEM Support |  | China | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | [122 empty] | TA
China | Lenovo | 1-Diamond |  |  | Messi_P_upgrade | Moto Z | Wireless Device | SmartPhone | a0D3A00000ORgBu | Nazgul | MSM8998 | Beijing |  |  | PM8998 | WTR5975 |  | Third Party | Third Party | None | WCN3990 | WCN3990 BT | 3GB | 3000 | 6'' |  | 12M | Android O | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SDM636.LA.2.1 | SB4 | SDM835 project for NA market | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless | 2016-03-07 | 2016-04-11 | 2016-07-25 | 2016-06-15 |  | 2016-06-15 | [5 empty] | 2018-12-30 | 2019-02-23 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *SDM835 project for NA market | Gavin Song | 2018-08-23 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | rbaig@qct.qualcomm.com ; 2018-12-14 06:59:32Z | [11 empty] | Other |  |  | Mobile |  |  | North America (NA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 |  | [CCB Note:[9/28/2018] Upgrading project] |  |  |  | [9/28/2018 | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [123 empty] | TA
China | Hisense | 2-Platinum |  |  | HLTE720T | HLTE720T | Wireless Device | SmartPhone | a0D3A00000OSO20 | Talos | SM6150 | Qingdao |  |  | PM6150;PM6150L | Other |  | QET4101 | Third Party | Third Party | WCN3950 | WCN3950 | 6GB |  |  |  |  | Android P | N/A 0.0.002.0 | SM6150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | 2018-12-03 | 2019-01-09 | 2019-02-18 | 2018-12-28 | [7 empty] | 2019-02-25 | 2019-02-25 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * It is HIsense first 6150 project for CT.。 From HW view 1:SCH/Layout review is finished 2: EVB board has finished, and basic HW feature is ok. 3: Hisense report Thermal is high, I have asked them to provide some current test forms to us. From SW view 1: Hisense highly concern security boot, But our CS will support it. 2: Some basic application run well in their EVB board.。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-10-11 03:08:32Z | [11 empty] | WCD9370 |  |  | Mobile | Direct OEM Support |  | China | Integrated | Other | None |  |  |  | No | [32 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column41: EVT; 2019-01-01 Column78: DVT | [18 empty] | PVT | [6 empty] | TA
China | Linkchip | 1-Diamond |  |  | L590(Uniscope)-Reseller |  | Wireless Device | SmartPhone | a0D3A00000OSfP9 | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2000 | 5 |  |  | Android O |  | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - T-Mobile (USA) | 2017-12-19 | 2018-01-15 | 2018-02-14 |  |  | 2018-03-18 | [5 empty] | 2019-02-25 | 2019-02-25 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Schematics Review; Layout Review |  |  | *MSM8909 Reseller Project to Uniscope as TMO bidding win. *Spirent Lab testing started on 11/12, FIT ongoing << No issue reported so far *TMC Ongoing - 2 failure remaining in PTCRB and 2 in RCS. *Official LE as Stock project planned on 1/9 | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-11-26 10:24:24Z | [11 empty] | PM8909 |  |  | Mobile | JV's Reference Design |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [125 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV_SM8150_Uranus |  | Wireless Device | VR/AR | a0D3A00000ORsxl | Hana | SM8150P | Beijing |  |  | PM8150 | None |  | None | None | None | WCN3998 | WCN3998 | 6GB |  |  |  |  | Android P |  | SM8150.LA.1.0 | SB4 | - | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-04 | 2018-11-20 | 2019-01-22 | [8 empty] | 2019-02-25 | 2019-02-25 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review |  |  | * It is for Oculus' next generation design. * Pl: SongYulong 18603047791 * It is in EV1 stage. * SW initial version was release at 11/15. | Jiuyao Shu | 2018-12-23 | Planning | 2018-02-05 |  |  | dongmoon@qct.qualcomm.com ; 2018-05-14 19:21:25Z | Planning |  |  |  |  | Planning |  |  |  |  | Completed | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2017-09-01 | [13 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | tkoseki@qct.qualcomm.com ; 2018-11-21 20:32:11Z | [11 empty] | WCD9341 |  |  | IoT VR/AR | Transparent OEM Support |  | China | Other | Other | None |  | No | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B30 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | VR/AR Project: No need CPI audit |  | 2018-11-01 Column28: DVT; 2019-01-01 Column91: PVT | [25 empty] | TA
China | Linkchip | 1-Diamond |  |  | K810(KKB)-Reseller |  | Wireless Device | IOT Industrial Handheld | a0D3A00000OT9fO | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2000 | 5 |  |  | Android O |  | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-04-14 | 2018-05-16 |  |  |  | 2018-03-18 | [5 empty] | 2019-02-25 | 2019-02-25 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Schematics Review; Layout Review |  |  | *MSM8909-0+4905,Reseller Project to KuKu Bao as POC to China Open Market. * 8+8，android O, NFC, 2.7' LCD, POC(PTT Over Cellular), domestic *DVT device debuggging, software features developing | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-11-28 14:04:16Z | [11 empty] | PM8909 |  |  | IoT Smart-Cities | Direct OEM Support |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [125 empty] | TA
China | MeiG Smart Technology Co., Ltd. | 3-Gold |  |  | SLB749_ATT | A930(POS) | Wireless Device | IOT Industrial Handheld | a0D3A00000OemeK | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660 | WCN3660 | 2GB |  |  |  |  | Android N |  | MSM8917.LA.3.0 | SB4 |  | Existing design to a different carrier | SLB749 | Design/Development | NA - AT&T Wireless | 2018-07-25 | 2018-09-25 | 2018-12-25 | [8 empty] | 2019-02-26 | 2019-02-26 |  | Baoming Zhang |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * 8917 POS Machine with 5.5' HD(720p) display; * MeiG's customer will use this POS to pass ATT's certification. | Baoming Zhang | 2018-07-25 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-07-26 01:52:53Z | [11 empty] | NA |  |  | IoT Smart-Cities | Direct OEM Support |  | North America (NA) | NA | Other | WCN |  | FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty |  | 2018-12-01 Column63: PVT | [26 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F2 |  | Wireless Device | SmartPhone | a0D3A00000Odivr | Warlock | SDM712 | Beijing |  |  | PM670;PM670L | Other |  | QET4101 | Third Party | None | WCN3990 | WCN3990 BT | >4GB | 3000 | 5.5 |  | 48MP +8M + 12M | Android P |  | SDM710.LA.2.0 | SB3 | high volume project with global launch. 48M camera leading project. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-10 | 2018-11-24 | 2019-01-15 | [8 empty] | 2019-02-26 | 2019-02-26 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *F2/SDM712 kickoff in Xiaomi on 8/1, plan launch with F1; *F2 P0 10/12, P1 11/10, P2 12/22, MP 2/26; *P1 based on SDM712; *Triple cam(48M+8M+13M) support required. Both W+T Bokeh and W+U Bokeh are required, development based on the legacy camera SBA build; *Xiaomi requested SDM710 LA2.0 MPSS/CNSS/TZ CPL branch on post-CS8 for both F2/E2 android P launch support, pending on the PdM side; | Guowei Qin | 2018-12-18 | [25 empty] | Planning | [24 empty] | Staffed/In progress | 2017-11-27 | [33 empty] | gqin@qct.qualcomm.com ; 2018-10-10 03:24:48Z | [11 empty] | PM660 |  |  | Mobile |  | QLN | China; Eastern Europe (EE); Western Europe (WE) | Other | Undecided | WCN |  |  |  | No |  | 1 High: Full QTI Support Required | Qualcomm |  |  | 1. Real-time Bokeh 2. MFNR 3. Slow motion(480fps/240 fps/120fps) 4. Rear 3 camera will be configured as 2+1, 2+1 means W+T (SAT), and Ultra stand alone. W+T is defalut used, will have optical zoom, just like dual camera; Ultra wide is used alone, have UI button to switch from W+T to Ultra, no zoom with wide. 5. Need support W+T bokeh and W+U bokeh. 6. 48MP is wide sensor, 8MP is tele sensor, 13MP is Ultra wide sensor. | [26 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column32: DVT; 2019-01-01 Column84: PVT | [26 empty] | TA
China | MeiG Smart Technology Co., Ltd. | 3-Gold |  |  | SLM756P_ATT |  | Wireless Device | IOT Industrial Handheld | a0D3A00000OemeF | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR4905 |  | Third Party | Third Party | None | WCN3610 | WCN3610 (BT) | 2GB |  |  |  |  | Android N |  | MSM8909.LA.3.0 | SB4 |  | Existing design to a different carrier | SLM756P | Design/Development | NA - AT&T Wireless | 2018-07-25 | 2018-09-25 | 2018-12-25 | [8 empty] | 2019-02-27 | 2019-02-27 |  | Baoming Zhang |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * 8909 Module for POS vendor with Android N; * MeiG's customer will use this module to pass ATT's certification. | Baoming Zhang | 2018-07-25 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-07-26 01:49:59Z | [11 empty] | NA |  |  | IoT Smart-Cities | Direct OEM Support |  | North America (NA) | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B34 (TDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty |  | 2018-12-01 Column63: PVT | [27 empty] | TA
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_SDM845_boe01 |  | Wireless Device | SmartPhone | a0D3A00000OSLdL | Napali | SDM845 | Beijing |  |  | PM8005;PM8998;PM845 | SDR845 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | 4GB |  | 5.65“ |  | 12M | Android O |  | SDM845.LA.1.0.1 | SB4 | SIM first SDM845 project. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-01 | 2019-01-30 | 2019-01-30 | [8 empty] | 2019-02-28 | 2019-02-28 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * It is one display Development Board project. for BOE. No RF, wifi only. * SIM Beijing 845 project. * PM: Wang Yu 13661304174. * Pending from BOE side for this project. | Jiuyao Shu | 2018-12-11 | [85 empty] | jshu@qct.qualcomm.com ; 2018-11-28 03:19:32Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | Eastern Europe (EE) | Other | Other | None |  | No | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B40 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column39: EVT; 2019-01-01 Column99: PVT | [28 empty] | TA
China | Chongqing Luobin Information Technology Co., Ltd. | 4-Silver |  |  | LB1812 |  | Automotive | Auto Infotainment | a0D3A00000OeSq7 | Feero | MSM8937 | Shenzhen |  |  | PM8937 | WTR2965 |  | QFE2101 | QPA4373 | None | WCN3615 | WCN3615 | >8GB |  | 5.0 |  | 4M | Android M | MPSS.JO.1.2.c4-00001-8937_GENNS_PACK-2 | Snapdragon_High_Med_2016.SPF.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-07-15 | 2018-10-17 | 2018-12-20 | [8 empty] | 2019-02-28 | 2019-02-28 |  | Vivian Liu |  | 1 | 0 | [26 empty] | Staffed/In progress | [64 empty] | wenjuanl@qct.qualcomm.com ; 2018-07-04 06:44:31Z | [11 empty] | PM8937 |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column58: PVT | [28 empty] | TA
China | Shenzhen Hipad Telecommunication Technology Co., Ltd. | 3-Gold |  |  | CU55C82 | N/A | Wireless Device | SmartPhone | a0D3A00000OeHZW | Jacala | MSM8953 | Beijing |  |  | PM8953;PMI8952 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 4GB | 3500 | 5.5 |  | 13M | Android O | MSM8953.LA.3.0.1 | MSM8953.LA.3.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Unicom (CU) | [11 empty] | 2018-10-12 | 2019-02-28 | CU encryption still under debug(network tune). also need L+L move to TA.3.0 | Jiaqi Fan |  | 1 | 1 |  |  |  | *Smartphone, need Unicom volte encryption, as well as L+ L feature. TA plan: Feb 2019 *CU encryption still under debug(network tune). also need L+L move to TA.3.0 | Jiaqi Fan | 2018-12-16 | [85 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-17 03:25:53Z | [11 empty] | PM8952 |  |  | Mobile |  |  | China | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [128 empty] | TA
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | Harpoon |  | Wireless Device | Robotics | a0D3A00000OdCx2 | Cheel | APQ8009 | Beijing |  |  | PM8909;Other | Other |  | None | None | None | WCN3660B | WCN3660B | TBD/Unknown |  | No Display |  | NA | Linux Other | APQ8009.LE.1.0.2 | APQ8009.LE.1.0.2 | SB4 | iRobot ODM , volume project. Trident cost down version to 1-4-1 | ODM or partner CP associated with an indirect account | iRobot-APQ8009-Trident | Design/Development | [12 empty] | 2019-02-28 | 2019-02-28 |  | Tianhao Fei |  | 1 | 1 |  |  |  | Robot swaping robot, ODM project on top of APQ8009, apq8009.LE.1.0.2. Cost down version to 1-4-1 stack. | Tianhao Fei | 2018-04-19 | [85 empty] | tfei@qct.qualcomm.com ; 2018-12-10 07:00:09Z | [11 empty] | PM8916 |  |  | IoT Robotics | Direct OEM Support |  |  | Other | No NFC | None |  | No |  | No | [32 empty] | Mandatory Filed: Operator1 : Empty Target Region : Empty Strongly Requested Filed: Device Official Name : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [128 empty] | TA
China | Lenovo | 1-Diamond |  |  | Channel EMEA | Moto G (OSLO M ) | Wireless Device | SmartPhone | a0D3A00000OTDfK | Jacala | MSM8953 | Nanjing |  |  | PM8953 | WTR3925 |  | Third Party | None | QAT3550 | WCN3615 | WCN3615 | 3GB | 3000 | 6.5'' |  | 12M | Android P | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 | Next generation Moto G on SDM632 | Parent CP for Original design (OEM) | QL1685(ROW)-Lenovo | Design/Development | MEA - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2019-02-28 | 2019-02-28 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *As Lenovo still no SDM632 contact, put this project onto MSM8953 *SDM632 project *HW ODM by huaqin | Gavin Song | 2018-12-02 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-12 |  |  |  |  | 2015-07-30 |  |  |  |  | 2015-05-15 |  |  |  |  | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  |  | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-12-03 02:38:36Z | [11 empty] | Other |  |  | Mobile |  |  | Middle East & Africa (MEA) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [128 empty] | TA
China | Quli Information Technology Co., Ltd. dba Movision Tech | 4-Silver |  |  | X68_SC |  | Wireless Device | IOT AIO VR | a0D3A00000OeWVk | Kingsman | SXR1130 | Shanghai |  |  | PM670 | None |  | None | None | None | WCN3990 | WCN3990 BT | 4GB |  |  |  |  | Android O |  | SXR1130.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-02-28 | 2019-02-28 |  | Andy Li |  | 1 | 1 |  |  |  | * SXR1130 AR design. Target for Shadow Creator | Andy Li | 2018-07-08 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-12-03 03:45:13Z | [11 empty] | Other |  |  | IoT VR/AR | Direct OEM Support |  | China |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [128 empty] | TA
China | Quli Information Technology Co., Ltd. dba Movision Tech | 4-Silver |  |  | V101_DaPeng |  | Wireless Device | IOT AIO VR | a0D3A00000OeG5i | Kingsman | SXR1130 | Shanghai |  |  | PM670 | None |  | None | None | None | WCN3990 | WCN3990 BT | 3GB |  |  |  |  | Android O |  | SXR1130.LA.1.0 | SB3 | SXR1130 leading VR project, ODM for Dapeng | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-02-28 | 2019-02-28 |  | Andy Li |  | 1 | 1 |  |  |  | * SXR1130 VR design. Target for OEM Dapoon. | Andy Li | 2018-07-02 | [85 empty] | xinzhou@qct.qualcomm.com ; 2018-12-03 06:44:11Z | [11 empty] | Other |  |  | IoT VR/AR | Direct OEM Support |  | China |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [128 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV_APQ8053_Transition |  | Wireless Device | IOT Robots | a0D3A00000OeMVm | Jacala | APQ8053 | Beijing |  |  | PM8953;PMI8952 | Other |  | None | None | None | WCN3680B | WCN3680B | 2GB |  | None |  | None | Android O |  | MSM8953.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-07-15 | 2017-08-31 | 2018-10-08 | [8 empty] | 2019-02-28 | 2019-02-28 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | *Thundercomm APQ8053 robotic project for UBTech. * PM: wang Wei 13910219876 *Need support HDR, Dual camera, PDAF. * EVT is ready. * First Demo version was released in the end of July. * TA delay to the end of Dec due to customer want to change ID. * No update this week. | Jiuyao Shu | 2018-12-23 |  |  |  |  | junjiel@qct.qualcomm.com ; 2016-04-22 02:04:21Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-11-20 06:29:51Z | [11 empty] | Other |  |  | IoT Robotics | Transparent OEM Support |  | China | NA | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [128 empty] | TA
China | Fibocom Wireless Inc. | 3-Gold |  |  | SC802-CN-00 | SC802-CN-00 | Wireless Device | IOT Smart POS | a0D3A00000OS7Zw | Cheel | MSM8909 | Shenzhen |  |  | PM8909 | WTR4605 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 4620 | 5" |  |  | Android L | MSM8909.LA.1.1 | MSM8909.LA.1.1.c11 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - AT&T Wireless | 2018-09-10 | 2018-10-20 | 2018-12-20 | [8 empty] | 2019-02-28 | 2019-02-28 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * EVT phase, Pos module . * Hardware board back begin to do bring up | Xiangkui Liu | 2018-12-09 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-09-24 13:01:19Z | [11 empty] | PM8909 |  |  | IoT Smart-Cities | Direct OEM Support |  | North America (NA) | NA | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column58: PVT | [28 empty] | TA
China | Shenzhen Grandsun Electronic Co., Ltd. | 4-Silver |  |  | GS1275 |  | Wireless Device | Media | a0D3A00000OChvu | Cheel | APQ8009 | Shenzhen |  |  | PM8916 | Other |  | None | None | None | WCN3660B | WCN3660B | 1GB |  |  |  |  | Linux Other |  | APQ8009.LE.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-02-28 | 2019-02-28 |  | Andy Li |  | 1 | 1 |  |  |  | * Smart Speaker project, target announce in end of Oct * Using QC Fluence solution inital schedual: 2018/1/15 EVT(ASR/NLR are workable) 2018/2/15 DVT 2018/4/30 PVT 2018/5/30 MP * Project is pending customer's commercial plan | Andy Li | 2018-07-02 | [85 empty] | xinzhou@qct.qualcomm.com ; 2018-12-14 04:46:50Z | [11 empty] | WCD9326 |  |  | IoT Media/TV | Direct OEM Support |  | China; Western Europe (WE) | Other | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [128 empty] | TA
China | FIH | 1-Diamond |  |  | Dynamo2_P_Upgrade | Nokia 2.1 | Wireless Device | SmartPhone | a0D3A00000OZmQo | Feero Lite | MSM8917 | Beijing |  |  | PM8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 1GB | 4000 |  |  | 8MP | Android O |  | MSM8917.LA.3.2.1 | SB4 | ODM for HMD/Nokia. forecast: 2Mu | ODM or partner CP associated with an indirect account |  | Design/Development | ROW - Open Market | 2018-01-15 | 2018-04-23 | 2018-05-14 | 2014-03-26 | [7 empty] | 2019-02-28 | 2019-02-28 |  | Alvin Tung |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * New Nokia 2 project with 8917 Android Go * Kick off meeting on 11/23 * User Android Stock UI with minor modification * start the system test and also pre-test for TPA in week10. * GCF/CE certification has started * DVT 2 phase. * Project is on track. * MP SW froze on 6/15. * Case#3543371 - WiFi fail @ 11g PER. It blocks PVT production. * Case#3542185 - GTS Widevine failure. case owner is working closely with FIH. | Alvin Tung | 2018-12-18 | [85 empty] | alvint@qct.qualcomm.com ; 2018-12-19 06:36:06Z | [11 empty] | PM8937 |  |  | Mobile | Parallel Support |  | Rest of World (ROW) | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B20 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [128 empty] | TA
China | Suzhou Snail Digital Technology Co., Ltd. | 4-Silver |  |  | G3 | G3 | Wireless Device | SmartPhone | a0D3A00000Oe8kO | Warlock | SDM670 | Shenzhen |  |  | PM670;PM670L | SDR660 |  | QET4100;QET4101 | QPA8802;QPA5460 | None | WCN3990 | WCN3990 BT | 6GB | 3600 | 6" |  | 16M | Android O |  | SDM710.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-08-25 | 2018-10-25 | 2018-12-20 | [8 empty] | 2019-02-28 | 2019-02-28 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Training; Concept review; Kickoff meeting; Requirement Review; Schedule review; SW architecture review |  |  | * Snail game project and pre-HW design is ongoing. | Bruce Wang | 2018-06-12 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-06-12 08:57:59Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support | 1020, 1030 | China |  | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | [29 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column2: DVT; 2018-12-01 Column58: PVT | [28 empty] | TA
China | Linkchip | 1-Diamond |  |  | Q2801(Teelepoch)-Reseller |  | Wireless Device | FeaturePhone | a0D3A00000OSlmu | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 2000 | 5 |  |  | Android O |  | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless | 2018-07-09 | 2018-08-10 | 2018-09-16 |  |  | 2018-03-18 | [5 empty] | 2019-03-01 | 2019-03-01 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Schematics Review; Layout Review |  |  | *MSM8909 Reseller Project to Teleepoch for Verizon network *FP with 2.8'/1.71' dual-display and 4+4 memory using 8909 Android OGO for Verizon. *Dual display dev and FP UI porting to 8909 completed, SFN ongoing | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-11-12 16:02:33Z | [11 empty] | PM8909 |  |  | Mobile | JV's Reference Design |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [129 empty] | TA
China | Huaqin | 2-Platinum |  |  | QL1606-LG | LG MH4 | Wireless Device | SmartPhone | a0D3A00000OKogL | Jacala | SDM450 | Shanghai |  |  | PMI8952;PM8953 | WTR3925 |  | QFE2101 | Third Party | None | WCN3660 | WCN3660 | 3GB | 3200 | 5.5 | FHD (1920x1080) | 13M | Android O | SDM450.LA.3.0.1.c4 | SDM450.LA.3.0.1.c4 | SB3 | * Huaqin JDM SDM450 project for LG for NA market * forecast is about 2Mu | ODM or partner CP associated with an indirect account |  | Design/Development | NA - Open Market | 2018-09-05 | 2018-12-05 | 2019-02-05 | [8 empty] | 2019-03-01 | 2019-03-01 |  | Hongye Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | *JDM project for LG and target for NA tier 1 carriers for next Q1. DVT3 debug and test is ongoing now * Current key issue is the stability issues during factory aging test. we have tried many software change but have no improvement. issue only happen with Huaqin software on Hynix memory device. next we need to enable UART5 to get more log to check | Hongye Liu | 2018-12-23 | Staffed/In progress |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [5 empty] | Planning |  |  |  | zge@qct.qualcomm.com ; 2016-04-28 23:53:42Z | Planning | 2016-06-08 |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z |  | 2017-05-02 | 2017-05-02 | [8/7] • Compare QAT3550 to fixed matching, from customer experiments, at 900MHz, the same S11, QAT3550 will introduce 2dB loss. Will onsite support to check the reported issue. | yajunc@qct.qualcomm.com ; 2017-08-05 21:40:25Z | Planning | 2016-06-20 |  | 4 | xiwang@qct.qualcomm.com ; 2016-08-21 09:04:53Z | Planning | 2016-06-13 |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | Planning | 2016-07-04 |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | Staffed/In progress | 2016-06-20 | 2016-06-20 | All cases pass, no issue reported. | shaojunh@qct.qualcomm.com ; 2016-10-13 22:54:19Z | Staffed/In progress | 2016-06-27 | 2016-06-27 | All cases pass, no issue reported. | shaojunh@qct.qualcomm.com ; 2016-10-13 22:54:19Z | Staffed/In progress | 2016-07-01 | 2016-07-01 | [04-21-2017] 1.no critical issue [04-14-2017] 1.no critical issue，ppt sanity test is passed, will go to test on next week [04-04-2017] 1.no critical issue [07-01] 1.no critical issue [07-08] project DVT stage 1.antutu score is lower than 5W, get big gap with Qcom data. Action:clarifying this with huaqin member 2.PPT test will start if basic perf is good. [07-15] 1.no critical issue.antutu score can reach 6.1w,meet qcom data [07-22] 1.no critical issue ppt entry. [07-30] 1.no critical issue ppt test result is good. [08-05] 1.no critical issue [08-12] 1.no critical issue [08-19] 1.no critical issue [08-26] 1.no critical issue ppt round2 test will begin [09-02] 1.no critical issue [09-23] 1.no critical issue ppt round2 test finished. [09-30] Case# 02641233 [HQ][C6]后摄像头弹出“媒体服务器死机，关闭摄像头”提示框，后置摄像头启动失败 action: see much log enable,need huaqin disable those log firstly [10-14] 1.no critical issue [10-21] 1.no critical issue [10-28] #02667403 [小米][C6][AL1512] Toshiba eMMC performance mmc clk behavior get diff between ss and toshiba,under checking | peshen@qct.qualcomm.com ; 2017-04-21 00:50:14Z | [5 empty] | Planning |  |  |  | zge@qct.qualcomm.com ; 2016-04-28 23:53:42Z | Planning |  |  |  | zge@qct.qualcomm.com ; 2016-04-28 23:53:42Z | Planning |  |  |  | zge@qct.qualcomm.com ; 2016-04-28 23:53:42Z | Planning |  |  |  | zge@qct.qualcomm.com ; 2016-04-28 23:53:42Z | Planning | 2016-09-30 |  |  | zge@qct.qualcomm.com ; 2016-04-28 23:53:42Z | hongyel@qct.qualcomm.com ; 2018-10-09 06:15:25Z | [11 empty] | PM8953 |  |  | Mobile |  |  | North America (NA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [30 empty] | 2018-12-01 Column43: DVT | [5 empty] | PVT | [23 empty] | TA
China | Huaqin | 2-Platinum |  |  | WD503 |  | Wireless Device | IOT Smart watch | a0D3A00000OLe8b | Cheel | MSM8909W | Shanghai |  |  | PM8916-1 | WTR2965 |  | QFE2101 | Third Party | None | WCN3620 | WCN3620 | 1GB |  | 1.3" |  |  | Android N | MSM8909W.LAW.2.0 | MSM8909W.LAW.2.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-02-06 | 2018-03-30 | 2018-05-31 | [8 empty] | 2019-02-28 | 2019-03-01 |  | Hongye Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * Huaqin MSM8909W watch project. DVT test is ongoing *car BT connection issue was fixed with BT dev and CE team great support * power consumption issues are under debug | Hongye Liu | 2018-12-21 | Completed |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Completed |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Completed |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Completed |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  | 2 | xiwang@qct.qualcomm.com ; 2016-08-21 09:04:44Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Completed |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | Planning |  |  |  | yizheny@qct.qualcomm.com ; 2015-09-18 00:43:43Z | hongyel@qct.qualcomm.com ; 2018-12-22 00:07:15Z | [11 empty] | PM8916 |  |  | IoT Wearable | Direct OEM Support |  | China | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [129 empty] | TA
China | Fibocom Wireless Inc. | 3-Gold |  |  | NL678-AM |  | Wireless Device | Embedded Module | a0D3A00000OH6UH | Tesla | MDM9640 | Shenzhen |  |  | PMD9645 | WTR3925 |  | QFE3100 | Third Party | None | No WLAN | No BT | 512MB |  |  |  |  | Linux Other |  | MDM9640.LE.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-04-09 | 2018-06-18 | 2018-09-30 |  |  | 2018-09-01 | 2018-12-01 |  |  |  |  | 2019-03-01 | 2019-03-01 |  | Xiangkui Liu |  | 0 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schedule review |  |  | * Module project for NA market. * Evaluation phase, Still ongoing the end customer project requirement and project related evaluation | Xiangkui Liu | 2018-12-02 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-06-05 03:45:23Z | [11 empty] | NA |  |  | Mobile | Direct OEM Support |  | North America (NA) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [129 empty] | TA
China | Huawei | 1-Diamond |  |  | Bangkok(SDM632)-Overseas | Huawei Honor Y7 | Wireless Device | SmartPhone | a0D3A00000OS4PJ | Shanti | SDM632 | Xi'an |  |  | PM8953;PMI632 | WTR2965 |  | QET4101 | Third Party | Third Party | WCN3615 | WCN3615 | 4GB | 4000 | 6.26 19:9 |  | 13M+2M | Android O |  | SDM632.LA.1.0 | SB4 | *Huawei’s leading SDM632 project with big volume forecast. *Forcast: ~5M | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2016-01-23 | 2016-02-10 | 2016-04-30 |  |  | 2018-07-10 | [5 empty] | 2019-02-01 | 2019-03-01 |  | Yizhen Yang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | *JDM with Huaqin. Huawei are responsible for all the SW. *For overseas market. | Yizhen Yang | 2018-12-23 | [40 empty] | Staffed/In progress | [44 empty] | yizheny@qct.qualcomm.com ; 2018-12-21 03:07:41Z | [11 empty] | PM8953 |  |  | Mobile |  |  | Rest of World (ROW) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [129 empty] | TA
China | Qualper (Shanghai) Photoelectric Co., Ltd. | 4-Silver |  |  | Q3 |  | Wireless Device | SmartPhone | a0D3A00000OSWFJ | Starlord | SDM660 | Shanghai |  |  | PM660;PM660A | SDR660 |  | QET4101 | Third Party | None | WCN3990 | WCN3990 BT | 3GB | 4000 | 5.99" |  | 16M | Android O | Snapdragon_High_Med_2017.SPF.2.1 | SDM660.LA.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | 2018-08-06 | 2018-10-31 | 2019-02-22 |  |  | 2019-01-08 | [5 empty] | 2019-03-02 | 2019-03-02 |  | Hongye Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | * new account Qualper 1st Qualcomm project with Laser projector function. * DVT debug is ongoing now | Hongye Liu | 2018-12-15 |  |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [11 empty] | 2016-06-08 | [9 empty] | 2016-06-20 |  | 4 |  |  | 2016-06-13 |  |  |  |  | 2016-07-04 |  |  |  |  | 2016-06-20 |  |  |  |  | 2016-06-27 |  |  |  |  | 2016-07-01 | [29 empty] | 2016-09-30 |  |  |  | hongyel@qct.qualcomm.com ; 2018-10-19 01:12:37Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR4 |  | This is a dual camera 16M+5M project..Bayer + Depth | [26 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | Column8: DVT | [22 empty] | PVT | [7 empty] | TA
China | BBK | 1-Diamond |  |  | PD1838A | X25i ? | Wireless Device | SmartPhone | a0D3A00000OTJsj | Talos | SM6150 | Shenzhen |  |  | None | Other |  | Third Party | None | Third Party | WCN3980 | WCN3980 BT | 6GB | 3400 | 6.28’ |  | 12M+ 5M | Android P | ​SM6150.LA.1.0-00201-STD.PROD-1 | SM6150.LA.1.0 | SB4 | Our 1st uMCP SM6150 project with larger volume than the leading PD1832F_EX. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2019-01-09 | 2019-02-15 | 2019-02-28 | [8 empty] | 2019-03-03 | 2019-03-03 |  | Hongtao Dong |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | *Vivo 2nd SM6150 model,target for China market, TA plan is early Mar; *Same ID/ME as PD1829(SDM710, X25?); *uMCP and Type-C USB would be the main difference with PD1832F_EX; *Vivo request 4 uMCP(two are 128+6, and another two are 128+8) for this model; *Design review is ongoing per Case#03800067,EVT layout tape out plan is e/Dec | Hongtao Dong | 2018-12-23 | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2016-12-04 20:23:01Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2017-03-20 |  |  |  | Planning |  |  |  |  | Planning | [19 empty] | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | hongtaod@qct.qualcomm.com ; 2018-12-21 10:33:29Z | [11 empty] | WCD9370 |  |  | Mobile |  | QLN 4640 PRx | China | Other | No NFC | WCN |  | TDD | B1 (FDD); B3 (FDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2019-01-01 Column78: EVT | [15 empty] | DVT | [12 empty] | PVT |  |  | TA
China | OPPO | 1-Diamond |  |  | ED103 |  | Wireless Device | SmartPhone | a0D3A00000OH2aG | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | Third Party | QAT3514 (x2);QAT3550 (x2) | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP+TOF | Android P |  | SM8150.LA.1.0 | SB2 | OnePlus’s SM8150 leading project, high volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-26 | 2018-11-29 | 2018-12-24 | [8 empty] | 2019-03-04 | 2019-03-04 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *RF HW GSM RXBN case 03759957, prepare SBA to move spur away. And ask customer check noise floor on Post CS5. *Camera SW camp continue in QC Shanghai lab, P0 Issues: 39 out of 47 P0 issues closed since 12/5. Around 5 P0 issues closed per day. DXO 1st round SW delivered and test start on schedule. *Camera POR FR HDR + Bokeh patch was released. And FR "support different picture size for different camera in triple camera mode, rejected by SD PDM. *Display HDR10+ need QC PDM to confirm schedule | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [9 empty] | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  | NA | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  |  | zhibingz@qct.qualcomm.com ; 2015-12-25 01:39:25Z |  |  |  |  | xinjyang@qct.qualcomm.com ; 2015-12-25 02:51:41Z |  |  |  |  | jiugangg@qct.qualcomm.com ; 2017-09-28 22:19:17Z |  |  |  |  | jiugangg@qct.qualcomm.com ; 2017-08-20 23:52:58Z |  | 2018-01-04 | 2018-01-04 | Current state WiFi TPut issue unblocked, customer uses incorrect defconfig for test. Now customer is trying to find out what kernel configuration items impact the result. | yigenz@qct.qualcomm.com ; 2018-03-02 00:45:29Z | [30 empty] | zhiyangg@qct.qualcomm.com ; 2018-11-14 02:56:35Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty |  | 2018-11-01 Column37: DVT; 2018-12-01 Column62: PVT | [32 empty] | TA
China | OPPO | 1-Diamond |  |  | ED103_India |  | Wireless Device | SmartPhone | a0D3A00000OSy7q | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | Third Party | QAT3514 (x2);QAT3550 (x2) | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP+TOF | Android P |  | SM8150.LA.1.0 | SB4 | OnePlus’s SM8150 leading project, high volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | India - Open Market | 2018-09-26 | 2018-11-29 | 2018-12-24 | [8 empty] | 2019-03-04 | 2019-03-04 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *India varinat *modem field testing | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-11-17 07:13:40Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | India | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note: (11/23/2018) leverage ED103, change owner to customer] |  |  |  | (11/23/2018) leverage ED103, change owner to customer | [22 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column37: DVT; 2018-12-01 Column62: PVT | [32 empty] | TA
China | OPPO | 1-Diamond |  |  | ED103_EU |  | Wireless Device | SmartPhone | a0D3A00000OSy6Y | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | Third Party | QAT3514 (x2);QAT3550 (x2) | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP+TOF | Android P |  | SM8150.LA.1.0 | SB4 | OnePlus’s SM8150 leading project, high volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | EE - Open Market | 2018-09-26 | 2018-11-29 | 2018-12-24 | [8 empty] | 2019-03-04 | 2019-03-04 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *EU varinat *modem field testing | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-11-17 03:03:29Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | Eastern Europe (EE) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note: (11/23/2018) leverage ED103, change owner to customer] |  |  |  | (11/23/2018) leverage ED103, change owner to customer | [22 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column37: DVT; 2018-12-01 Column62: PVT | [32 empty] | TA
China | OPPO | 1-Diamond |  |  | ED103_NA |  | Wireless Device | SmartPhone | a0D3A00000OSy6d | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | Third Party | QAT3514 (x2);QAT3550 (x2) | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP+TOF | Android P |  | SM8150.LA.1.0 | SB4 | OnePlus’s SM8150 leading project, high volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-09-26 | 2018-11-29 | 2018-12-24 | [8 empty] | 2019-03-04 | 2019-03-04 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *NA variant * *modem field testing | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-11-17 03:04:31Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note: (11/23/2018) leverage ED103, change owner to customer] |  |  |  | (11/23/2018) leverage ED103, change owner to customer | [22 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column37: DVT; 2018-12-01 Column62: PVT | [32 empty] | TA
China | TCL | 2-Platinum |  |  | Newton | Alcatel Newton | Wireless Device | SmartPhone | a0D3A00000OeTqF | Jacala | SDM450 | Shenzhen |  |  | PMI632 | WTR2965 |  | Third Party | Third Party | None | WCN3980 | WCN3680 | 3GB |  | 6.4'' FHD+ notch/1080x2246 |  | 8M FF | Android P | SDM450.LA.3.0.1 0.0.009.0 | SDM450.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-09-20 | 2018-10-30 | 2019-02-27 |  | 2018-10-17 | 2018-10-30 | [5 empty] | 2019-03-07 | 2019-03-07 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *new project with Android P designed by SZ team * * Verified HW version last week completely. | Haijun Wang | 2018-12-03 | [28 empty] | 2 | [56 empty] | haijunw@qct.qualcomm.com ; 2018-07-19 03:46:34Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B6 (FDD); B8 (FDD); B19 (FDD); B38 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | OV12A(12M) +GC2375(2M ) | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column7: DVT | [27 empty] | PVT | [7 empty] | TA
China | TCL | 2-Platinum |  |  | A5A 7 4G | Alcatel 5T 7 4G | Wireless Device | SmartPhone | a0D3A00000Odj0S | Jacala | SDM450 | Shenzhen |  |  | PMI632 | WTR2965 |  | Third Party | Third Party | None | WCN3980 | WCN3680 | 3GB |  | 6.4'' FHD+ notch/1080x2246 |  | 8M FF | Android P | SDM450.LA.3.0.1 0.0.009.0 | SDM450.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-09-20 | 2018-10-30 | 2019-02-27 |  | 2018-10-17 | 2018-10-30 | [5 empty] | 2019-03-07 | 2019-03-07 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *new project android P designed by SZ team *Doing HW design | Haijun Wang | 2018-12-03 | [28 empty] | 2 | [56 empty] | haijunw@qct.qualcomm.com ; 2018-07-19 03:46:24Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B6 (FDD); B8 (FDD); B19 (FDD); B38 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | OV12A(12M) +GC2375(2M ) | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column7: DVT | [27 empty] | PVT | [7 empty] | TA
China | Wingtech | 2-Platinum |  |  | K80129 | RY 129F | Wireless Device | SmartPhone | a0D3A00000ORXxk | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100 | Third Party | None | WCN3998 | WCN3998 | 4GB | 3000 | 5.5 |  | 13M | Android P |  | SM8150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-07-07 | 2017-09-19 | 2017-10-30 | [8 empty] | 2019-03-08 | 2019-03-08 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Bring up ongoing, now mainly focus on Camera/RF feature o Upgrading to 11/14 release, will use it for CTA o Dual-camera didn't work, help with SR03743949 o RF bring up nearly finished o Some modem issues are under debugging o Build fail with CamerX code, under checking | Tian Zhou | 2018-11-25 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [15 empty] | Staffed/In progress | [64 empty] | tzhou@qct.qualcomm.com ; 2018-12-03 06:41:01Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | WSA8815 x2 (Stereo) | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | [136 empty] | TA
China | BBK | 1-Diamond |  |  | PD1829 | X25 | Wireless Device | SmartPhone | a0D3A00000OS1NP | Warlock | SDM710 | Shenzhen |  |  | Other;PM670A | Other |  | None | Third Party | Third Party | WCN3990 | WCN3990 BT | 6GB | 3400 | 6.28’ |  | 48M+ 12M | Android P | SDM710.LA.2.0-00050-STD.PROD-2 | SDM710.LA.2.0 | SB3 | * 2019 Feb New year window key project X25, big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-01 | 2018-12-15 | 2018-01-15 | [8 empty] | 2019-03-08 | 2019-03-08 |  | Hui Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | * Vivo changed new ID design and started EVT from early Dec. | Hui Zhang | 2018-12-16 | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | Planning |  |  |  |  | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | [5 empty] | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | Planning | [19 empty] | Staffed/In progress | 2015-11-02 |  |  |  | Planning |  |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-16 06:56:12Z | [11 empty] | PM660 |  |  | Mobile |  | QLN 4640 PRx | China | Other | No NFC | None |  | TDD | B1 (FDD); B3 (FDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column9: EVT; 2018-12-01 Column53: DVT | [36 empty] | TA
China | Wingtech | 2-Platinum |  |  | R8150 | Razer | Wireless Device | SmartPhone | a0D3A00000OZkdc | Hana | SM8150 | Shanghai |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100 | Third Party | None | WCN3998 | WCN3998 | 4GB | 3000 | 6.42 OLED FHD+ on-cell |  | 13M | Android P |  | SM8150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-12-16 | 2018-12-16 | 2018-12-16 | [8 empty] | 2019-03-08 | 2019-03-08 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Evaluation | Tian Zhou | 2018-12-16 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [15 empty] | Staffed/In progress | [64 empty] | tzhou@qct.qualcomm.com ; 2018-12-17 07:21:12Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | WSA8815 x2 (Stereo) | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column54: PVT | [36 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F7-B | Xiaomi Redmi PRO | Wireless Device | SmartPhone | a0D3A00000ORU9s | Talos | SM6150 | Shanghai |  |  | PM6150;PM6150L | SDR660 |  | Third Party | Third Party | None | WCN3980 | WCN3980 BT | 4GB | 4000 | 5.95" |  | 48M/12M + 5M | Android P |  | SM6150.LA.1.0 | SB3 | Global Leading SM6150 project for Xiaomi. | Parent CP for Original design (OEM) | M6300 | Design/Development | India - Open Market | 2018-08-29 | 2018-11-24 | 2019-01-15 | [8 empty] | 2019-03-10 | 2019-03-10 |  | Li Wang | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * SM6150 smartphone for Xiaomi as F7-B leading project of the platform * P1 Pilot production yield rate low: *case#03797046 Phone failed to connect QPST randomly << USB write error during large chunk of data transmission. USB team is checking. Blocking P1 build with -AB variant. * Upgrading to 12/14 Post-CS build, planning to lock down on this build. * PPT/Camera/Stability Status, please see detailed reports | Li Wang | 2018-12-17 | [28 empty] | 4 | [11 empty] | Completed | 2018-02-27 |  |  |  | Completed | 2018-02-27 | [38 empty] | liw@qct.qualcomm.com ; 2018-08-09 09:41:06Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | India | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 1 High: Full QTI Support Required | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column32: DVT; 2019-01-01 Column84: PVT | [38 empty] | TA
China | Shenzhen Huiye Communication Technology Co., Ltd. | 2-Platinum |  |  | X81 | X81 | Wireless Device | SmartPhone | a0D3A00000OTALT | Blackbolt | SDM636 | Shanghai |  |  | PM660 | Other |  | Third Party | Third Party | Third Party | WCN3980 | WCN3980 BT | 3GB | 3000 |  |  |  | Android O | TBD | SDM635.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | Korea - SK Telecom | [11 empty] | 2019-03-18 | 2019-03-11 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * ODM for MOTO in LA * This project has changed from 450 to 636。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-11-29 08:22:10Z | [11 empty] | Other |  |  | Mobile |  |  | Korea | NA | Other | WCN |  |  |  | No |  |  | Customer | [29 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [139 empty] | TA
China | ZTE | 1-Diamond |  |  | GM620S | GM620S | Wireless Device | IOT Smart POS | a0D3A00000OegHa | Jacala | MSM8953 | Xi'an |  |  | PMI8952;PM8953 | WTR2965 |  | None | Third Party | None | WCN3680B | WCN3680B | >12GB | 3000 |  |  | 13M | Android O | MSM8953.LA.3.0.1-00490-STD.PROD-1 | MSM8953.LA.3.0.1 | SB4 | ZTE China Center's key Axon Max2 model with Dual 13M Bayer+Mono cameras for CMCC. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-03-15 | 2019-03-15 |  | Nicholas Chen | Eugenia Chen | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Plan to release SYS B01 on 12/18, they are debugging HDMI feature, no issue pending on QCOM side * Gosuncn release INT B03 on 12/7 * Gosuncn release INT B02 on 11/14 * Gosuncn release INT B01 on 10/15 * Mother board back on 9/23, developing is ongoing. Gosuncn team plan to support Double screen different show * EVT phase, TO board on 7/25. The 1st daughter board is back on 8/15, bring up finished on 8/24 * Gosuncnkicked off the 1st Smart Module on MSM8953 | Nicholas Chen | 2018-12-17 | Planning |  |  |  | baomingz@qct.qualcomm.com ; 2015-08-18 10:17:34Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [24 empty] | jic@qct.qualcomm.com ; 2018-12-04 22:57:48Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | China | NA | Other | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [143 empty] | TA
China | OPPO | 1-Diamond |  |  | BD186 |  | Wireless Device | SmartPhone | a0D3A00000ORpVi | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100 | Third Party | QAT3518 (x2) | WCN3998 | WCN3998 | >4GB |  | 6.67" |  | TBD | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SM8150.LA.1.0 | SB2 | OPPO's 1st SM8150 4G official launch, big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-14 | 2019-01-16 | 2019-03-02 | [8 empty] | 2019-03-15 | 2019-03-15 |  | Magic Wang |  | 1 | 1 |  |  |  | * EVT device is just ready, all kinds of test will start soon. * SVA3.0 evaluation is ongoing, BU is done. Need more keywords training. * Camera support plan is completed, OPPO will camp in Shanghai, they will not go to SD. * WCN3998 "emission test fail" issue, we provided the new solution to OPPO, it can help OPPO pass regulatoy test. TDC is onsite support. * currently main problem areas are modem and RF SW. | Magic Wang | 2018-12-23 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-10-19 09:42:19Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B29 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD); B41-XGP (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column52: EVT; 2019-01-01 Column85: DVT | [30 empty] | PVT | [12 empty] | TA
China | Wingtech | 2-Platinum |  |  | T89626AA1 | Nokia N3 - Deadpool | Wireless Device | SmartPhone | a0D3A00000ORswa | Hathi | SDM429 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | None | None | None | WCN3680B | WCN3680B | 2GB | 3300 | 6.26 |  | 8M | Android P |  | SDM429.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-10-19 | 2018-12-19 | 2019-01-31 | [8 empty] | 2019-03-15 | 2019-03-15 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * for open market． | Tian Zhou | 2018-12-09 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-12-19 07:35:13Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column57: DVT | PVT | [42 empty] | TA
China | ZTE | 1-Diamond |  |  | K82_Bell | K82 | Wireless Device | Tablet | a0D3A00000OSvNg | Cheel | MSM8909 | Xi'an |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 2GB | 4050 | 8'' |  | 5M | Android O | MSM8909.LA.3.1.1 | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Bell Mobility | [5 empty] | 2019-01-14 |  | 2019-02-18 |  |  |  | 2019-03-15 | 2019-03-15 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE 8909 Android O tablet project for Canada Bell based on LA 3.1.1 PL. * LCD: 8", 800 *1280. * Leverage the HW design as TMO K82 project, need to support LTE B66. * Project status: confirmed, target TA by mid of Mar 2019. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-11-22 08:24:08Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | None |  | FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD) | No |  | 2 Medium: Case by Case Support On Demand |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [143 empty] | TA
China | ZTE | 1-Diamond |  |  | T1000B | T1000B | Wireless Device | Tracking Device | a0D3A00000OSzF9 | Lykan | MDM9207 | Xi'an |  |  | PMD9607 | WTR2965 |  | QFE2101 | Third Party | Third Party | QCA9377 | Other | 256MB | 400 | NO Display |  | NA | Linux Other | MDM9607.LE.2.0-00080-STD.PROD-3 | MDM9607.LE.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Bell Mobility |  |  | 2018-01-22 | 2018-01-22 |  | 2019-02-05 | [5 empty] | 2019-03-15 | 2019-03-15 | delayed due to BIS ban | Nicholas Chen |  | 1 | 1 |  |  |  | * Waiting for requirement from the carrier by mid of Dec'18 * ZTE kicked off MDM9207 + QCA9377 based Tracker with TI BT solution for Bell, reuse the HW of T1000 | Nicholas Chen | 2018-12-17 | [85 empty] | jic@qct.qualcomm.com ; 2018-11-20 00:01:34Z | [11 empty] | Other |  |  | IoT Smart-Cities |  |  | North America (NA) | Other | No NFC | None |  | FDD | B2 (FDD); B4 (FDD); B12 (FDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | [143 empty] | TA
China | OPPO | 1-Diamond |  |  | AD066_CT |  | Wireless Device | SmartPhone | a0D3A00000OTN9L | Warlock | SDM710 | Shenzhen |  |  | PM670;PM670A | SDR660 |  | QET4101 | Third Party | QAT3518 | WCN3990 | WCN3990 BT | 8GB | 3000 | 6" |  | 16M + 5M | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SDM710.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | 2018-11-15 | 2018-12-15 | 2019-01-18 |  |  | 2019-01-21 | [5 empty] | 2019-03-18 | 2019-03-18 |  | Magic Wang | Nikhil Shevade | 1 | 1 |  |  |  | * AD066 CT project | Magic Wang | 2018-12-12 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [45 empty] | Staffed/In progress | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-12-14 04:37:06Z | [11 empty] | NA |  |  | Mobile |  | QDM2305 | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B10 (FDD); B18 (FDD); B19 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column23: EVT; 2018-12-01 Column53: DVT; 2019-01-01 Column87: PVT | [46 empty] | TA
China | OPPO | 1-Diamond |  |  | AD069_CMCC | AD066 CMCC | Wireless Device | SmartPhone | a0D3A00000OTN9Q | Warlock | SDM710 | Shenzhen |  |  | PM670;PM670A | SDR660 |  | QET4101 | Third Party | QAT3518 | WCN3990 | WCN3990 BT | 8GB | 3000 | 6" |  | 16M + 5M | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SDM710.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2018-11-15 | 2018-12-15 | 2019-01-18 |  |  | 2019-01-21 | [5 empty] | 2019-03-18 | 2019-03-18 |  | Magic Wang | Nikhil Shevade | 1 | 1 |  |  |  | * AD066 CMCC project | Magic Wang | 2018-12-12 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [45 empty] | Staffed/In progress | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-12-14 04:37:24Z | [11 empty] | NA |  |  | Mobile |  | QDM2305 | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B10 (FDD); B18 (FDD); B19 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column23: EVT; 2018-12-01 Column53: DVT; 2019-01-01 Column87: PVT | [46 empty] | TA
China | Wind | 2-Platinum |  |  | IFL016 |  | IOT | Media | a0D3A00000ORg9T | Jacala | SDM450 | Shanghai |  |  | PMI8952 | Other |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 3GB |  |  |  | 16M | Android O |  | SDM450.LA.3.0.1 | SB4 | ODM for BQ | ODM or partner CP associated with an indirect account |  | Evaluation | China - Open Market | 2018-09-13 | 2018-10-29 | 2019-01-09 | [8 empty] | 2019-03-18 | 2019-03-18 |  | Qiang Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * translator project for Iflytek *EVT gerber out, HW will return around Dec.23 | Qiang Liu | 2018-12-09 | [85 empty] | qiangliu@qct.qualcomm.com ; 2018-11-23 03:10:51Z | [11 empty] | Other |  |  | IoT Media/TV | Direct OEM Support |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B20 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Evaluation project: No need CPI audit |  | Column6: DVT; 2019-01-01 Column78: PVT | [46 empty] | TA
China | ZTE | 1-Diamond |  |  | NX621J |  | Wireless Device | SmartPhone | a0D3A00000OSAbw | Blackbolt | SDM636 | Shenzhen |  |  | PM660L | SDR660 |  | QET4101 | Third Party | Third Party | WCN3980 | WCN3990 BT | 4GB | 4000 | 6 |  | 24M | Android O | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SDM660.LA.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-04 | 2019-01-09 | 2019-03-20 | [8 empty] | 2019-03-20 | 2019-03-20 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Kickoff meeting; Schematics Review; Layout Review; Schedule review |  |  | * (6.3 "/FHD 1080 *2280, 4GB/6GB DDR,EMMC5.1 64GB/128GB for china market target to launch end of April,2019) * EVB phase , customer change the device SPEC , and HW team still modify the schematic currently. | Xiangkui Liu | 2018-12-23 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2017-02-17 | [33 empty] | xiangkui@qct.qualcomm.com ; 2018-10-09 08:51:31Z | [11 empty] | NA |  |  | Mobile |  |  | China | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column42: EVT; 2019-01-01 Column78: DVT | [48 empty] | PVT
China | ZTE | 1-Diamond |  |  | P450K10_MR | Blade V9 | Wireless Device | SmartPhone | a0D3A00000OSz03 | Jacala | SDM450 | Shanghai |  |  | PM8953 | WTR3925 |  | QFE2101 | Third Party | Third Party | WCN3615 | WCN3615 | 3GB |  | 5.7" |  | 16M | Android O | SDM450.LA.3.0.1.c4 | SDM450.LA.3.1.1 | SB4 | ZTE Blade Center's key SDM450 V9 model for Vodafone. | Parent CP for Original design (OEM) |  | Design/Development | WE- Vodafone (Global) | 2017-10-30 | 2017-12-15 | 2018-12-27 |  |  | 2018-12-12 | [5 empty] | 2019-03-20 | 2019-03-20 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Blade V9 MR model with 5.7", FHD+, 2160 *1080 for Vodafone; * Upgraded with TA.3.0. | Baoming Zhang | 2018-11-19 | Planning |  |  |  | baomingz@qct.qualcomm.com ; 2015-08-18 10:17:34Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [24 empty] | baomingz@qct.qualcomm.com ; 2018-11-19 13:09:09Z | [11 empty] | PM8953 |  |  | Mobile |  |  | Western Europe (WE) | Other | Other | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 |  | [Schedule] Bring-up/PLD gating: 9/10/2017 - 9/17/2017 Golden module ready: 9/10/2017 IQ Basic tuning: 10/15/2017 - 10/30/2017 IQ Fine tuning: 11/1/2017 - 1/30/2017 Actuator Basic tuning: 10/15/2017 - 10/21/2017 CAF tuning: 10/21/2017- 11/14/2017 PDAF fine tuning: 11/15/2017 - 1/30/2017 [Key Feature] hope qcom support real time bokeh in fullsize preview resolution. | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column65: PVT | [48 empty] | TA
China | Meizu | 2-Platinum |  |  | M1923 - CMCC | Note9 | Wireless Device | SmartPhone | a0D3A00000OTLdq | Talos | SM6150 | Shanghai |  |  | PM6150;PM6150L | SDR660 |  | None | None | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 5.5 |  | 24M | Android P |  | SM6150.LA.1.0 | SB4 | Meizu and Wingtech's first SM6150 project, tough schedule | Parent CP for Original design (OEM) | K81923AA1-CMCC | Design/Development | China - China Mobile (CMCC) | 2018-09-28 | 2018-11-20 | 2018-12-26 | [8 empty] | 2019-03-22 | 2019-03-22 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * For cmcc | Tian Zhou | 2018-12-11 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [35 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-12-12 03:40:57Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | [29 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column28: DVT; 2018-12-01 Column64: PVT | [50 empty] | TA
China | Yulong | 2-Platinum |  |  | 332A_CC | Milo | Wireless Device | Mobile Router | a0D3A00000OSesD | Lykan | MDM9207 | Shenzhen |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | QCA9377-3 | QCA9377-3 | 128MB |  |  |  |  | Linux Other |  | MDM9607.LE.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Sprint | 2018-10-15 | 2018-11-05 |  |  |  | 2018-09-19 | [5 empty] | 2019-03-22 | 2019-03-22 |  | Min Fang |  | 1 | 1 |  |  |  | * Coolpad SZ Jerry's team 1st MDM9207 MBB product for Sprint. realteck wifi chip. * Take the GSM remove build, LTE only. L1 1/14, Gate 5 2/18. test done 3/1. * MMI requirment under development. * P2 with SAR improvement comes back. | Min Fang | 2018-12-21 | [85 empty] | mfang@qct.qualcomm.com ; 2018-10-30 01:48:22Z | [11 empty] | Other |  |  | Mobile | Direct OEM Support | SKY77645-11,Sony/CXA4429GC |  | Other | No NFC | None |  | FDD | B2 (FDD); B4 (FDD); B12 (FDD) | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column13: DVT | [50 empty] | TA
China | OPPO | 1-Diamond |  |  | ED139 |  | Wireless Device | SmartPhone | a0D3A00000ORucw | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | QPM2622;QPM8870 | QAT3514 (x2);QAT3550 (x2) | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP+TOF | Android P |  | SM8150.LA.1.0 | SB3 | OnePlus SDM8150 standard model with high volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-10 | 2019-01-18 | 2019-02-28 | [8 empty] | 2019-03-25 | 2019-03-25 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *Thermal simulation done. * Request display MIPI layout review | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-11-26 03:18:16Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column18: EVT; 2019-01-01 Column87: DVT | [28 empty] | PVT | [24 empty] | TA
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_SDM845_Tungsten |  | Wireless Device | SmartPhone | a0D3A00000OdEvP | Napali | SDM845 | Beijing |  |  | PM8005;PM8998;PM845 | SDR845 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | 4GB |  | 5.65“ |  | 12M | Android O |  | SDM845.LA.1.0.1 | SB3 | SIM first SDM845 project. | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | 2018-06-04 | 2018-08-06 | 2019-03-25 | [8 empty] | 2019-03-25 | 2019-03-25 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ODM for Dark Matter. * SIM Beijing 845 project. * PM: Wang Yu 13661304174. * Schematic review and PND review are completed. * EVT board bring up is completed. * It is in DV2 stage. * Plan to release DV3 on 12/21, PVT plan in April,2019. * No blockiing issue is reported. | Jiuyao Shu | 2018-12-11 | [85 empty] | jshu@qct.qualcomm.com ; 2018-04-23 03:04:44Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | Eastern Europe (EE) | Other | Other | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B40 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [153 empty] | PVT
China | MeiG Smart Technology Co., Ltd. | 3-Gold |  |  | SLB781 | JLY-G6 | Wireless Device | IOT Body Camera | a0D3A00000ORzPM | Jacala | SDM450 | Shanghai |  |  | PM8953;PMI8952 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660 | WCN3660 | 2GB |  |  |  | 5M | Android N |  | SDM450.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-13 | [10 empty] | 2019-03-26 | 2019-03-26 |  | Baoming Zhang |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * SDM450 Police law enforcement equipment with 2.0" 960x240 screen; * Talked with MeiG that they must switch to P PL after they sign the license for SPF2018. | Baoming Zhang | 2018-09-13 | [85 empty] | zhigangw@qct.qualcomm.com ; 2018-09-14 09:56:18Z | [11 empty] | NA |  |  | IoT Connected Camera | Direct OEM Support |  | China | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [154 empty] | TA
China | OPPO | 1-Diamond |  |  | EA017_Android_P_Upgrade | Oneplus3_P_OTA | Wireless Device | SmartPhone | a0D3A00000OSn5m | Istari | MSM8996 | Shenzhen |  |  | PM8996;PMI8996 | WTR3925 |  | QFE3100 | Third Party | Third Party | QCA6164A-1 | QCA6164A-1 | >4GB | 3000 | 5.5" |  | 16M | Android P |  | MSM8996.LA.2.0.3 | SB4 | Oneplus 3/3T Android P OTA project , aggressive schedule | MR - Updated OS | 15811 | Design/Development | NA - Open Market |  |  |  | 2017-09-30 | [7 empty] | 2019-03-27 | 2019-03-27 |  | Zhiyang Gao | Karthik Koneru | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference |  |  | *Keep modem unchanged, *QIPL owned this project | Zhiyang Gao | 2018-11-19 | Staffed/In progress |  |  |  | zhiyangg@qct.qualcomm.com ; 2016-04-10 09:24:45Z | [11 empty] | 2015-10-10 | [8 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Staffed/In progress | 2017-09-11 | [33 empty] | kkoneru@qct.qualcomm.com ; 2018-11-06 13:07:00Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China; India; North America (NA); Western Europe (WE) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | LPDDR4 |  | [CCB Note: (11/23/2018) Upgrading project, leverage 15811, change owner to customer] |  |  |  | (11/23/2018) Upgrading project, leverage 15811, change owner to customer | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [155 empty] | TA
China | ZTE | 1-Diamond |  |  | P855Y01 |  | Wireless Device | SmartPhone | a0D3A00000ORVn6 | Carrera | SDX50M + SM8150 | Shanghai |  |  | PM8005;PM8150;PM8150A;PM8150B;PM8150L;PMK8002;PMX50 | QTM052;SDR8150;SDR8154 |  | QET5100 | QPA8842;QPA2625;QPM4630;QPM4640 | QAT3516 (x2);QAT3550 | WCN3998 | WCN3998 | 6GB |  | 6.36 |  | 20M | Android P |  | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB3 | ZTE's 1st 5G mobile project targeting for China, NTT DCM, SBM and Telstra | Parent CP for Original design (OEM) |  | Design/Development | ROW - Telstra (Australia) | 2018-10-15 |  |  |  |  | 2018-11-30 | [5 empty] | 2019-03-28 | 2019-03-28 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Locked down the demo contract with Telstra; * Sent model for Telstra’s IOT testing from Nov 27, 2018 based on 11/15 release. Already made E2E call/network usage in Telstra with E/// infra; * With TW/SD CE’s support, QTM052-8/QTM052-5 ES1 BU, TPUT and beam CHAR finished on ZTE’s 5G smartphone and CPE model; * W/ QC 5GNR AS CE’s on-site support during weekend, both smart phone and CPE can register and do UL/DL iperf test on ZTE XA infra with June spec. | Baoming Zhang | 2018-12-17 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-10-08 10:41:45Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China; Japan; Rest of World (ROW) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | [CCB Note: (10/31/2018) Checked with ZTE and the project is for 5G evaluation. Camera part will not be included, and the product will be planned on P855A01/A02/SM8150 (Axon X). changed to CUSTOMER] |  |  |  | (10/31/2018) Checked with ZTE and the project is for 5G evaluation. Camera part will not be included, and the product will be planned on P855A01/A02/SM8150 (Axon X). changed to CUSTOMER | [22 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [156 empty] | TA
China | Sonim Technologies, Inc. | 4-Silver |  |  | Sonim_8909_XP3 | XP3 | Wireless Device | IOT Industrial Handheld | a0D3A00000OZLRG | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | None | None | WCN3660B | WCN3660B | 2GB | 3000 |  |  | 5M | Android O |  | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - AT&T Wireless | 2018-03-05 | 2018-05-07 | 2018-09-10 | [8 empty] | 2019-03-28 | 2019-03-28 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | * This project is AT&T . *Zhenpeng Liu +86 18600139029 * TA date: 2019/3/28. * AT&T LE： 2019/1/7 * No blocking issue is for this project. | Jiuyao Shu | 2018-12-11 | [85 empty] | jshu@qct.qualcomm.com ; 2018-12-12 03:26:57Z | [11 empty] | Other |  |  | IoT Smart-Cities | Direct OEM Support |  | North America (NA) | Other | Other | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B30 (FDD) | 1x | C850 BC0; C850 ext BC0+BC10; C1900 BC1 | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Display Physical Size (inches) : Empty | [156 empty] | TA
China | OPPO | 1-Diamond |  |  | TD11809_4G |  | Wireless Device | SmartPhone | a0D3A00000OGuU3 | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | QPA2625;QPM4621;QPM4630;QPM4641 | Third Party | WCN3998 | WCN3998 | 6GB |  | 6" |  | 16MP+20MP | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SM8150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-07-05 | 2018-10-29 | 2019-03-15 | [8 empty] | 2019-03-28 | 2019-03-28 |  | Magic Wang |  | 1 | 1 |  |  |  | * OPPO SDM855 4G evaluation project * project info is not complete, waiting for OPPO's input | Magic Wang | 2018-03-15 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [9 empty] | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  | NA | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z |  |  |  |  | zhibingz@qct.qualcomm.com ; 2015-12-25 01:39:25Z |  |  |  |  | xinjyang@qct.qualcomm.com ; 2015-12-25 02:51:41Z |  |  |  |  | jiugangg@qct.qualcomm.com ; 2017-09-28 22:19:17Z |  |  |  |  | jiugangg@qct.qualcomm.com ; 2017-08-20 23:52:58Z |  | 2018-01-04 | 2018-01-04 | Current state WiFi TPut issue unblocked, customer uses incorrect defconfig for test. Now customer is trying to find out what kernel configuration items impact the result. | yigenz@qct.qualcomm.com ; 2018-03-02 00:45:29Z | [30 empty] | cbulisac@qct.qualcomm.com ; 2018-07-02 17:08:55Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Evaluation project: No need CPI audit |  | Column6: DVT | [43 empty] | PVT | [12 empty] | TA
China | IDEA International Development Limited | 3-Gold |  |  | H6620 | Otto-8 | Wireless Device | SmartPhone | a0D3A00000OSmTY | Starlord | SDM660 | Shenzhen |  |  | PM660;PM660A | SDR660 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | 6GB | 4000 | 6.01' |  | 12M | Android P |  | SDM660.LA.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-10-15 | 2018-11-30 | 2019-01-10 | [8 empty] | 2019-03-29 | 2019-03-29 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Schematics Review; Layout Review; Schedule review |  |  | *IDEA first SDM660 project and P0 board debugging ongoing and no critical issue this week. | Bruce Wang | 2018-12-02 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2017-11-13 23:38:11Z | [80 empty] | wbruce@qct.qualcomm.com ; 2018-11-23 06:32:02Z | [11 empty] | PM660 |  |  | Mobile | Direct OEM Support |  | China | Other | Other | None |  | TDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B17 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column38: DVT; 2019-01-01 Column79: PVT | [57 empty] | TA | [443 empty] | TA
China | Beijing Zero Zero Infinity Technology Co., Ltd. | 4-Silver |  |  | HoverCamera Falcon |  | Wireless Device | IOT Drones | a0D3A00000OF4IH | Istari | APQ8096 | Beijing |  |  | PM8996;PMI8994 | Other | No WWAN | None | None | None | QCA6174A-1 | QCA6174A-1 | 4GB |  | NA |  | NA | Linux Other |  | APQ8096.LE.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-03-29 | 2019-03-29 |  | Andy Li |  | 1 | 1 |  |  |  | * ZeroZero APQ8096 based drone product, Hover Camera Second Generation; * Not too much activity now. | Andy Li | 2018-07-01 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-12-03 03:45:58Z | [11 empty] | NA |  |  | IoT Robotics | Direct OEM Support |  | China | NA | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [157 empty] | TA
China | Quectel | 2-Platinum |  |  | SC60-Jeavox |  | Automotive | Auto Infotainment | a0D3A00000OH9ZT | Jacala | MSM8953 | Shanghai |  |  | PMI8952 | WTR3925 |  | QFE2101 | Third Party | None | WCN3680 | WCN3680 | 2GB |  | TBD |  | TBD | Android N |  | MSM8953.LA.2.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-04-20 | 2018-07-20 | 2018-12-20 | [8 empty] | 2019-03-29 | 2019-03-29 | add 3 month for MKT launch. | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * 8953 Module Project for Smart Devices. To support specific feature requests for automotive user scenario. 1. support two camera working in the same time, and each camera can support dual-stream: 1080p /30fps H.265 storage+ 640 *480 /30fps H.265 UL. all the streams need audio and video together. 2.when powering on, Rearview camera preview in LCD in short time, 2S-5S +2 more month for MKT shipment, | Vivian Liu | 2018-03-29 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-11-20 03:26:36Z | [11 empty] | PM8953 |  |  | Automotive |  |  | China | NA | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B34 (TDD); B39 (TDD) | Rev A | C850 BC0 | 3 Low: No Need For QTI Support | Customer | Other | [28 empty] | Strongly Requested Filed: Device Official Name : Empty |  | 2018-12-01 Column58: PVT | [57 empty] | TA
China | GoerTek Inc. | 4-Silver |  |  | Blue |  | Wireless Device | Wearable | a0D3A00000OS7fz | Cheel | MSM8909W | Beijing |  |  | PMW3100 | WTR2965 |  | QFE2101 | Third Party | None | WCN3620 | WCN3620 | 512MB |  | 1.3 |  |  | Android for Wearables (LAW) |  | MSM8909W.LAW.3.0.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Evaluation | China - Open Market | [11 empty] | 2019-03-29 | 2019-03-29 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * GoerTek's SDW2500 project * GoerTek Beijing team is working on this project. * in evaluation phase. * Prepare for CES demo. | Huize Wang | 2018-12-23 |  |  |  |  | c_vingut@qct.qualcomm.com ; 2017-02-27 19:47:48Z | [25 empty] | Planning | [54 empty] | huizew@qct.qualcomm.com ; 2018-12-03 04:03:57Z | [11 empty] | NA |  |  | IoT Wearable | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR2 | [28 empty] | Evaluation project: No need CPI audit | [157 empty] | TA
China | Beijing Airlango Technology Co., Ltd. | 4-Silver |  |  | Tahoe |  | Wireless Device | IOT Drones | a0D3A00000OCloA | Istari | APQ8096 | Beijing |  |  | PM8996;PMI8994 | Other |  | None | None | None | QCA6174A-1 | QCA6174A-1 | 4GB |  | NA |  | NA | Linux Other |  | APQ8096.LE.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-03-29 | 2019-03-29 |  | Andy Li |  | 1 | 1 |  |  |  | * Customer is fine tuning the product, no confirmed shipment plan yet. | Andy Li | 2018-07-01 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-12-03 03:46:31Z | [11 empty] | NA |  |  | IoT Robotics | Direct OEM Support |  | China; North America (NA) | NA | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [157 empty] | TA
China | Longcheer | 2-Platinum |  |  | B810 | Obital | Wireless Device | IOT Smart watch | a0D3A00000OeCh7 | Cheel | APQ8009W | Shanghai |  |  | PMW3100 | None |  | None | None | None | WCN3620 | WCN3620 | 1GB |  |  |  |  | Android Wear (LW) |  | MSM8909W.LW.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | [11 empty] | 2019-03-29 | 2019-03-29 |  | Andy Li |  | 1 | 1 |  |  |  | * Smart watch for TAGHeuer | Andy Li | 2018-11-15 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-06-15 01:58:15Z | [11 empty] | PM8909 |  |  | IoT Wearable | Direct OEM Support |  | Japan; North America (NA); Rest of World (ROW); Western Europe (WE) |  | Other | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [157 empty] | TA
China | NREAL Technology Co., Ltd. | 4-Silver |  |  | Xiaomi AR_SDA845 |  | IOT | IOT AR | a0D3A00000Odc1b | Napali | SDA845 | Beijing |  |  | PM845 | None |  | None | None | None | WCN3680B | WCN3680B | 6GB |  |  |  |  | Android O |  | SDM845.LA.1.3 | SB3 |  | Parent CP for Original design (OEM) |  | Design/Development |  | 2018-06-01 | 2018-10-01 | 2018-12-01 | [8 empty] | 2019-03-29 | 2019-03-29 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training |  |  | *Nreal SDK/SLAM succesfully runing on the QRD845 reference board, still some performance gap; *Nreal own design P0 board SMT in SZ on 11/23, battery charictiz requirement, ETA ~1month; *Nreal is planning for the 2019 CES shows; *NReal agree on the adoption on QCOM VR SDK/SLAM, which need QC support; | Guowei Qin | 2018-12-16 | [85 empty] | gqin@qct.qualcomm.com ; 2018-12-14 08:36:22Z | [11 empty] | WCD9335 |  |  | IoT VR/AR | Direct OEM Support |  | China |  | No NFC | WCN |  |  |  | No | [32 empty] | Mandatory Filed: Operator1 : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column39: PVT | [57 empty] | TA
China | Shanghai Tricheer Technology Co., Ltd. | 3-Gold |  |  | K218 |  | Automotive | Auto Infotainment | a0D3A00000OeRx5 | Feero Lite | MSM8917 | Xi'an |  |  | PM8937 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3615 | WCN3615 | 2GB |  | 7 |  | 8M | Android N |  | MSM8917.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-08-20 | 2018-09-25 | 2018-12-10 | [8 empty] | 2019-03-29 | 2019-03-29 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  |  | Vivian Liu | 2018-07-02 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-07-03 06:16:49Z | [11 empty] | PM8937 |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column48: PVT | [57 empty] | TA
China | GoerTek Inc. | 4-Silver |  |  | Falcon_CV2_Pico |  | Wireless Device | VR/AR | a0D3A00000OeRwM | Napali | SDM845 | Beijing |  |  | PM8005;PM845;PMI8998 | None |  | None | None | None | WCN3990 | WCN3990 BT | 4GB |  |  |  |  | Android O |  | SDM845.LA.1.3 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | [11 empty] | 2019-03-29 | 2019-03-29 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Pico's SDA845 AR glass project. * Demo in CES 2019 * Launch in July 2019. | Huize Wang | 2018-12-23 |  |  |  |  | junjiel@qct.qualcomm.com ; 2016-10-03 23:55:13Z | [80 empty] | huizew@qct.qualcomm.com ; 2018-07-03 03:42:33Z | [11 empty] | Other |  |  | IoT VR/AR | Direct OEM Support |  | China | NA | No NFC | None |  | No |  | No | [32 empty] | VR/AR Project: No need CPI audit | [157 empty] | TA | [447 empty] | TA
China | Wingtech | 2-Platinum |  |  | WA036 |  | Wireless Device | IOT 360/VR Camera | a0D3A00000OCb8r | Jacala | MSM8953 | Shanghai |  |  | PM8953;PMI8952 | WTR2965 |  | Third Party | Third Party | None | WCN3680B | WCN3680B | 2GB |  | 2 |  | 8MP | Android O |  | MSM8953.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | Japan - Open Market | [11 empty] | 2018-07-26 | 2019-03-29 |  | Andy Li |  | 1 | 1 |  |  |  | * The Target OEM changed to Pioneer. * Target to launch March'19 | Andy Li | 2018-06-28 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-07-12 02:09:09Z | [11 empty] | WCD9326 |  |  | IoT Connected Camera | Direct OEM Support |  | China; Western Europe (WE) | WSA8815 | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B7 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [157 empty] | TA
China | Anhui Huami Information Technology Co., Ltd. | 4-Silver |  |  | Xihu |  | Wireless Device | IOT Smart watch | a0D3A00000OdPSM | Cheel | MSM8909W | Shenzhen |  |  | PMW3100 | WTR2965 |  | QET4101 | None | None | WCN3620 | WCN3620 | 512MB |  |  |  |  | Android for Wearables (LAW) |  | MSM8909W.LAW.3.0 | SB3 | * Xiaomi Ecosystem company, leading wearable brand. High volume forecast for adult smart watch | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-03-29 | 2019-03-29 |  | Andy Li |  | 1 | 1 |  |  |  | * Adult sport watch using MI brand and Huami own brand; * Target to launch in Q1'19 * Huami is working on EVT board hardware design. Schematic design review done. | Andy Li | 2018-06-05 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-05-03 05:30:49Z | [11 empty] | NA |  |  | IoT Wearable | Direct OEM Support |  | China |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [157 empty] | TA
China | Xiaomi | 1-Diamond |  |  | E4_D2T_Android P upgrade |  | Wireless Device | SmartPhone | a0D3A00000OS3EC | Blackbolt | SDM636 | Beijing |  |  | PM660;PM660L | SDR660 |  | QET4101 | Third Party | None;Third Party | WCN3990 | WCN3990 BT | >4GB | 3000 | 5.5 |  | 12M | Android P |  | SDM636.LA.3.0 | SB4 |  | MR - Updated OS | E4-SDM636 | Design/Development | China - Open Market | 2017-10-25 | 2017-11-25 | 2018-01-10 |  |  | 2016-12-28 | [5 empty] | 2019-03-29 | 2019-03-29 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *This project target for Xiaomi SDM660/SDM636 Android P upgrade support; *SDM660 LA3.0 CPL required from Xiaomi, which request the TZ CPL branch out and combine with SDM660 LA2.1.c6 MPSS/CNSS, pending on the PdM side; *! Xiaomi start on the Jan,2019 security patch application. | Guowei Qin | 2018-12-16 | [25 empty] | Planning | [24 empty] | Staffed/In progress | 2018-02-26 | [33 empty] | gqin@qct.qualcomm.com ; 2018-09-19 06:48:46Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China | WSA8815 x2 (Stereo) | Other | WCN |  |  |  | No |  | 3 Low: No Need For QTI Support | Customer |  |  | [CCB Note: (10/31/2018) Upgrading project. changed to CUSTOMER] |  |  |  | (10/31/2018) Upgrading project. changed to CUSTOMER | [22 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [157 empty] | TA
China | Beijing ErenEben Information Technology Co., Ltd. | 3-Gold |  |  | T11 | T11 | Wireless Device | SmartPhone | a0D3A00000OeUxL | Eldarion | MSM8976 | Shenzhen |  |  | PM8004;PMI8952 | WTR2655 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 4GB |  | 8" |  | 21MP | Android L | MSM8976.LA.1.0.1-00080-STD.PROD-1 | MSM8976.LA.1.2.1 | SB4 | *ErenEben's smart phone . (Not 8848) | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-08-13 | 2018-10-08 | 2018-12-06 | [8 empty] | 2019-03-29 | 2019-03-29 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *ErenEben's next generation smart phone . ( Not 8848 ). | Bruce Wang | 2018-07-05 |  | 2018-07-05 |  |  | wbruce@qct.qualcomm.com ; 2018-07-05 20:28:38Z |  | 2016-01-04 | [78 empty] | wbruce@qct.qualcomm.com ; 2018-07-06 03:24:56Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China | WSA8810 | No NFC | WCN |  | FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B26 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column44: PVT | [57 empty] | TA
China | GOSUNCN TECHNOLOGY GROUP CO., LTD. | 4-Silver |  |  | GM552A | GM552A | Wireless Device | Telematics | a0D3A00000OTDAa | Lykan | MDM9628 | Xi'an |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | No WLAN | No BT | 512MB | 0 |  |  |  | Linux Other | MDM9607.LE.2.2-00075-STD.PROD-1 | MDM9607.LE.2.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-30 | 2019-01-11 | 2019-02-28 | 2019-01-11 |  | 2018-12-28 |  | 2019-01-24 |  | 2019-03-05 |  | 2019-03-29 | 2019-03-29 |  | Nicholas Chen |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Schematics Review; Layout Review; System Design Review |  |  | * Gosuncn plan to release INT B01 on 11/19 * EVT phase, the 1st board was back on 12/7, bringup is done on 12/17. * Gosuncn kicked off MDM9628 based CAT4 module | Nicholas Chen | 2018-12-16 | [85 empty] | jic@qct.qualcomm.com ; 2018-12-01 04:20:40Z | [11 empty] | NA |  |  | Automotive |  |  | China |  | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B6 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column38: EVT; 2019-01-01 Column80: DVT | [28 empty] | PVT | [28 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV_APQ8098_CPB |  | Wireless Device | VR/AR | a0D3A00000ODxc4 | Nazgul | APQ8098 | Beijing |  |  | PM8998;PMI8998 | WTR5975 |  | None | None | None | WCN3990 | WCN3980 BT | 4GB |  | 1280*960 |  | 4224*3136 | Android N | MSM8998.LA.2.0-20168-STD.PROD-1 | MSM8998.LA.2.0 | SB4 | APQ8098 VR ODM for Lenovo. The volume is high. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-05-24 | 2018-06-19 | 2018-07-16 | [8 empty] | 2019-03-29 | 2019-03-29 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ODM AR project for Rokid. TS handle PCBA and SW part for this project. *Project Manager:18682331797 fanrong@thundersoft.com * EVT bring up is completed. * Demo devices provided to customer. * It is in EV3 stage. * SW: Phase I has finished delivery. TC is working on the Beta release. | Jiuyao Shu | 2018-12-23 |  |  |  |  | huizew@qct.qualcomm.com ; 2017-01-22 19:48:17Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-11-09 06:52:02Z | [11 empty] | WCD9335 |  |  | IoT VR/AR | Transparent OEM Support |  | China | NA | No NFC | None |  | No |  | No | [32 empty] | VR/AR Project: No need CPI audit | [157 empty] | TA
China | Blackshark Technologies (Nanchang) Co., Ltd. | 4-Silver |  |  | SharkII |  | Wireless Device | SmartPhone | a0D3A00000OengL | Hana | SM8150 | Shanghai |  |  | PM8150A | SDR8150 |  | QET5100 | Third Party | None | WCN3998 | WCN3998 | 6GB | 4000 | 2340x1080 |  | 12M | Android P |  | SM8150.LA.1.0 | SB3 | Blackshark first SM8150 project, 2nd Generation Gaming phone on SM8150 4G and expect volume. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-05 | 2018-10-05 | 2018-12-19 | 2018-10-15 | [7 empty] | 2019-03-29 | 2019-03-29 |  | Min Fang |  | 1 | 1 |  |  |  | * Blackshark 1st SM8150 4G project for his 2nd generation gaming phone. * 4x4 MIMO/W+T, FP under glass. DVT2 12/20, PVT on 1/20/2019. * DVT1 phase, SW at post-CS5. DVT2 will return by 12/25. *MTBF and PPT will run after DVT2. * All camera function integrated, will run MFSR function test. * Modem FT domestic from 12/24 with CS5 and oversea after post-CS7. * PP 5K in Jan. MP after CNY. | Min Fang | 2018-12-21 | [85 empty] | mfang@qct.qualcomm.com ; 2018-08-24 07:18:13Z | [11 empty] | WCD9341 |  |  | Mobile | Direct OEM Support | QM77033 QM77011 QM13126(TBD) | China |  | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column57: PVT | [57 empty] | TA
China | Lenovo | 1-Diamond |  |  | sky blue |  | Wireless Device | VR/AR | a0D3A00000OLg4X | Napali | SDM845 | Beijing |  |  | PM8005;PM845;PM8998 | Other |  | None | None | None | WCN3990 | WCN3990 BT | TBD/Unknown |  |  |  |  | Android O |  | SDM845.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) | Avatar | Design/Development | NA - Open Market | 2018-06-11 | 2018-08-20 | 2018-10-29 | [8 empty] | 2019-03-29 | 2019-03-29 |  | Jiuyao Shu |  | 1 | 0 |  |  |  | * Lenovo SDA845 AR/VR project. * HW and driver handled by Thundercomm. * Use Lenovo own AR/VR SDK. *TPM yin QIn 18116119052. * No update this week. | Jiuyao Shu | 2018-12-01 | [85 empty] | jshu@qct.qualcomm.com ; 2018-10-14 11:12:18Z | [11 empty] | WCD9340 |  |  | IoT VR/AR | Direct OEM Support |  | North America (NA) | WSA8815 x2 (Stereo) | No NFC | None |  |  |  | No | [32 empty] | VR/AR Project: No need CPI audit |  | Column6: PVT | [57 empty] | TA
China | CloudMinds Inc. | 4-Silver |  |  | A2H_Android_P_Upgrade |  | Wireless Device | SmartPhone | a0D3A00000OTKgW | Nazgul | MSM8998 | Beijing |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | Third Party | QAT3514 | WCN3990 | WCN3990 BT | 4GB | 4500 | 5.7inch |  | 12M | Android P | MSM8998.LA.2.0.1-00162-STD.PROD-1 | MSM8998.LA.2.0.2 | SB4 |  | MR - Updated OS | A2H_ATT | Design/Development | NA - AT&T Wireless | [11 empty] | 2019-03-29 | 2019-03-29 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * A2H Android P upgrade project. * OTA launch in March 2019. * They use latest MSM8998.LA.2.0.2 | Huize Wang | 2018-12-23 | [85 empty] | huizew@qct.qualcomm.com ; 2018-12-11 02:45:12Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | North America (NA) | WSA8815 | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD); B29 (FDD); B30 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | 3D camera | [26 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [157 empty] | TA
China | ZTE | 1-Diamond |  |  | SD2000 | SD2000 | Wireless Device | Tracking Device | a0D3A00000OSYeI | Lykan | MDM9207 | Xi'an | MDM9207-1 |  | PMD9607 | WTR2965 |  | None | Third Party | None | Other | Other | 256MB | 400 | No Display |  | NA | Linux Other | MDM9607.LE.2.0-00100-STD.PROD-2 | MDM9607.LE.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - T-Mobile (USA) | 2018-11-14 | 2018-12-26 | 2018-12-26 |  |  | 2018-12-26 | [5 empty] | 2019-03-29 | 2019-03-29 |  | Nicholas Chen | Eugenia Chen | 1 | 1 |  |  |  | * New HW plan to be back by 12/24, Gosuncn plan to release INT B02 on 12/20 * Release INT B01 on 11/30 * Board back on 11/15, bring up is finished on 11/26 * Design review done, TO the 1st PCB on 10/30 * ZTE Welink MDM9x07 based Tracker for TMO | Nicholas Chen | 2018-12-16 | [85 empty] | jic@qct.qualcomm.com ; 2018-11-27 06:26:26Z | [11 empty] | Other |  |  | IoT Wearable |  |  | North America (NA) | NA | No NFC | None |  | FDD | B2 (FDD); B4 (FDD); B6 (FDD); B12 (FDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column22: EVT; 2018-12-01 Column64: PVT | [57 empty] | TA
China | Wingtech | 2-Platinum |  |  | WA035 |  | Wireless Device | IOT 360/VR Camera | a0D3A00000OeZsu | Jacala | SDM450 | Shanghai |  |  | PM8953;PMI632 | WTR2965 |  | QFE2101 | Third Party | None | WCN3680B | WCN3680B | 2GB |  | 2 |  | 8MP | Android O |  | MSM8953.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | Japan - Open Market | [11 empty] | 2018-07-26 | 2019-03-29 |  | Andy Li |  | 1 | 1 |  |  |  | * The Target OEM changed to Pioneer with Single Camera from Cista C2390 * Target to launch March'19 | Andy Li | 2018-07-11 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-07-12 02:07:30Z | [11 empty] | WCD9326 |  |  | IoT Connected Camera | Direct OEM Support |  | China; Western Europe (WE) | WSA8815 | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B7 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [157 empty] | TA
China | Lenovo | 1-Diamond |  |  | Zippo | Heart | Wireless Device | SmartPhone | a0D3A00000OSt4m | Hana | SM8150 | Beijing |  |  | PM8150 | SDR8150 |  | None | Third Party | QAT3550 | WCN3998 | WCN3998 | 3GB | 3000 | 6'' |  | 16MP + 24MP | Android P |  | SM8150.LA.1.0 | SB4 | China BU SDM855 product | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-03 | 2018-10-14 | 2018-11-15 | 2016-06-15 |  | 2018-11-15 | [5 empty] | 2019-03-30 | 2019-03-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *Lenovo 2nd 8150 product | Gavin Song | 2018-11-13 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-11-13 08:28:39Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column23: PVT | [58 empty] | TA
China | Shanghai BroadMobi Communication Technology Co., Ltd. | 4-Silver |  |  | P750 |  | Wireless Device | Embedded Module | a0D3A00000OT77v | Lykan | MDM9607 | Shanghai |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | QCA9377 | No BT | 512MB |  |  |  |  | ThinUI (no MM) |  | MDM9607.TX.1.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2016-01-20 | 2016-03-20 | 2016-04-30 |  |  | 2016-05-02 | [5 empty] | 2019-03-30 | 2019-03-30 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * 9x07 Module with TX1.0 small memory. | Li Wang | 2018-11-26 | [85 empty] | liw@qct.qualcomm.com ; 2018-11-26 09:14:24Z | [11 empty] | NA |  |  | Mobile |  |  | China | NA | No NFC | None |  | FDD | B3 (FDD); B7 (FDD); B20 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [158 empty] | TA
China | ZTE | 1-Diamond |  |  | NX0004 |  | Wireless Device | SmartPhone | a0D3A00000OSnYb | Cheel | MSM8909 | Shenzhen |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 4620 | 5" |  | 5M | Android N | MSM8909.LA.2.0.1 | MSM8909.LA.2.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless | 2018-12-01 | 2019-02-28 | 2019-03-31 | [8 empty] | 2019-03-31 | 2019-03-31 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * 8909 smart phone for NA VZW/ATT. LCD: 2.8" QVGA * Finshed the schemaitc and PCB layout, and the 1st version device test plan in 1/10 . * The 2nd version device test in 2/21, and MP plan in end of March | Xiangkui Liu | 2018-12-23 | [85 empty] | xiangkui@qct.qualcomm.com ; 2018-11-09 06:40:04Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | NA | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B25 (FDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column39: EVT | [28 empty] | DVT | [30 empty] | PVT
China | ZongMu Technology (Shanghai) Co., Ltd | 4-Silver |  |  | ZM_S820A_IVI | NA | Automotive | Auto Infotainment | a0D3A00000NLS1G | IstariAU | APQ8096AU |  |  |  | PMM8996AU | Other |  | Third Party | Third Party | Third Party | No WLAN | No BT | TBD/Unknown |  |  |  |  | Linux Other |  | APQ8096AU.HQX.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-03-31 | 2019-03-31 |  | Dan Li |  | 1 | 1 | [91 empty] | weiweih@qct.qualcomm.com ; 2018-10-26 06:56:39Z | [11 empty] | NA |  |  | Automotive |  | NA |  | Other | Undecided | Third party (non-SiLab) |  |  |  | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [159 empty] | TA
China | Lenovo | 1-Diamond |  |  | River ME | Moto G | Wireless Device | SmartPhone | a0D3A00000OTDfU | Jacala | MSM8953 | Beijing |  |  | PM8953 | WTR3925 |  | Third Party | None | QAT3550 (x2) | WCN3660B | WCN3660B | 3GB | 3000 | 6.5'' |  | 12M | Android P | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 | Next generation Moto G on SDM632 | Parent CP for Original design (OEM) |  | Design/Development | MEA - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2019-03-31 | 2019-03-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *As Lenovo still no SDM632 contact, put this project onto MSM8953 | Gavin Song | 2018-12-02 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-12 |  |  |  |  | 2015-07-30 |  |  |  |  | 2015-05-15 |  |  |  |  | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  |  | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-12-03 02:42:07Z | [11 empty] | Other |  |  | Mobile |  |  | Middle East & Africa (MEA) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [159 empty] | TA
China | Lenovo | 1-Diamond |  |  | Lake RoW | Moto G | Wireless Device | SmartPhone | a0D3A00000OTDfZ | Blackbolt | SDM636 | XiaMen |  |  | PM660 | SDR660 |  | None | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 5MP | Android N | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SDM636.LA.2.1 | SB4 | *Next generation Moto G, high volume expected | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-04-15 |  | 2018-04-15 | [5 empty] | 2019-03-31 | 2019-03-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *SW freezed *PVT done *Target freeze QC SW baseline on the 10/26 release *ADR on-final stage, pending on FR35486 to pass the NFC section *CTS/VTS pre-test going smooth. *System testing on-going. *Provided AI training to Lenovo *Lenovo no longer consider change platform. *Lenovo working on P early access SW *Bring up on-going, system brought up *EVB back at 5/24 *SDM636 ,Moto G * wait for 11/12 release for final release. | Gavin Song | 2018-12-02 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2017-08-17 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-12-03 02:42:49Z | [11 empty] | Other |  |  | Mobile |  |  | Rest of World (ROW) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [159 empty] | TA
China | Lenovo | 1-Diamond |  |  | Ocean RoW | Moto G (OSLO H ) | Wireless Device | SmartPhone | a0D3A00000OTDfP | Jacala | MSM8953 | Shanghai |  |  | PM8953 | WTR3925 |  | Third Party | None | QAT3550 | WCN3615 | WCN3615 | 3GB | 3000 | 6.5'' |  | 12M | Android P | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 | Next generation Moto G on SDM632 | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2019-03-31 | 2019-03-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *As Lenovo still no SDM632 contact, put this project onto MSM8953 | Gavin Song | 2018-12-02 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-12 |  |  |  |  | 2015-07-30 |  |  |  |  | 2015-05-15 |  |  |  |  | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  |  | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-12-03 02:43:21Z | [11 empty] | Other |  |  | Mobile |  |  | Rest of World (ROW) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [159 empty] | TA
China | Fibocom Wireless Inc. | 3-Gold |  |  | NL678-APAC |  | Wireless Device | Embedded Module | a0D3A00000OH6UM | Tesla | MDM9640 | Shenzhen |  |  | PMD9645 | WTR3925 |  | QFE3100 | Third Party | None | No WLAN | No BT | 512MB |  |  |  |  | Linux Other |  | MDM9640.LE.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-04-09 | 2018-06-18 | 2018-09-30 |  |  | 2018-09-01 | 2018-12-01 |  |  |  |  | 2019-03-31 | 2019-03-31 |  | Xiangkui Liu |  | 0 | 0 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schedule review |  |  | * Module project for APAC market. * Evaluation phase, Still ongoing the end customer project requirement and project related evaluation. | Xiangkui Liu | 2018-12-16 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-06-05 03:46:09Z | [11 empty] | NA |  |  | Mobile | Direct OEM Support |  | Rest of World (ROW) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [159 empty] | TA
China | Lenovo | 1-Diamond |  |  | Robusta S lite | Moto K | Wireless Device | SmartPhone | a0D3A00000OZmKE | Jacala | MSM8953 | Shanghai |  |  | PMI8952 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660 | WCN3660 | 3GB | 3000 | 6.5'' |  | 12M | Android O | Snapdragon_High_Med_2016.SPF.3.0.1 | SDM450.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2017-05-31 | 2017-07-10 | 2017-09-29 |  |  | 2017-11-27 | [5 empty] | 2019-03-31 | 2019-03-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | * New project the change memory to the 32EMCP16-EL3GTB29-A90 * HW by OEM vendor * BSP SW in Lenovo shanghai, other components by both shanghai and Xiamen | Gavin Song | 2018-12-18 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  |  | 2015-06-15 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-12 |  |  |  |  | 2015-07-30 |  |  |  |  | 2015-05-15 |  |  |  |  | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  |  | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-12-19 02:43:43Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Undecided | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [159 empty] | TA
China | Wind | 2-Platinum |  |  | A306_P_upgrade |  | Wireless Device | SmartPhone | a0D3A00000OSLb0 | Feero Lite | MSM8917 | Shanghai |  |  | PM8937;PMI8937 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3660B | WCN3660B | 1GB | 2800 | 5.2 |  | 13M/8M | Android P |  | MSM8917.LA.3.1.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | EE - Open Market | 2017-12-18 | 2018-01-18 | 2018-04-30 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *The project will be transferred to Asus, wind is discussing details with ASUS for handover | Qiang Liu | 2018-12-16 |  |  |  |  | tzhou@qct.qualcomm.com ; 2016-09-12 00:38:52Z | [80 empty] | qiangliu@qct.qualcomm.com ; 2018-10-15 06:19:42Z | [11 empty] | PM8937 |  |  | Mobile |  |  | Eastern Europe (EE) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B38 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [160 empty] | TA
China | Wind | 2-Platinum |  |  | E300_P_upgrade |  | Wireless Device | SmartPhone | a0D3A00000OSLb5 | Feero Lite | MSM8917 | Shanghai |  |  | PM8937;PMI8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 4000 | 5.45" HD+ (1440*720) |  | 13M+8M | Android P |  | MSM8917.LA.3.1.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-10-26 | 2017-12-02 | 2018-01-27 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *The project will be transferred to Asus, wind is discussing details with ASUS for handover *Android P upgrade project, TA: April'19 | Qiang Liu | 2018-12-16 |  |  |  |  | tzhou@qct.qualcomm.com ; 2016-09-12 00:38:52Z | [80 empty] | qiangliu@qct.qualcomm.com ; 2018-10-15 06:19:59Z | [11 empty] | Other |  |  | Mobile |  |  |  | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B26 (FDD); B28 (FDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [160 empty] | TA
China | Wind | 2-Platinum |  |  | A305_P_upgrade |  | Wireless Device | SmartPhone | a0D3A00000OSLav | Feero Lite | MSM8917 | Shanghai |  |  | PM8937;PMI8937 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3660B | WCN3660B | 1GB | 2800 | 5.2 |  | 13M/8M | Android P |  | MSM8917.LA.3.1.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | EE - Open Market | 2017-12-18 | 2018-01-18 | 2018-04-30 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Qiang Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * it's Android P - GO upgrade project * The project will be transferred to Asus, wind is discussing details with ASUS for handover | Qiang Liu | 2018-12-16 |  |  |  |  | tzhou@qct.qualcomm.com ; 2016-09-12 00:38:52Z | [80 empty] | qiangliu@qct.qualcomm.com ; 2018-10-15 06:20:12Z | [11 empty] | PM8937 |  |  | Mobile |  |  | Eastern Europe (EE) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B25 (FDD); B26 (FDD); B38 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [160 empty] | TA
China | Queclink Wireless Solutions Co., Ltd. | 4-Silver |  |  | QL200 | QL200 | Wireless Device | USB Modem | a0D3A00000ORkoR | Lykan | MDM9207 | Shanghai |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | No WLAN | No BT | 2GB |  |  |  |  | Linux Other | MDM9607.LE.2.0.1-00070-STD.PROD-1 | MDM9607.LE.2.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-10-25 | 2018-12-31 | 2019-02-19 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Weizheng Lv |  | 1 | 1 |  |  |  | s their rst 9207 project。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-08-29 08:35:50Z | [11 empty] | Other |  |  | IoT Smart-Cities |  |  | China | Other | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | Column2: EVT; 2018-12-01 Column69: DVT | [19 empty] | PVT | [40 empty] | TA
China | TCL | 2-Platinum |  |  | Benz | Alcatel 3C | Wireless Device | SmartPhone | a0D3A00000Oebjk | Hathi | SDM429 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 3500 | 5.94" |  | 13MP Bayer + 5MP Bayer | Android O | SDM429 | SDM429.LA.1.0 | SB3 | * TCL first SDM429 project and big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | LA - Telcel | 2018-08-20 | 2018-10-10 | 2018-11-20 |  | 2018-12-20 | [6 empty] | 2019-04-01 | 2019-04-01 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * LE candidate image for EU carrier is under preparing; * PPT lab test planned from next week and TCL is preparing the golden devices as well as the SW candidate image; * Stability/Monkey/power and performance test is ongoing on PVT phone and waiting TCL to update the latest test result; * Case#03795445 - there are many color noise when camera capturing after upgrading baseline, need team to check it with priority. | Bruce Wang | 2018-12-16 | [28 empty] | 2 | [56 empty] | wbruce@qct.qualcomm.com ; 2018-12-04 02:28:41Z | [11 empty] | PM8937 |  |  | Mobile | Direct OEM Support | HRTXAH005-01, CUC1294A-11,CUCT, AP7219M-71 | Latin America (LA); Middle East & Africa (MEA); South East Asia (SEA) | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B28 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 |  | [CCB Assignment:Donglian Zeng] [CCB Support Type:TS] [CCN Note: (11/1/2018) TCL-Benz is tuned by Huizhou camera tuning team. But the team does not have Qcom camera tuning experience. Need support from QC]. [CCB Support Level:Med] [CCB Score:18] [DRI/PoC:Yang Yang] -- Bring-up/PLD gating: 09/15/2018 - 09/25/2018 -- Golden module ready: 09/25/2018 -- IQ Basic tuning: 09/26/2018 -10/25/2018 -- IQ Fine tuning: 11/25/2018 - 12/25/2018 -- Actuator Basic tuning: 10/25/2018 -11/25/2018 -- CAF tuning: 10/25/2018 -11/25/2018 -- PDAF/TOF fine tuning: 10/25/2018 -11/25/2018 | Yang Yang | 18 | Med |  | TS | Donglian Zeng | [20 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column28: PVT | [60 empty] | TA
China | Xiaomi | 1-Diamond |  |  | C3H | Xiaomi | Wireless Device | SmartPhone | a0D3A00000OSfOu | Hathi | SDM439 | Shanghai |  |  | PM439;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 4000 | 5.7" |  | 13M | Android P | SDM439.LA.1.1 | SDM439.LA.1.1 | SB3 | * Xiaomi Redmi ODM project. high volume forecast | Parent CP for Original design (OEM) | C3H_Xiaomi | Design/Development | China - Open Market | 2018-12-18 | 2019-01-10 | 2019-03-20 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Hongye Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review; Schedule review |  |  | * Xiaomi SDM439 ODM by Huaqin. * 1st PCB SMT in 12/18 and bring up is ongoing. So far BB and RF basic function (boot, LCD, RF call etc) are fine. Pending further test and debug * SW change for PMI632-1 is not ready. current it is WA. Customer request formal code change ready before Jan-5 to meet their Jan-10 SMT schedule | Hongye Liu | 2018-12-23 | [28 empty] | 2 | [56 empty] | hongyel@qct.qualcomm.com ; 2018-11-28 06:08:11Z | [11 empty] | NA |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column56: EVT; 2019-01-01 Column79: DVT | [48 empty] | PVT | [11 empty] | TA
China | Huaqin | 2-Platinum |  |  | QP1669A | Sunmi P2 Mini | Wireless Device | IOT Smart POS | a0D3A00000ORu9K | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | None | Third Party | None | WCN3660B | WCN3660B | 1GB | 4000 | 6 |  | 8M | Android N | Snapdragon_High_Med_2016.SPF.2.0 | MSM8917.LA.3.0 | SB4 | ODM for ShangMi. Key POS project. | ODM or partner CP associated with an indirect account |  | Design/Development | India - Open Market | 2018-10-15 | 2018-11-30 | 2019-01-15 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Hongye Liu |  | 1 | 1 |  |  |  | * New POS project for ShangMi. sch review is ongoing; * project is on hold for biz reason. 1st PCBA have not been taped out; | Hongye Liu | 2018-11-22 | [85 empty] | hongyel@qct.qualcomm.com ; 2018-09-28 07:27:54Z | [11 empty] | NA |  |  | IoT Smart-Cities | Direct OEM Support |  | India | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column38: DVT; 2019-01-01 Column84: PVT | [60 empty] | TA
China | Quectel | 2-Platinum |  |  | EG18 |  | Wireless Device | Embedded Module | a0D3A00000OeWvA | Stingray | SDX20 | Shanghai |  |  | PMX20 | SDR845 |  | QET4101 | Third Party | Third Party | QCA6174A-1 | No BT | 512MB |  | None |  | None | ThinUI (no MM) |  | SDX20.LE.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-09-02 | 2018-11-02 | 2019-02-04 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *Quectel EG18 CAT18 LGA modules. The first SKU of EG18 is EG18-EA *SDX20+PMX20+SDR845+QET4101+QLN1035+QLN1020, support 4X4MIMO. *RF tuning ongoing. | Li Wang | 2018-11-19 | [20 empty] | Planning | [64 empty] | liw@qct.qualcomm.com ; 2018-11-28 06:16:37Z | [11 empty] | NA |  |  | Mobile |  |  | Rest of World (ROW) | NA | No NFC | None |  | FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B6 (FDD); B7 (FDD); B8 (FDD); B9 (FDD); B10 (FDD); B11 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B21 (FDD); B22 (FDD); B23 (FDD); B24 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column10: DVT |  |  |  |  | PVT | [55 empty] | TA
China | Shenzhen Hipad Telecommunication Technology Co., Ltd. | 3-Gold |  |  | Smart X |  | Wireless Device | Media | a0D3A00000OeYI6 | Feero Lite | MSM8917 | Nanjing |  |  | None | WTR2965 |  | QFE2101 | None | Third Party | WCN3680B | WCN3680B | 2GB |  | 7 |  |  | Android O |  | MSM8917.LA.3.0.1 | SB4 | Smart assistant production, similar as Amazon echo/XiaoduXiaodu | Parent CP for Original design (OEM) |  | Design/Development | [12 empty] | 2019-04-01 | 2019-04-01 |  | Jiaqi Fan |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *Smart assistant， TA Plan April 2019. *Hardware design | Jiaqi Fan | 2018-07-30 |  |  |  |  | c_vingut@qct.qualcomm.com ; 2016-11-04 13:27:20Z | [80 empty] | xinzhou@qct.qualcomm.com ; 2018-12-14 04:45:59Z | [11 empty] | Other |  |  | IoT Media/TV | Direct OEM Support |  | China | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Operator1 : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [160 empty] | TA
China | Huaqin | 2-Platinum |  |  | WD251-Mobvoi | Mobvoi(出门问问) | Wireless Device | Wearable | a0D3A00000OSSGW | Cheel | MSM8909W | Xi'an |  |  | PMW3100 | WTR2965 |  | QET4101 | None | Third Party | WCN3620 | WCN3620 | 512MB | 660 | 1.4" |  |  | Android O |  | MSM8909W.LAW.3.0.0.1 | SB4 | Huaqin Watch PCBA project. Will fan out more projects. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-13 | 2018-12-15 | 2018-03-01 | 2018-01-16 |  | 2018-03-01 | [5 empty] | 2019-04-01 | 2019-04-01 |  | Yizhen Yang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review; Schedule review; SW architecture review |  |  | *Fan-out project of PCBA project WD2500. *ODM for Mobvoi *Huaqin have upgraded to the latest baseline build for WD251 project. *Huaqin required QCOM to support SIM_VCC change to LD015 from external LDO(Case: 03763874/03760938) | Yizhen Yang | 2018-12-14 |  |  |  |  | junjiel@qct.qualcomm.com ; 2016-04-22 02:14:10Z | [80 empty] | yizheny@qct.qualcomm.com ; 2018-12-14 09:01:03Z | [11 empty] | Other |  |  | IoT Wearable | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column21: EVT; 2018-12-01 Column53: DVT | [60 empty] | TA
China | TCL | 2-Platinum |  |  | Gauss | Alcatel 3 | Wireless Device | SmartPhone | a0D3A00000ORowx | Hathi | SDM439 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 3500 | 5.94" |  | 12MP Bayer + 2MP Bayer | Android O |  | SDM439.LA.1.0 | SB4 | * TCL first SDM439 project and big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | MEA - Orange | 2018-09-10 | 2018-10-17 | 2018-11-27 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * TCL first SDM439 project. | Bruce Wang | 2018-09-02 | [28 empty] | 2 | [56 empty] | wbruce@qct.qualcomm.com ; 2018-12-04 02:27:48Z | [11 empty] | PM8937 |  |  | Mobile | Direct OEM Support | HRTXAH005-01, CUC1294A-11,CUCT, AP7219M-71 | Latin America (LA); Middle East & Africa (MEA); South East Asia (SEA) | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B28 (FDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column35: PVT | [60 empty] | TA
China | Hisense | 2-Platinum |  |  | HLTE215T | HLTE215T | Wireless Device | SmartPhone | a0D3A00000OSUnt | Hathi | SDM429 | Qingdao |  |  | PM439 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3680B | WCN3680B | 4GB | 4500 | 6.21 |  | 13M | Android O | SDM439.LA.1.0-00230-STD.PROD-1 | SDM429.LA.1.0 | SB4 | It is Hisense first 439 project. | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | 2018-10-17 | 2018-11-10 | 2018-12-06 | 2018-11-24 |  | 2018-09-28 | [5 empty] | 2018-10-23 | 2019-04-01 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * It is Hisense first 429 project.。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-10-18 06:17:21Z | [11 empty] | NA |  |  | Mobile | Direct OEM Support |  | China | Other | No NFC | None |  |  |  | No |  |  | Customer | [29 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column18: DVT; 2018-12-01 Column44: PVT | [60 empty] | TA
China | Quectel | 2-Platinum |  |  | SC66 |  | Wireless Device | IOT Smart POS | a0D3A00000ORdYj | Starlord | SDM660 | Shanghai |  |  | PM660;PM660L | SDR660 |  | QET4101 | Third Party | None | WCN3980 | WCN3980 BT | 2GB |  |  |  |  | Android O |  | SDM660.LA.2.1 | SB4 | Smart cities AI Module on SDM660 for Sunm | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-09-20 | 2018-12-20 | 2019-03-20 | [8 empty] | 2019-04-01 | 2019-04-01 |  | Andy Li |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Smart cities AI Module on SDM660 for Sunmi * Sunmi is a top ECR vendor. Their SW will be developed based on our platform. * Need to pin-to-pin module with their MSM8953 desgn. | Li Wang | 2018-10-08 | [85 empty] | liw@qct.qualcomm.com ; 2018-08-20 14:33:47Z | [11 empty] | NA |  |  | IoT Smart-Cities | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column58: DVT | [48 empty] | PVT | [11 empty] | TA
China | Huaqin | 2-Platinum |  |  | QL1607-LG | LG MH4 | Wireless Device | SmartPhone | a0D3A00000OSLcm | Jacala | SDM450 | Shanghai |  |  | PMI632;PM8953 | WTR3925 |  | QFE2101 | Third Party | None | WCN3680B | WCN3680B | 3GB | 3200 | 5.5 |  | 13M | Android P | SDM450.LA.3.2.1 | SDM450.LA.3.2.1 | SB4 | * Huaqin JDM SDM450 project for LG for NA market * forecast is about 2Mu | ODM or partner CP associated with an indirect account |  | Design/Development | NA - T-Mobile (USA) | 2018-09-05 | 2018-12-05 | 2019-02-05 | [8 empty] | 2019-04-05 | 2019-04-05 |  | Hongye Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | * The QL1607 project is based on the QL1606-LG project to modify the RF band, operator TMUS/Sprint/AT&T * RF bring up finished with RFSW DRI onsite supporrt | Hongye Liu | 2018-11-22 | Staffed/In progress |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [5 empty] | Planning |  |  |  |  | Planning | 2016-06-08 |  |  |  |  | 2017-05-02 |  |  |  | Planning | 2016-06-20 |  | 4 |  | Planning | 2016-06-13 |  |  |  | Planning | 2016-07-04 |  |  |  | Staffed/In progress | 2016-06-20 |  |  |  | Staffed/In progress | 2016-06-27 |  |  |  | Staffed/In progress | 2016-07-01 | [8 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2016-09-30 |  |  |  | hongyel@qct.qualcomm.com ; 2018-12-15 10:15:25Z | [11 empty] | PM8953 |  |  | Mobile |  |  | North America (NA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column43: DVT | [5 empty] | PVT | [58 empty] | TA
China | Xiaomi | 1-Diamond |  |  | C3F | XIAOMI C3F | Wireless Device | SmartPhone | a0D3A00000OSZpG | Shanti | SDM632 | Shanghai |  |  | PM8004 | WTR2965 |  | Third Party | Third Party | None | WCN3660 | WCN3660 | 3GB | 3000 | 5.7 |  | 12M | Android P |  | SDM632.LA.1.0 | SB3 | Target for Redmi7, big volume forecast | Parent CP for Original design (OEM) | S88568 | Design/Development | China - Open Market | 2018-11-05 | 2018-12-07 | 2019-01-13 | [8 empty] | 2019-04-06 | 2019-04-06 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Pending, a new project is under discussion with the same ID | Tian Zhou | 2018-11-18 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [35 empty] | Staffed/In progress |  |  |  |  | Staffed/In progress | [39 empty] | tzhou@qct.qualcomm.com ; 2018-10-24 07:21:33Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B1 (FDD); B3 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column13: EVT; 2018-12-01 Column45: DVT; 2019-01-01 Column82: PVT | [65 empty] | TA
China | ZTE | 1-Diamond |  |  | P855A02 | A2020 pro | Wireless Device | SmartPhone | a0D3A00000OSLeJ | Hana | SM8150 | Shanghai |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100 | Third Party | Third Party | WCN3998 | WCN3998 | 6GB |  | 6.47 |  | 48M | Android P | SM8150.LA.1.0 | SM8150.LA.1.0 | SB4 | ZTE's next generation AXON flagship model based on SM8150 4G. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-15 |  |  |  |  | 2019-01-08 | [5 empty] | 2019-04-09 | 2019-04-09 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * SM8150 4G flagship model which targets launching in Mar, 2019. | Baoming Zhang | 2018-10-09 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-11-19 13:20:35Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Customer |  |  | [CCB Note: (10/31/2018) Camera part will be planned on P855A01/SM8150 (Axon X). changed to CUSTOMER] |  |  |  | (10/31/2018) Camera part will be planned on P855A01/SM8150 (Axon X). changed to CUSTOMER | [22 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column23: EVT | [68 empty] | TA
China | ZTE | 1-Diamond |  |  | P855A01 | A2020 pro | Wireless Device | SmartPhone | a0D3A00000OSLe9 | Hana | SM8150 | Shanghai |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100 | Third Party | Third Party | WCN3998 | WCN3998 | 6GB |  | 6.47 |  | 48M | Android P | SM8150.LA.1.0 | SM8150.LA.1.0 | SB4 | ZTE's next generation AXON flagship model based on SM8150 4G. | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | 2018-11-15 |  |  |  |  | 2019-01-08 | [5 empty] | 2019-04-09 | 2019-04-09 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * SM8150 4G flagship model which targets launching in Mar, 2019. | Baoming Zhang | 2018-10-09 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-11-19 13:19:52Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | Western Europe (WE) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column23: EVT | [68 empty] | TA
China | Meizu | 2-Platinum |  |  | M1971 | Meizu | Wireless Device | SmartPhone | a0D3A00000OeB50 | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET4101 (Not POR) | Third Party | QAT3514;QAT3550 | WCN3998 | WCN3998 | 6GB | 3100 | 6.01" |  | 12M + 20M（3倍光学变焦） | Android P | TBD | SM8150.LA.1.0 | SB3 | Meizu in-house team the first SM8150 project，MEIZU brand Y2019 flagship phone | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-10-25 | 2018-12-26 | 2019-03-03 | 2018-06-25 | [7 empty] | 2019-04-12 | 2019-04-12 |  | Jiechu Gui | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Meizu brand next year flagship phone. 6.01" FHD+ display. target to launch in Apr,2019. upgrading the SW to Post-CS5 release. o SDV test stage. Will SIT LE review this week. TPE test ongoing in QC lab. 50pcs DVT1.1 phone with CS chipset under antenna/audio tuning , plan Dec,24 @1600pcs PVT with CS chipset. o Meizu decided to remove QC WCD codec as only digital earphone support . o OZ/Bokeh function ready. tuning ongoing. | Jiechu Gui | 2018-12-16 | [85 empty] | jgui@qct.qualcomm.com ; 2018-08-20 01:48:13Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | Column2: EVT; 2018-12-01 Column64: DVT | [31 empty] | PVT | [39 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F3A |  | Wireless Device | SmartPhone | a0D3A00000OS3IR | Talos | SM6150 | Beijing |  |  | PM6150;PM6150L | SDR660 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | >4GB | 3000 | 5.5 |  | 12M +5M +13M | Android P |  | SM6150.LA.1.0 | SB3 | Xiaomi 1st SM6150 in house project. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2019-01-11 | 2019-03-02 | 2019-04-12 |  |  | 2019-03-02 | [5 empty] | 2019-04-12 | 2019-04-12 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review; Schedule review |  |  | *F3 kickoff on 10/17; *P0 11/28, P1 1/11, P2 3/2, PreMP 4/8； *P0 build SMT start on 11/23, CS release upgrade done; code freeze plan on 1st Feb release; *SM6150 F3A &F3B projects planned from Xiaomi, F3-Android One planned for oversea market; *Camera code alignment with SM8150 need to be identified, start working on the CAMx/3A source application for SM6150; | Guowei Qin | 2018-12-18 | [25 empty] | Planning | [24 empty] | Staffed/In progress | 2017-05-15 | [33 empty] | gqin@qct.qualcomm.com ; 2018-12-14 09:02:35Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | WSA8815 x2 (Stereo) | SN100U | WCN |  |  |  | No |  | 1 High: Full QTI Support Required | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2019-01-01 Column80: EVT | [30 empty] | DVT | [40 empty] | PVT
China | Hing Lung Technology (HK) Company Limited | 4-Silver |  |  | SMP-J6001 |  | Wireless Device | IOT Smart POS | a0D3A00000OTBuk | Jacala | MSM8953 | XiaMen |  |  | PMI8952;PM8953 | WTR2965 |  | QFE2101 | Third Party | None | WCN3680B | WCN3660B | 2GB | 2850 | 5.99" |  |  | Android O |  | MSM8953.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-25 | 2019-01-30 | 2019-03-20 |  |  | 2019-02-15 | [5 empty] | 2019-04-15 | 2019-04-15 |  | Jiechu Gui |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Hing Lung MSM8953 smart pos for Medion *5.99" 2160 *1080 MIPI LCD | Jiechu Gui | 2018-11-29 | [85 empty] | jgui@qct.qualcomm.com ; 2018-11-30 02:41:13Z | [11 empty] | PM8953 |  |  | IoT Smart-Cities | Direct OEM Support |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B7 (FDD); B8 (FDD); B13 (FDD); B17 (FDD); B20 (FDD); B25 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column63: EVT; 2019-01-01 Column99: DVT | [48 empty] | PVT | [25 empty] | TA
China | Hing Lung Technology (HK) Company Limited | 4-Silver |  |  | SMP-J1401 |  | Wireless Device | IOT Smart POS | a0D3A00000OTBv9 | Jacala | MSM8953 | XiaMen |  |  | PMI8952;PM8953 | WTR2965 |  | QFE2101 | Third Party | None | WCN3680B | WCN3660B | 2GB |  | 14" |  |  | Android O |  | MSM8953.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-25 | 2019-01-30 | 2019-03-20 |  |  | 2019-02-15 | [5 empty] | 2019-04-15 | 2019-04-15 |  | Jiechu Gui |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Hing Lung MSM8953 smart dock pos for Medion *14" 1920 *1080 HDMI BOE LCD *external MIPI2HDMI convert | Jiechu Gui | 2018-11-29 | [85 empty] | jgui@qct.qualcomm.com ; 2018-11-30 03:00:16Z | [11 empty] | PM8953 |  |  | IoT Smart-Cities | Direct OEM Support |  | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B7 (FDD); B8 (FDD); B13 (FDD); B17 (FDD); B20 (FDD); B25 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column63: EVT; 2019-01-01 Column99: DVT | [48 empty] | PVT | [25 empty] | TA
China | OPPO | 1-Diamond |  |  | ED109 |  | Wireless Device | SmartPhone | a0D3A00000OdwJD | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8150 | SDR8150;SDR8154 |  | QET5100 | QPM5650;QPM4620 | QAT3516 (x2);QAT3550 (x2) | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP | Android P |  | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB2 | OnePlus 1st 5G project | Parent CP for Original design (OEM) |  | Design/Development | WE-EE (UK) | 2018-08-06 | 2019-02-05 | 2019-03-09 | [8 empty] | 2019-03-31 | 2019-04-15 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *OnePlus had change plan to test 4G only in Jan and asking QC share IOT update in weekly conf. *5G modem mini dump feature rejected on SDX50, need PDM to follow up with OPPO/OnePlus on their concern. *Request PCIE stress-test tool, no solution so far. *High standby current 35mA issue, checking by RIL team. | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [5 empty] | Staffed/In progress |  |  |  | zhiyangg@qct.qualcomm.com ; 2018-07-30 19:03:04Z |  | 2018-08-05 |  |  | zhiyangg@qct.qualcomm.com ; 2018-07-30 19:03:04Z | [31 empty] | 2018-01-04 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-10-15 01:57:45Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [105 empty] | DVT | [31 empty] | PVT | [36 empty] | TA
China | CloudMinds Inc. | 4-Silver |  |  | A2H_TMO |  | Wireless Device | SmartPhone | a0D3A00000OSawm | Nazgul | MSM8998 | Beijing |  |  | PM8005;PM8998;PMI8998 | WTR5975 |  | QET4100 | Third Party | QAT3514 | WCN3990 | WCN3990 BT | 4GB | 4500 | 5.7inch |  | 12M | Android O | MSM8998.LA.2.0.1-00162-STD.PROD-1 | MSM8998.LA.2.0.1 | SB4 |  | Existing design to a different carrier | A2H_ATT | Evaluation | NA - T-Mobile (USA) | [5 empty] | 2019-03-04 |  | 2019-04-01 |  |  |  | 2019-04-15 | 2019-04-15 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * A2H project for TMO USA * Launch in April 2019. The detail schedule is under discussion with TMO. * Internal development: 2018/11/1 - 2019/2/25 * RC1 2019/3/4 - 3/29/2019 * RC2 2019/4/1 - 4/13 * CloudMinds check B71 support on AT2.0.C4. It is not supported. | Huize Wang | 2018-12-10 | [85 empty] | huizew@qct.qualcomm.com ; 2018-10-25 02:39:49Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | North America (NA) | WSA8815 | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD); B29 (FDD); B30 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | 3D camera | [26 empty] | Evaluation project: No need CPI audit | [174 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | LST_MU8950D_071 | MU990 | Wireless Device | SmartPhone | a0D3A00000OSgMs | Jacala | SDM450 |  |  |  | PM8953;PMI8952 | WTR3925 |  | QFE2101 | Third Party | Third Party | WCN3660B | WCN3680B | >12GB |  |  |  |  | Android O | TBD | SDM450.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-12 | 2019-01-21 | 2019-03-18 | [8 empty] | 2019-04-15 | 2019-04-15 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * It is SUNSEA project, HW board for SCANNER.。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-10-31 03:16:32Z | [11 empty] | NA |  |  | Mobile |  |  | China | NA | No NFC | WCN |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column20: EVT; 2019-01-01 Column90: DVT | [46 empty] | PVT | [27 empty] | TA
China | Yulong | 2-Platinum |  |  | 302A |  | Wireless Device | Wearable | a0D3A00000OKnsV | Cheel | MSM8909W | Shenzhen |  |  | PMW3100 | WTR2965 |  | QFE2101 | None | None | WCN3620 | WCN3620 | 512MB | 605 | 1.22" |  | NO | Android N | MSM8909W.LAW.2.0-00035-STD.PROD-1 | MSM8909W.LAW.3.0.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | NA - T-Mobile (USA) | 2017-10-30 | 2017-11-15 | 2017-11-30 | [8 empty] | 2018-06-21 | 2019-04-19 |  | Min Fang |  | 1 | 1 |  |  |  | * Yulong SDW2500watch product for TMO. * under evaluation. | Min Fang | 2018-11-29 |  |  |  | Direct OEM support | c_vingut@qct.qualcomm.com ; 2017-02-01 15:45:37Z | [80 empty] | mfang@qct.qualcomm.com ; 2018-12-14 06:51:28Z | [11 empty] | PM8916 |  |  | IoT Wearable | Direct OEM Support | CXA4429GC: Ant. Swtich | China; North America (NA) | NA | No NFC | None |  |  | B2 (FDD); B4 (FDD) | No | [32 empty] | Evaluation project: No need CPI audit | [178 empty] | TA
China | Xiaomi | 1-Diamond |  |  | E5G |  | Wireless Device | SmartPhone | a0D3A00000OS3Ig | Carrera | SDX50M + SM8150 | Beijing |  |  | PM8005 | SDR8154 |  | QET5100 | QPM5650;QPM5651 | Third Party | WCN3998 | WCN3998 | >4GB |  |  |  | 48M + 12M | Android P |  | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB3 | XiaoMi 5G SDX50 Sub6 leading project for VDF | Parent CP for Original design (OEM) |  | Design/Development | WE - Vodafone (U.K.) | 2018-09-13 | 2018-11-20 | 2019-03-24 | [8 empty] | 2019-04-01 | 2019-04-19 |  | Wilson Fu | Michael Liu | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | * XiaoMI 5G VDF product * P0 @9/13; P1 @11/20; P2 @ 1/7/19; MP @ 3/24 * precs2.5 posted, CS delay to 1/31. * E5G plan 2019 MWC demo | Wilson Fu | 2018-12-23 | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:33:46Z | [5 empty] | Planning |  |  |  |  | Planning | 2018-08-18 | [8 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [29 empty] | Planning |  |  |  |  | wilsonf@qct.qualcomm.com ; 2018-12-16 16:06:59Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | Western Europe (WE) | Other | SN100U | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm |  |  | [CCB Assignment: Mingchen Gao/Monkey Hou] [CCB Support Type: DRI] [CCB Note: (5/26/2018) Xiaomi next flagship, features under discussion] [CCB Support Level: High] [CCB Score: 34] [CCB Project Info: Project: F1, ID: a0D3A00000OM0ZC] [DRI/POC: Mingchen Gao/Monkey Hou] | Mingchen Gao/Monkey Hou | 34 | High | (5/26/2018) Xiaomi next flagship, features under discussion | DRI | Mingchen Gao/Monkey Hou | [20 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column28: DVT | [52 empty] | PVT | [25 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F3B |  | Wireless Device | SmartPhone | a0D3A00000OZjLU | Talos | SM6150 | Beijing |  |  | PM6150;PM6150L | SDR660 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | >4GB | 3000 | 5.5 |  | 12M +5M +13M | Android P |  | SM6150.LA.1.0 | SB4 | Xiaomi 1st SM6150 in house project. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2019-01-16 | 2019-03-07 | 2019-04-19 |  |  | 2019-03-07 | [5 empty] | 2019-04-19 | 2019-04-19 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review; Schedule review |  |  | *F3B kickoff on 10/17; *P0 12/20, P1 1/16, P2 3/7, PreMP 419； *P0 build SMT start on 12/20, CS release upgrade done; *SM6150 F3A &F3B projects planned from Xiaomi, F3-Android One planned for oversea market; *Camera code alignment with SM8150 need to be identified, start working on the CAMx/3A source application for SM6150; | Guowei Qin | 2018-12-14 | [25 empty] | Planning | [24 empty] | Staffed/In progress | 2017-05-15 | [33 empty] | gqin@qct.qualcomm.com ; 2018-12-14 09:02:10Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | WSA8815 x2 (Stereo) | SN100U | WCN |  |  |  | No |  | 1 High: Full QTI Support Required | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2019-01-01 Column85: EVT | [35 empty] | DVT | [42 empty] | PVT
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_SDM450_B4 | 5FFD41 | Wireless Device | SmartPhone | a0D3A00000OSMDl | Jacala | SDM450 | Beijing |  |  | PMI632 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 3GB |  |  |  |  | Android O |  | SDM450.LA.3.2.c1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-10-24 | 2018-12-25 | 2019-04-22 | [8 empty] | 2019-04-22 | 2019-04-22 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * SDM450 Shanghai smartphone project * Pl: Yang Yunxia 13917042100 * No update this week. | Jiuyao Shu | 2018-12-11 | [85 empty] | jshu@qct.qualcomm.com ; 2018-10-09 14:08:08Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B26 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column63: DVT | [81 empty] | PVT
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_SDM450_G7 | G7 | Wireless Device | SmartPhone | a0D3A00000OTBte | Jacala | SDM450 | Beijing |  |  | PM8953;PMI8952 | WTR2965 |  | QFE2101 | Third Party | Third Party | WCN3680B | WCN3680B | 3GB |  |  |  |  | Android N |  | MSM8953.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2019-01-10 | 2019-03-06 | 2019-04-22 | [8 empty] | 2019-04-22 | 2019-04-22 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * SDM450 Beijing smart scanner device. * Pl: Nie Qilei 13810493899. * New project | Jiuyao Shu | 2018-11-29 | [85 empty] | jshu@qct.qualcomm.com ; 2018-11-30 01:55:25Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2019-01-01 Column79: EVT | [34 empty] | DVT | [46 empty] | PVT
China | ZTE | 1-Diamond |  |  | Z2321V | Z2321V | Wireless Device | SmartPhone | a0D3A00000OGxdB | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB | 1500 | 2.8"+1.77" TFT QVGA |  | 2M | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 | * ZTE-NA 8909 Android Go key project for VzW. | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless | 2018-03-20 | 2018-04-20 | 2018-06-20 | 2018-04-01 |  | 2018-04-01 |  | 2018-05-01 |  | 2018-07-01 |  | 2018-08-31 | 2019-04-22 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE-NA 8909 Android Go key project (smart feature phone) for Verizon/USCC. * Project status: confirmed, target TA by end of Apr 2019. * Product spec: 8909/512M+4GB/2.8''+1.77'' * Need to use JO 3.1 modem for RTT support, ZTE have to maintain the combo (JO 3.1 + keep other components as 8909 LA 3.0.1 ) by themselves. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-11-30 02:41:06Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | None |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B13 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [181 empty] | TA
China | OPPO | 1-Diamond |  |  | ED113 |  | Wireless Device | SmartPhone | a0D3A00000ORj8f | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | QPM4650 | QAT3514 (x2);QAT3550 (x2) | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP | Android P |  | SM8150.LA.1.0 | SB3 | OnePlus’s SM8150 project for TMO US, high volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | NA - T-Mobile (USA) | 2018-09-24 | 2018-02-05 | 2018-02-09 | [8 empty] | 2019-04-25 | 2019-04-25 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *Dual SIM request from OnePlus by TMO, BD/PDM team is discussing internally *QC suggest 2018Q4 MTR shall be good enough, waiting customer feedback *QTuner char can be done waiting OnePlus antenna to be ready. | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-11-14 08:53:55Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [184 empty] | TA
China | Nokia of America Corporation | 4-Silver |  |  | Fast Mile R3 5G CPE | Fast Mile R3 5G CPE | Wireless Device | Fixed WAN Router | a0D3A00000OejO0 | Carrera | SDX50M + SM8150 | Shanghai |  |  | PM8005;PMK8002 | SDR8150;SDR8154 |  | QET5100;QET5100M | QPM4621;QPM4630;QPM4641;QPM5650;QPM5651 | QAT3518;QAT3550 | No WLAN | No BT | 6GB | 3500 |  |  | 12M+5M | Android P | SM8150.LA.1.5 + SDX50M.TN.2.0 ES | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB4 | Nokia 1st official 5G project; | Parent CP for Original design (OEM) |  | Design/Development | ROW - Optus (Australia) | 2018-08-23 | 2018-10-24 | 2019-01-29 | [8 empty] | 2019-04-25 | 2019-04-25 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *Nokia schedule * schematic design (pending on architecture feedback): 18wk30 - 18wk32(8/6). Qualcomm schematic review support is needed since week 33(8/13) * layout design: 18wk33(8/13) - 18wk36, Qualcomm layout review is needed since 18wk36(9/3), including PI/SI support in 18wk37(9/10) * PCB build: 18wk38-18wk39(9/24) * SMT: 18wk40(10/5) * Board bring-up: 18wk41(10/8). Request Qualcomm on-site support in Nokia SH -lab . test instrument for 5G sub6GHz Keysi *Doing HW verification | Haijun Wang | 2018-12-03 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z | [21 empty] | 2016-07-11 | [14 empty] | 2016-07-11 |  |  |  |  | 2016-08-14 |  |  |  |  | 2017-10-08 | [29 empty] | 2016-02-20 |  |  |  | haijunw@qct.qualcomm.com ; 2018-07-23 05:22:41Z | [11 empty] | NA |  |  | Mobile |  |  | China; Rest of World (ROW) | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B4 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR4X | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty |  | 2019-01-01 Column98: PVT | [84 empty] | TA
China | OPPO | 1-Diamond |  |  | BD229 |  | Wireless Device | SmartPhone | a0D3A00000ORpVs | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8005;PM8150;PM8150A;PM8150B;PMK8002;PMX50 | SDR8150;SDR8154 |  | QET5100 | QPM5650 | QAT3518 (x2) | WCN3998 | WCN3998 | >4GB |  | 6.67" |  | TBD | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | [SM8150.LA.1.5 + SDX50M.TN.2.0].r1 | SB3 | OPPO's 1st SM8150 5G official launch, it is also Swisscom's 1st 5G launch. | Parent CP for Original design (OEM) |  | Design/Development | WE - Swisscom | 2019-01-04 | 2019-02-14 | 2019-03-19 |  |  | 2019-02-24 |  | 2019-03-31 |  | 2019-04-28 |  | 2019-04-26 | 2019-04-26 |  | Magic Wang |  | 1 | 1 |  |  |  | * this project will be used for MWC demo. * EVB BU is ongoing, most of functions go well. * OPPO demo with Ericsson started, the 1st OTA Sub6 call is successfully. * FR "5G mini dump" is rejected. We need to provide the justification to OPPO. PdM to follow it. * FR "FR54464:Diag-over-socket to be supported on SDX50M/SDX55 fusion platform" is rejected. PdM to communicate with OPPO. * RF is the main problem area. | Magic Wang | 2018-12-23 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-11-23 09:45:16Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | Western Europe (WE) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B29 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2019-01-01 Column73: EVT | [14 empty] | DVT | [32 empty] | PVT | [37 empty] | TA
China | Huaqin | 2-Platinum |  |  | Q2070-Lenovo | Lenovo M8 | Wireless Device | Tablet | a0D3A00000OSKsN | Hathi | SDM429 | Shanghai |  |  | PM439;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3680B | WCN3680B | 2GB | 4850 | 10.1"/1280x800 |  | 5M | Android P |  | SDM429.LA.1.0.1 | SB4 | ODM for Lenovo as Tablet project | Parent CP for Original design (OEM) |  | Evaluation | ROW - Open Market | 2018-11-16 | 2018-12-28 | 2019-02-18 | [8 empty] | 2019-04-29 | 2019-04-29 |  | Hongye Liu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * SDM429 Tablet for Lenovo, has another SKU with SDA429 with wifi only * Project is under bidding; *Requires Non-PORed Y-Cable and PoGo charging. Following Longcheer's request discussion with PMIC and USB team | Hongye Liu | 2018-11-22 | [28 empty] | 2 | [56 empty] | hongyel@qct.qualcomm.com ; 2018-10-08 06:15:19Z | [11 empty] | NA |  |  | Compute |  |  | Rest of World (ROW) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Evaluation project: No need CPI audit |  | 2018-11-01 Column24: EVT; 2018-12-01 Column66: DVT | [18 empty] | PVT | [69 empty] | TA
China | ZTE | 1-Diamond |  |  | K83V | K83V | Wireless Device | Tablet | a0D3A00000OT1f3 | Feero Lite | MSM8917 | Shanghai |  |  | PM8937;PMI8952 | WTR2965 |  | QFE2101 | Third Party | None | WCN3680B | WCN3680B | 2GB | 4600 | 8'' |  | 8M | Android P | MSM8917.LA.3.1.2 | MSM8917.LA.3.1.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless |  | 2019-04-01 |  |  |  | 2019-01-10 |  | 2018-06-20 |  |  |  | 2019-04-29 | 2019-04-29 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE 8917 Android P tablet project for VzW based on 2016 SPF 3.1.2 PL. * LCD: 8", 800 *1280. * Need to support LTE B66, layout review ongoing. * Project status: confirmed, target TA by mid of Apr 2019. | Frank Lu | 2018-12-16 | [85 empty] | binli@qct.qualcomm.com ; 2018-12-03 01:22:16Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | None |  | FDD | B2 (FDD); B4 (FDD); B5 (FDD); B13 (FDD) | No |  | 2 Medium: Case by Case Support On Demand |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [160 empty] | DVT | [27 empty] | TA
China | Huawei | 1-Diamond |  |  | Dubai(In-house)-Overseas |  | Wireless Device | SmartPhone | a0D3A00000OeYMg | Jacala | SDM450 | Xi'an |  |  | PMI632;PM8953 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660B | WCN3615 | 3GB | 4000 | 6.29" |  | 13M+2M | Android O |  | SDM450.LA.3.2 | SB4 | *Huawei's leading SDM450 project. It has big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-07-08 | 2018-07-28 | 2018-08-28 |  |  | 2018-08-28 | [5 empty] | 2019-04-30 | 2019-04-29 |  | Yizhen Yang | Nikhil Shevade | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | *In-house design. For Overseas market | Yizhen Yang | 2018-12-23 | [85 empty] | yizheny@qct.qualcomm.com ; 2018-12-21 03:07:15Z | [11 empty] | PM8953 |  |  | Mobile |  |  | Rest of World (ROW) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [188 empty] | TA
China | Longcheer | 2-Platinum |  |  | P400 | Lenovo M10 | Wireless Device | Tablet | a0D3A00000OS859 | Hathi | SDM429 | Shanghai |  |  | PM439;PMI632 | WTR2965 |  | Third Party | Third Party | None | WCN3680B | WCN3680B | 2GB | 4850 | 10.1"/1280x800 |  | 5M | Android P |  | SDM429.LA.1.0.1 | SB4 | ODM for Lenovo as Tablet project | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-10-21 | 2018-12-14 | 2019-03-17 | [8 empty] | 2019-04-29 | 2019-04-29 |  | Li Wang | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * SDM429 Tablet for Lenovo, has another SKU with SDA429 with wifif only * EVT Returned and bring up done * Risk: Requires Non-PORed Y-Cable and PoGo charging << Lenovo rejected our SOW and downgraded to PoGo PIN charging only, propose to let Longcheer handle the requirement | Li Wang | 2018-11-19 | [28 empty] | 2 | [56 empty] | liw@qct.qualcomm.com ; 2018-10-30 05:47:28Z | [11 empty] | NA |  |  | Compute |  |  | Rest of World (ROW) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column52: DVT | [45 empty] | PVT | [42 empty] | TA
China | Quectel | 2-Platinum |  |  | U358 |  | Automotive | Telematics | a0D3A00000Odm36 | Lykan | MDM9628 | Shanghai |  |  | PMD9607 | WTR2965 |  | QFE2101 | Third Party | None | QCA6564A-3 | QCA6564A-3 | 256MB |  |  |  |  | Linux Other |  | MDM9607.LE.2.2 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - China Telecom (CTC) | 2018-04-02 | 2018-06-25 | 2019-01-21 |  |  | 2017-04-15 | [5 empty] | 2019-04-29 | 2019-04-29 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Quectel MDM9628 Telematics Box to Desay with QX-PPE/QDR support on LE2.2 * Cooperation with Desay + PATAC | Li Wang | 2018-09-03 | [85 empty] | liw@qct.qualcomm.com ; 2018-09-03 08:14:00Z | [11 empty] | NA |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2019-01-01 Column90: PVT | [88 empty] | TA
China | ThunderSoft | 2-Platinum |  |  | TS_630_XP8_O_upgrade | Sonim XP8 | Wireless Device | SmartPhone | a0D3A00000OT96Y | Starhawk | SDM630 | Beijing |  |  | PM660;PM660L | SDR660 |  | QET4101 | Third Party | None | WCN3980 | WCN3980 BT | 4GB | 4900 | 6'' |  | 13M | Android O | Snapdragon_High_Mid_2017.SPF.1.0 1.0_00523.0 | SDM630.LA.1.0 | SB4 |  | MR - Updated OS | Sonim_630_XP8 | Design/Development | NA - AT&T Wireless | 2017-03-29 | 2017-05-30 | 2017-07-30 |  |  | 2019-02-25 |  | 2017-10-16 |  | 2017-11-27 |  | 2019-04-29 | 2019-04-29 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | * Sonim Beijing team for HW * Thundersoft for SW part * base project is TS_630_XP8 * PL: Chen Bing 18600048884. | Jiuyao Shu | 2018-11-27 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2015-07-12 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | jshu@qct.qualcomm.com ; 2018-11-28 06:35:44Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | North America (NA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B17 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD); B29 (FDD); B30 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [188 empty] | TA
China | Dongguan BBK Educational Technology Corp., Ltd. | 4-Silver |  |  | i18 |  | Wireless Device | IOT Kids watch | a0D3A00000ORvVq | Cheel | MSM8909W | Shenzhen |  |  | PM8916-1 | WTR2965 |  | QFE2101 | None | None | WCN3620 | WCN3620 | 512MB |  |  |  |  | Android for Wearables (LAW) |  | MSM8909W.LAW.2.0 | SB3 | BBK Ed CY19 flagship kid watch. Big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-04-29 | 2019-04-29 |  | Andy Li |  | 1 | 1 |  |  |  | * Flagship product for CY19 * 8MP+5MP dual camera | Andy Li | 2018-09-11 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-09-11 08:49:54Z | [11 empty] | NA |  |  | IoT Wearable | Direct OEM Support |  | China |  | Other | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [188 empty] | TA
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_SDM845_Wonder |  | Wireless Device | SmartPhone | a0D3A00000OSLd6 | Napali | SDM845 | Beijing |  |  | PM8005;PM8998;PM845 | SDR845 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | 4GB |  | 5.65“ |  | 12M | Android P |  | SDM845.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-06-04 | 2018-08-06 | 2019-03-25 | [8 empty] | 2019-04-30 | 2019-04-30 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Game phone for NA open. * SIM Beijing 845 project. * PM: Wang Yu 13661304174. * No update this week. * EV1 board is released and will be back in the beggining of Jan,2019. | Jiuyao Shu | 2018-12-11 | [85 empty] | jshu@qct.qualcomm.com ; 2018-10-09 06:33:40Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | North America (NA) | Other | Other | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B40 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [153 empty] | PVT | [35 empty] | TA
China | BBK | 1-Diamond |  |  | PD1823 |  | Wireless Device | SmartPhone | a0D3A00000OZpgJ | Warlock | SDM710 | Shenzhen |  |  | Other;PM670A | Other |  | None | Third Party | Third Party | WCN3990 | WCN3990 BT | 6GB | 3400 | 6.28’ |  | 48M+ 12M | Android P | SDM710.LA.2.0-00050-STD.PROD-2 | SDM710.LA.2.0 | SB4 | * Second SDM710 product ,big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-01 | 2018-12-15 | 2018-01-15 | [8 empty] | 2019-04-30 | 2019-04-30 |  | Hui Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | * Schematic review is ongoing. | Hui Zhang | 2018-12-22 | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2018-11-02 01:55:07Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [19 empty] | Staffed/In progress | 2015-11-02 |  |  |  | Planning |  |  |  |  | zhanghui@qct.qualcomm.com ; 2018-12-22 09:50:09Z | [11 empty] | PM660 |  |  | Mobile |  | QLN 4640 PRx | China | Other | No NFC | None |  | TDD | B1 (FDD); B3 (FDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-11-01 Column9: EVT; 2018-12-01 Column53: DVT | [89 empty] | TA
China | JSR Limited | 3-Gold |  |  | N75 |  | Wireless Device | Embedded Module | a0D3A00000Oepe1 | Lykan | MDM9607 | Shenzhen |  |  | PMD9607 | WTR2965 |  | QFE2101 | Third Party | None | No WLAN | Other | 256MB | 0 |  |  |  | Linux Other | MDM9607.LE.2.1 | MDM9607.LE.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-30 | 2019-01-30 | 2019-03-30 | [8 empty] | 2019-04-30 | 2019-04-30 |  | Xiangkui Liu |  | 1 | 1 |  |  |  | * The N75 is mdm9207 modem which need pass PTCRB and AT&T Certification * EVT phase, taped out the 1st board in 12/15, and waiting for the board back for debugging. | Xiangkui Liu | 2018-12-23 | [85 empty] | xiangkui@qct.qualcomm.com ; 2018-12-07 03:14:04Z | [11 empty] | NA |  |  | IoT Smart-Cities |  | WTR2955+SKY77643-21+QFE2101+SKY77916-21 | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B17 (FDD); B34 (TDD); B39 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column68: EVT; 2019-01-01 Column99: DVT | [58 empty] | PVT | [30 empty] | TA
China | Fibocom Wireless Inc. | 3-Gold |  |  | SC826-AHD | SC826-AHD | Wireless Device | Auto Infotainment | a0D3A00000OSllI | Jacala | MSM8953 | Shenzhen |  |  | PM8953;PMI8952 | WTR3925 |  | None | Third Party | None | WCN3660B | WCN3680B | 1GB | 4620 | 5" |  |  | Android N | MSM8953.LA.2.0 | MSM8953.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-20 | 2018-12-15 | 2019-03-15 | [8 empty] | 2019-04-30 | 2019-04-30 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Auto infotainment project on MSM8953 N. * The target launch time is at Q2 of 2019. * Evaluation phase, taped out the 1st board and waiting for the board back for bring up | Xiangkui Liu | 2018-12-16 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-11-05 07:18:52Z | [11 empty] | PM8953 |  |  | Automotive | Direct OEM Support |  | China | NA | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column28: EVT; 2018-12-01 Column53: DVT | [43 empty] | PVT | [45 empty] | TA
China | Lenovo | 1-Diamond |  |  | Foles | Moto Z3 play | Wireless Device | SmartPhone | a0D3A00000Oeezg | Talos | SM6150 | XiaMen |  |  | PM6150 | SDR660 |  | QET4101 | Third Party | QAT3550 | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 48M | Android P | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SM6150.LA.1.0 | SB3 | Next generation Moto Z | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2018-09-26 | 2018-11-09 | 2019-02-18 | 2018-04-15 |  | 2019-01-15 | [5 empty] | 2019-04-30 | 2019-04-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *SW working to rebase onto post CS1 *Several stability issues under tracking *HW DVT1B SMT on-going *Mini DP feature delivered, HDCP1.3 under Lenovo verification *MS0 testing *Lenovo feature developing on-going, Moto mods, camera, audio on-going *Pre-FT on-going *Lenovo Xiamen 6150 project | Gavin Song | 2018-12-18 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2017-08-17 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-09-21 02:42:33Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column17: DVT | [18 empty] | PVT | [70 empty] | TA
China | ZTE | 1-Diamond |  |  | P855A21 |  | Wireless Device | SmartPhone | a0D3A00000OTBSF | Carrera | SDX50M + SM8150 | Shanghai |  |  | PM8005;PM8150;PM8150A;PM8150B;PM8150L;PMK8002;PMX50 | QTM052;SDR8150;SDR8154 |  | QET5100 | QPM4621;QPM5650;QPM5651;QPM6582;QPA2625;QPM4630;QPM4640 | QAT3516 (x2);QAT3550 | WCN3998 | WCN3998 | 6GB |  | 6.47 |  | 48M+20M | Android P |  | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB4 | ZTE's 5G mobile project for CMCC | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2019-01-08 |  |  |  |  | 2019-02-15 | [5 empty] | 2019-04-30 | 2019-04-30 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE's 5G mobile phone for CMCC as Axon X | Baoming Zhang | 2018-11-29 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-11-29 14:46:14Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2019-01-01 Column77: EVT | [89 empty] | TA
China | Wingtech | 2-Platinum |  |  | N81850 | For Huawei | Wireless Device | Laptop | a0D3A00000OKjQY | Napali | SDM850 | Shanghai |  |  | PM845;PM8998 | SDR845 |  | None | None | None | WCN3990 | WCN3990 BT | 4GB | 3000 | 5.5 | FHD (1920x1080) | 13M | Win10 Redstone |  | SDM850.WP.1.2 | SB3 | Huawei’s first WoS laptop with mass volume forecast. WingTech is the ODM. | ODM or partner CP associated with an indirect account | Planck(SDM850) | Design/Development | China - Open Market | 2017-07-07 | 2017-09-19 | 2017-10-30 | [8 empty] | 2019-04-30 | 2019-04-30 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * V3 board was back last week o Continue have the workshop in Wingtech SH office this week, focus on Display/USB/Audio/Camera/Power/Stability/WCN/Power... o USB 3.0 Compliance test debugging, suggested Wingtech to change HW (adding Redriver), issue was fixed on V3 board o WCN EVM issue was fixed by Jiemei's temp solution on factory line o Will do FT very soon | Tian Zhou | 2018-12-23 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | Staffed/In progress |  |  | [QPA-0330] 1)RF SCH review had been finished on 12/20/2017; 2)Now customer is doing PCB layout, due to this project has a low priority, customer said PCB layout will be finished at the end of April. | qingweil@qct.qualcomm.com ; 2018-06-15 16:08:44Z |  |  |  |  | qingweil@qct.qualcomm.com ; 2018-08-13 00:36:04Z | [14 empty] | tzhou@qct.qualcomm.com ; 2017-03-30 01:57:15Z |  |  |  |  | tzhou@qct.qualcomm.com ; 2017-03-30 01:57:15Z |  |  |  |  | tzhou@qct.qualcomm.com ; 2017-03-30 01:57:15Z | [30 empty] | hyuan@qct.qualcomm.com ; 2018-12-24 01:53:48Z | [11 empty] | WCD9341 |  |  | Compute |  |  | China | WSA8815 x2 (Stereo) | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | 1x | C850 BC0; C1900 BC1 | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: RAM Type/technology : Empty | [189 empty] | TA
China | Lenovo | 1-Diamond |  |  | Zhanlang | TBD | Wireless Device | SmartPhone | a0D3A00000Ods8T | Other | ZZ_A Product Not Listed | Beijing |  |  | Other | Other |  | Other | Other | Other | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 24MP | Android P |  | SDM710.LA.1.0 | SB4 | China BU SDM855 product | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2016-03-07 | 2016-04-11 | 2016-07-25 | 2016-06-15 |  | 2016-06-15 | [5 empty] | 2019-04-30 | 2019-04-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | DM8150 | Gavin Song | 2018-05-31 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-05-31 08:02:40Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Evaluation project: No need CPI audit | [189 empty] | TA
China | Huaqin | 2-Platinum |  |  | WD2500 |  | Wireless Device | Wearable | a0D3A00000OeHQA | Cheel | MSM8909W | Xi'an |  |  | PMW3100 | WTR2965 |  | QET4101 | None | Third Party | WCN3620 | WCN3620 | 512MB | 660 | 1.4" |  |  | Android O |  | MSM8909W.LAW.3.0.0.1 | SB3 | Huaqin Watch PCBA project. Will fan out more projects. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-04-08 | 2018-06-20 | 2018-09-20 | [8 empty] | 2018-10-30 | 2019-04-30 |  | Yizhen Yang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review; Schedule review; SW architecture review |  |  | *Huaqin Watch PCBA project. *Huaqin ODM for Mobvoi project WD251 | Yizhen Yang | 2018-12-16 |  |  |  |  | junjiel@qct.qualcomm.com ; 2016-04-22 02:14:10Z | [80 empty] | yizheny@qct.qualcomm.com ; 2018-10-28 12:29:55Z | [11 empty] | Other |  |  | IoT Wearable | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [189 empty] | TA
China | IDEA International Development Limited | 3-Gold |  |  | H6630 | Otto-8 | Wireless Device | SmartPhone | a0D3A00000OT5yN | Starlord | SDM660 | Shenzhen |  |  | PM660L;PM660 | SDR660 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | 6GB | 3000 | 5' |  | 20M | Android P |  | SDM660.LA.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-15 | 2019-01-10 | 2019-03-15 | [8 empty] | 2019-04-30 | 2019-04-30 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Schematics Review; Layout Review; Schedule review |  |  | * IDEA second SDM660 project for China Open market. | Bruce Wang | 2018-11-22 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2017-11-13 23:38:11Z | [80 empty] | wbruce@qct.qualcomm.com ; 2018-11-23 06:31:15Z | [11 empty] | PM660 |  |  | Mobile | Direct OEM Support |  | China | Other | No NFC | None |  | TDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column53: EVT; 2019-01-01 Column79: DVT | [43 empty] | PVT | [45 empty] | TA
China | ZTE | 1-Diamond |  |  | P685M106 | P685M106 | Wireless Device | Fixed WAN Router | a0D3A00000OT66t | McLaren | MDM9250 | Xi'an |  |  | PMD9655 | WTR5975 |  | Third Party | Third Party | None | No WLAN | No BT | 256MB | 3000 |  |  |  | Linux Other | MDM9650.LE.1.2.c1-00015-NBOOT.GENNCH.NEFS.PROD-1 | MDM9650.LE.1.2.c1 | SB4 |  | Updated design |  | Design/Development | NA - Open Market | 2018-11-16 | 2018-11-30 | 2019-01-30 |  |  | 2019-01-30 | 2019-03-15 | 2019-04-15 |  |  |  | 2019-04-30 | 2019-04-30 |  | Nicholas Chen | Eugenia Chen | 1 | 1 |  |  |  | * EVT phase, leverage previous board, new PCB will be TO this week * ZTE kicked off CPE on MDM9250+WTR5975+QCA9563 for Mexico SKY | Nicholas Chen | 2018-12-17 |  |  |  |  | jic@qct.qualcomm.com ; 2015-11-12 03:17:21Z | [55 empty] | Planning |  |  |  |  | Planning | [19 empty] | jic@qct.qualcomm.com ; 2018-11-23 09:48:28Z | [11 empty] | NA |  |  | Mobile |  |  | North America (NA) | NA | No NFC | None |  | FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B26 (FDD); B30 (FDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column24: EVT; 2018-11-01 Column38: DVT; 2019-01-01 Column99: PVT | [89 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F11 | Poco phone | Wireless Device | SmartPhone | a0D3A00000OegRU | Hana | SM8150 | Shenzhen |  |  | PM8150A;PM8150;PM8150B | SDR8150 |  | QET5100 | Third Party | QAT3550;Third Party | WCN3998 | WCN3998 | >4GB | 40000 |  |  | 48MP +8M + 13M | Android P |  | SM8150.LA.1.0 | SB3 | XiaoMi 855 leading project for India market, Poco brand. design by xiaomi Shenzhen team | Parent CP for Original design (OEM) |  | Design/Development | India - Open Market | 2018-12-11 | 2019-01-19 | 2019-03-09 | [8 empty] | 2019-04-30 | 2019-04-30 |  | Bruce Wang | Michael Liu | 1 | 1 | Access to documentation granted; Access to Case granted; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | * P0 @12/16; P0.1 @12/28; P1 @1/19/2019; P2 @3/09; MP @4/30; SW stable version branch out @2/28/2019; SW freeze might be pulled in to the b/Apr, 2019; * P0 board is ready for bring up this week and board bring up is ongoing. * Triple-Camera,48+8+13, support: 1) Triple-camera support for SAT is still under discussion within XiaoMi; 2) Ask Xiaomi to raise camera feature review case; * Support fine tuning on the performance of Qtuner QAT3550 on F11/SM8150 P0 board. | Bruce Wang | 2018-12-16 | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:33:46Z | [5 empty] | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [29 empty] | Planning |  |  |  |  | wbruce@qct.qualcomm.com ; 2018-11-21 04:01:58Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | China; India | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm |  |  | [CCB Assignment: Mingchen Gao/Monkey Hou] [CCB Support Type: DRI] [CCB Note: (5/26/2018) Xiaomi next flagship, features under discussion] [CCB Support Level: High] [CCB Score: 34] [CCB Project Info: Project: F1, ID: a0D3A00000OM0ZC] [DRI/POC: Mingchen Gao/Monkey Hou] | Mingchen Gao/Monkey Hou | 34 | High | (5/26/2018) Xiaomi next flagship, features under discussion | DRI | Mingchen Gao/Monkey Hou | [20 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column49: EVT; 2019-01-01 Column88: DVT | [37 empty] | PVT | [51 empty] | TA
China | Fibocom Wireless Inc. | 3-Gold |  |  | AL930 | AL930 | Automotive | Telematics | a0D3A00000ORgD5 | Lykan | MDM9628 | Shenzhen |  |  | PMD9607 | WTR2965 |  | Third Party | Third Party | None | No WLAN | No BT | 256MB |  |  |  |  | Linux Other |  | MDM9607.LE.2.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-01 | 2018-12-15 | 2019-02-01 |  |  | 2019-02-22 | [5 empty] | 2019-04-30 | 2019-04-30 |  | Xiangkui Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Fibocom MDM9628 Telematics * Evaluation phase , still collect customers' requirement for the project SPEC | Xiangkui Liu | 2018-12-16 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-09-25 02:13:41Z | [11 empty] | NA |  |  | Automotive | Direct OEM Support |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column9: EVT; 2018-12-01 Column53: DVT |  | PVT | [87 empty] | TA
China | Motorola | 1-Diamond |  |  | Foles | Moto Z3 play | Wireless Device | SmartPhone | a0D3A00000ORdlm | Talos | SM6150 | XiaMen |  |  | PM6150 | Other |  | QET4101 | Third Party | Third Party | WCN3980 | Integrated | 3GB | 3000 | 6'' |  | 12M | Android P | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SDM636.LA.2.1 | SB4 | Next generation Moto Z | Parent CP for Original design (OEM) |  | Evaluation | LA - Open Market | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-04-15 |  | 2018-04-15 | [5 empty] | 2019-04-30 | 2019-04-30 |  | Danish Siddiqui |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *SM6150 | Danish Siddiqui | 2018-08-20 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2017-08-17 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | dsiddiqu@qct.qualcomm.com ; 2018-11-08 06:57:13Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 |  | [CCB Assignment:Jintao Xu] [CCB Support Type:DRI] [CCB Note:Lenovo BJ takes front camera tuning, need training and support as SDM660 is new to Lenovo BJ] [CCB Support Level:High] [CCB Score:28] [DRI/PoC:Jintao Xu] | Jintao Xu | 28 | High | Lenovo BJ takes front camera tuning, need training and support as SDM660 is new to Lenovo BJ | DRI | Jintao Xu | [20 empty] | Evaluation project: No need CPI audit | [189 empty] | TA | [412 empty] | TA
China | Lenovo | 1-Diamond |  |  | Lake CMCC | Moto G | Wireless Device | SmartPhone | a0D3A00000OZmS5 | Blackbolt | SDM636 | Beijing |  |  | PM660 | SDR660 |  | None | Third Party | None | WCN3980 | WCN3980 BT | 3GB | 3000 | 6'' |  | 16MP + 5MP | Android N | Snapdragon_High_Mid_2017.SPF.1.0-00460-STD.PROD-1 | SDM636.LA.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2017-07-31 | 2017-09-11 | 2018-04-15 | 2018-04-15 |  | 2018-04-15 | [5 empty] | 2019-04-30 | 2019-04-30 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | *CMCC B lab | Gavin Song | 2018-12-19 | Completed | 2015-02-13 |  |  | huangeng@qct.qualcomm.com ; 2015-06-19 02:48:42Z | Completed | 2015-03-05 |  |  |  | Completed |  |  |  |  | Completed | 2015-03-18 |  |  |  | Staffed/In progress | 2017-08-17 |  |  |  | Staffed/In progress | 2015-06-01 |  |  |  | Completed | 2015-07-15 |  |  |  | Completed | 2015-07-08 |  |  |  | Completed | 2015-06-15 |  |  |  | Staffed/In progress | 2015-07-13 |  |  |  | Staffed/In progress | 2017-03-20 |  |  |  | Completed | 2015-07-30 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-05-15 |  |  |  | Completed | 2015-06-05 |  |  |  | Staffed/In progress | 2015-07-15 |  |  |  | Planning | 2015-09-15 |  |  |  | huangeng@qct.qualcomm.com ; 2018-12-19 08:12:35Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [189 empty] | TA
China | Samsung Co., Ltd. | 1-Diamond |  |  | SS_6150_A60_CHN | Galaxy A60 | Wireless Device | SmartPhone | a0D3A00000OTGif | Talos | SM6150 |  |  |  | PM6150A;PM6150 | SDR660 |  | QET4101 | Third Party | None | WCN3980 | WCN3980 BT | TBD/Unknown | 3600 | 6.3" |  | 32M + 8M + 5M | Android P | r1.0_00010.0 | SM6150.LA.1.0 | SB4 | * Target Apr'19 for China/HK/Taiwan * SS GZ project * designed based on the 6150 A70 | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-04-30 | 2019-04-30 |  | Jiuyao Shu | Nitin Mehrotra | 1 | 1 |  |  |  | * Samsung A60 project for China Open market. * HW : 杨茹 (Yang Ru, ru.yang) * SW : 曾石生(Zeng Shisheng, stone.zeng) 18002237132 * DVR: 2/1, PVR: 3/7, PRA: 3/21. SRA 3/31 * Schematic is done for this project. | Jiuyao Shu | 2018-12-23 |  |  |  |  | hyunjuk@qct.qualcomm.com ; 2018-11-01 01:04:46Z | [80 empty] | hyunjuk@qct.qualcomm.com ; 2018-12-06 01:30:36Z | [11 empty] | Other |  |  | Mobile |  |  | China |  | Other | WCN |  |  | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B20 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [189 empty] | TA
China | Shanghai LovDream Communication Technology Co., Ltd. | 4-Silver |  |  | C801 | H1 | Wireless Device | SmartPhone | a0D3A00000OTLh8 | Jacala | SDM450 | Shanghai |  |  | PM8953 | WTR2965 |  | Third Party | None | None | WCN3680B | WCN3680B | 3GB | 4500 | 5.2 |  | 12M | Android O | MSM8953.LA。.3.0.1-00340-STD.PROD- | MSM8953.LA.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | 2018-11-20 | 2018-12-25 | 2019-03-25 | [8 empty] | 2019-05-01 | 2019-05-01 |  | Weizheng Lv |  | 1 | 1 |  |  |  | * It is their first 450 project for Europe open market。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-12 06:30:55Z | [11 empty] | NA |  |  | Mobile |  |  | Western Europe (WE) | Other | Other | WCN |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column28: EVT; 2018-12-01 Column63: DVT | [53 empty] | PVT | [36 empty] | TA
China | Shenzhen Quchuang Technology Co., Ltd. | 4-Silver |  |  | QS6416 | QS6416 | Wireless Device | SmartPhone | a0D3A00000OS1Pk | Starlord | SDM660 | Shenzhen |  |  | PM660;PM660A | SDR660 |  | None | None | Third Party | WCN3990 | WCN3990 BT | 6GB | 3000 | 6.21" |  | 20W+16W | Android P |  | SDM660.LA.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-17 | 2019-01-17 | 2019-02-25 | [8 empty] | 2019-05-01 | 2019-05-01 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Concept review; Kickoff meeting |  |  | * Quchuang Android P phone based on SDM660 project. | Bruce Wang | 2018-09-17 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-09-17 09:07:17Z | [11 empty] | WCD9335 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR4X |  | PDAF | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column25: EVT; 2019-01-01 Column86: DVT | [25 empty] | PVT | [64 empty] | TA
China | Wingtech | 2-Platinum |  |  | S89632AA1 |  | Wireless Device | SmartPhone | a0D3A00000OSx0q | Hathi | SDM439 | Shanghai |  |  | PM439;PMI632 | WTR2965 |  | Third Party | Third Party | None | WCN3615 | WCN3615 | 2GB | 3000 | 5 |  | 13M | Android P | Snapdragon_High_Med_2016.SPF.1.0-05000-STD.PROD-1 | SDM439.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-12-10 | 2019-01-25 | 2019-03-08 | [8 empty] | 2019-05-03 | 2019-05-03 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Evaluation for OEM | Tian Zhou | 2018-11-15 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-11-16 03:46:18Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 |  | [CCB Assignment:Zhiqiang Jin, Gary Ge(Lab)] [CCB Support Type:DRI, Service Lab] [CCB Note:(8/22) Gary Ge(Lab): 8/24-8/31, ISP(1) ODM： Xiaomi C3B] [CCB Support Level:Mid] [CCB Score:26] [DRI/PoC:Zhiqiang Jin] | Zhiqiang Jin | 26 | Mid | (8/22) Gary Ge(Lab): 8/24-8/31, ISP(1) ODM： Xiaomi C3B | DRI, Service Lab | Zhiqiang Jin, Gary Ge(Lab) | [20 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column48: EVT; 2019-01-01 Column94: DVT | [36 empty] | PVT | [55 empty] | TA
China | Huaqin | 2-Platinum |  |  | QL1886-Meizu | Meizu M1926 | Wireless Device | SmartPhone | a0D3A00000OSllw | Other | ZZ_A Product Not Listed | Shanghai |  |  | Other | Other |  | Other | Other | Other | WCN3980 | WCN3980 BT | 4GB | 4000 | 6.2 |  | 16M | Android P | TBD | SM7150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2019-01-15 | 2019-02-10 | 2019-04-15 | 2019-04-15 |  | 2019-04-15 | [5 empty] | 2019-05-06 | 2019-05-06 |  | Qiang Liu |  | 1 | 1 |  |  |  | *Evaluation 7150 project for Meizu. | Bill Li | 2018-11-25 | [85 empty] | binli@qct.qualcomm.com ; 2018-11-05 08:15:33Z | [11 empty] | Other |  |  | Mobile | Direct OEM Support |  | China | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | Rear camera: tri-camera 48M+8M+5M Wide + Tele；Bayer + Depth | [26 empty] | Evaluation project: No need CPI audit |  | 2019-01-01 Column84: EVT | [10 empty] | DVT | [63 empty] | PVT | [20 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | SIM8100 | SIMCom CV2X module | Automotive | C-V2X | a0D3A00000OTAMy | McLaren | MDM9150 | Shanghai |  |  | PMD9655 | WTR5975 |  | None | Third Party | None | No WLAN | Other | 1GB |  |  |  |  | Linux Other | TBD | MDM9150.LE.1.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-12-03 | 2019-01-09 | 2019-02-18 | 2018-12-28 | [7 empty] | 2019-05-06 | 2019-05-06 |  | Weizheng Lv |  | 1 | 1 |  |  |  | *It is Sunsea first project for CV2x。 | Weizheng Lv | 2018-12-17 | [85 empty] | akhosla@qct.qualcomm.com ; 2018-12-06 21:31:11Z | [11 empty] | NA |  |  | Automotive |  |  | China | NA | Other | None |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column41: EVT; 2019-01-01 Column78: DVT | [18 empty] | PVT | [76 empty] | TA
China | Hisense | 2-Platinum |  |  | HLTE216T | HLTE216T | Wireless Device | SmartPhone | a0D3A00000OTALn | Shanti | SDM632 |  |  |  | PM8953 | WTR2965 |  | Third Party | Third Party | None | WCN3680B | WCN3680B | 4GB |  |  |  |  | Android P | SDM632.LA.1.0.1-00035-STD.PROD-2 | SDM632.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | 2019-01-14 | 2019-02-18 | 2019-04-08 | [8 empty] | 2019-05-06 | 2019-05-06 |  | Weizheng Lv |  | 1 | 1 |  |  |  | *It is HIsense first 632 project。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-11-29 08:45:06Z | [11 empty] | NA |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2019-01-01 Column83: EVT | [18 empty] | DVT | [48 empty] | PVT | [27 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F10 |  | Wireless Device | SmartPhone | a0D3A00000OSvMf | Moorea | SM7150 | Shenzhen |  |  | PM7150;PM7150A | Other |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | 8GB | 4000 | 6.39 inch 19.5:9 |  | 48MP +8M + 13M | Android P |  | SM7150.LA.1.0 | SB1 | XiaoMi SM7150 leading project. | Parent CP for Original design (OEM) |  | Design/Development | India - Open Market | 2019-01-19 | 2019-02-25 | 2019-04-01 | [8 empty] | 2019-05-06 | 2019-05-06 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * XiaoMi POCO team locks down the SM7150 platform for F10; SM7150 global leading project and target for India/China open market 1st wave launch; * Project schedule: Pre-P0 @b/Jan, P0 @1/19; P1 @2/25; P1.1 @the early stage of Mar; P2 @4/1; MP @5/20; SW stable version branch out @the early stage of Apr; SW freeze @b/May; * Need biz team to support Pre-P0 schedule with priority; * Joint test plan/ FiT test plan/ QIPL Joint lab plan/PPT plan/pre-cert lab test plan: will sync the detail b/w QC/XM. | Bruce Wang | 2018-12-16 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-12-12 05:43:18Z | [11 empty] | WCD9370 |  |  | Mobile |  | QLN | China; Eastern Europe (EE); India; South East Asia (SEA); Western Europe (WE) | Other | Undecided | WCN |  |  | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2019-01-01 Column88: EVT | [25 empty] | DVT | [34 empty] | PVT | [34 empty] | TA
China | CK Telecom (Heyuan) Limited | 3-Gold |  |  | FIND01A |  | Wireless Device | SmartPhone | a0D3A00000OS1OD | Hathi | SDM439 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | Third Party | Third Party | QAT3514 | WCN3680 | WCN3980 BT | 3GB | 3000 | 5.99" |  | 13MP | Android P | TBD | SDM439.LA.1.0.1 | SB4 | 1st SDM439 model from CKT, for Doro | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | 2018-11-02 | 2018-12-14 | 2019-03-28 |  |  | 2019-03-01 | [5 empty] | 2019-05-06 | 2019-05-06 |  | Jiechu Gui |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | *ODM for Doro EU open market, 5.7" HD+, 3+32 Memory project, under DVT1 phone HW/SW functional validation, sample phone under Doro testing. CE/GCF certification will test with DVT2 in early of Jan. | Jiechu Gui | 2018-12-16 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-09-02 00:16:33Z | [46 empty] | 2018-02-01 | [33 empty] | jgui@qct.qualcomm.com ; 2018-12-11 05:47:50Z | [11 empty] | PM8937 |  |  | Mobile |  |  | Western Europe (WE) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B38 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Third Party | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column10: EVT; 2018-12-01 Column52: DVT | [56 empty] | PVT | [38 empty] | TA
China | OPPO | 1-Diamond |  |  | BD189 |  | Wireless Device | SmartPhone | a0D3A00000OSxAD | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100 | Third Party | QAT3518 (x2) | WCN3998 | WCN3998 | >4GB |  | 6.67" |  | TBD | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SM8150.LA.1.0 | SB4 | OPPO's 1st SM8150 4G official launch, big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | WE-EE (UK) | 2018-12-14 | 2019-01-16 | 2019-03-02 |  |  | 2019-02-15 |  | 2019-03-22 |  | 2019-04-19 |  | 2019-05-10 | 2019-05-10 |  | Magic Wang |  | 1 | 1 |  |  |  | * EVB BU is ongoing, now most of functions go well, only camera still has issue, we are onsite support now. * Project weekly review meeting with OPPO. * Making SDM855 SW training plan to OPPO. * Weekly SDM855 review meeting with OPPO & OnePlus. | Magic Wang | 2018-11-16 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [46 empty] | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-11-16 10:14:26Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | Western Europe (WE) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B29 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD); B41-XGP (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column52: EVT; 2019-01-01 Column85: DVT | [30 empty] | PVT | [68 empty] | TA
China | Yulong | 2-Platinum |  |  | 3705AS |  | Wireless Device | SmartPhone | a0D3A00000OZnXY | Jacala | SDM450 | Nanjing |  |  | PMI632;PM8953 | WTR3925 |  | QFE2101 | QPA4360 | None | WCN3660B | WCN3660B | 3GB | 4000 | 1080P |  | 16M+5M | Android P | SDM450.LA.3.2.1-00010-STD.PROD-1 | SDM450.LA.3.2.1 | SB4 | It's Yulong's 1st SDM450 Android P project for TMO. Forecast 1Mu-3Mu. | Parent CP for Original design (OEM) |  | Design/Development | NA - Sprint | 2018-12-21 |  | 2019-02-25 |  |  | 2019-03-18 |  | 2019-04-15 |  | 2019-04-29 |  | 2019-05-10 | 2019-05-10 |  | Min Fang |  | 1 | 1 |  |  |  | * It's Yulong's 1st SDM450 Android P project for Sprint, B71 supported. * HW main change at the antenna solution vs TMO project. | Min Fang | 2018-12-19 | [85 empty] | mfang@qct.qualcomm.com ; 2018-12-20 02:22:38Z | [11 empty] | PM8952 |  |  | Mobile | Direct OEM Support | SKY77643-61、VC7912-61, VC1545 | North America (NA) | Other | No NFC | WCN |  | TDD/FDD | B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B25 (FDD); B26 (FDD); B41 (TDD) | No |  |  | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column59: EVT | [25 empty] | PVT | [73 empty] | TA
China | Huaqin | 2-Platinum |  |  | QL1828-Lenovo | Lenovo JD20 | Wireless Device | SmartPhone | a0D3A00000OSllm | Other | ZZ_A Product Not Listed | Shanghai |  |  | Other | Other |  | Other | Other | Other | WCN3998 | WCN3998 | 8GB | 3600 | 6.53 |  | 16M | Android P | TBD | SM7150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-12-09 | 2019-01-26 | 2019-03-02 | 2019-03-04 |  | 2019-03-04 | [5 empty] | 2019-05-13 | 2019-05-13 |  | Qiang Liu |  | 1 | 1 |  |  |  | *HW design review is ongoing *7150 evaluation project. The project schedule is finalized by Lenovo, due to tight schedule, many jobs will be based on ES release, risk is very high *Evaluation 7150 project for Lenovo | Qiang Liu | 2018-12-16 | [85 empty] | binli@qct.qualcomm.com ; 2018-11-05 07:54:51Z | [11 empty] | Other |  |  | Mobile | Direct OEM Support |  | China | Integrated | Other | WCN |  | TDD/FDD | B3 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | Rear camera: tri-camera 16M+8M+5M | [26 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column47: EVT; 2019-01-01 Column95: DVT | [30 empty] | PVT | [71 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | A9599 （OneNet） |  | Wireless Device | M2M Module | a0D3A00000OTLcj | Lykan | MDM9206 | Shanghai |  |  | PMD9607 | WTR2965 |  | None | None | None | No WLAN | No BT | <128MB |  |  |  | 5M | ThreadX | MDM9206.TX.1.0-00025-STD.PROD-1 | MDM9206.TX.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2016-11-28 | 2017-01-13 | 2017-02-28 |  |  | 2017-11-27 | [5 empty] | 2019-05-13 | 2019-05-13 |  | Weizheng Lv |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | *Derived from Lonsung project.。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-12 02:50:53Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B8 (FDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [202 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | A9500(CMCC NB) |  | Wireless Device | M2M Module | a0D3A00000OTLcU | Lykan | MDM9206 | Shanghai |  |  | PMD9607 | WTR2965 |  | None | None | None | No WLAN | No BT | <128MB |  |  |  | 5M | ThreadX | MDM9206.TX.1.0-00025-STD.PROD-1 | MDM9206.TX.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2016-11-28 | 2017-01-13 | 2017-02-28 |  |  | 2017-11-27 | [5 empty] | 2019-05-13 | 2019-05-13 |  | Weizheng Lv |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | *Derived from Lonsung project.。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-12 02:48:26Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B8 (FDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [202 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | A9500(CT) |  | Wireless Device | M2M Module | a0D3A00000OTLce | Lykan | MDM9206 | Shanghai |  |  | PMD9607 | WTR2965 |  | None | None | None | No WLAN | No BT | <128MB |  |  |  | 5M | ThreadX | MDM9206.TX.1.0-00025-STD.PROD-1 | MDM9206.TX.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Mobile (CMCC) | 2016-11-28 | 2017-01-13 | 2017-02-28 |  |  | 2017-11-27 | [5 empty] | 2019-05-13 | 2019-05-13 |  | Weizheng Lv |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | *Derived from Lonsung project.。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-12 02:50:17Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B8 (FDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [202 empty] | TA
China | Yulong | 2-Platinum |  |  | Tracker-NB_CC |  | Wireless Device | Tracking Device | a0D3A00000OH5Mk | Lykan | MDM9207 | Shenzhen |  |  | PMD9607 | WTR2965 |  | QFE2101 | Third Party | Third Party | QCA9377-3 | QCA9377-3 | 256MB |  |  |  |  | Linux Other |  | MDM9607.LE.2.0 | SB4 |  | Parent CP for Original design (OEM) | QHY001 | Design/Development | NA - Sprint | 2018-03-31 | 2018-04-30 | [9 empty] | 2018-08-30 | 2019-05-14 |  | Min Fang |  | 1 | 1 |  |  |  | * Coolpad 1st MDM9207 tracker for Spring. * Outsourced to Huiye, target TA by Q2/2019. | Min Fang | 2018-12-13 | [85 empty] | mfang@qct.qualcomm.com ; 2018-11-23 06:16:17Z | [11 empty] | Other |  |  | IoT Smart-Cities | Direct OEM Support | Switcher: CXA4429GC |  | Other | No NFC | None |  | FDD | B2 (FDD); B12 (FDD) | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [203 empty] | TA
China | Dongguan BBK Educational Technology Corp., Ltd. | 4-Silver |  |  | H7000 |  | Wireless Device | IOT Media Box | a0D3A00000OSLdf | Starlord | SDA660 |  |  |  | PM660A | None |  | None | None | None | WCN3990 | WCN3990 BT | 4GB |  |  |  |  | Android P |  | SDM660.LA.3.0 | SB4 | * BBK Ed flagship educational tablet * Target to launch in May'19 | Parent CP for Original design (OEM) |  | Design/Development | [12 empty] | 2019-05-15 | 2019-05-15 |  | Andy Li |  | 1 | 1 |  |  |  | * CY19 flagship educational tablet; * BBK Ed team to handle, provided tech trainings to customer. | Andy Li | 2018-10-30 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-10-09 07:31:37Z | [11 empty] | NA |  |  | IoT Media/TV | Direct OEM Support |  |  |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Operator1 : Empty Target Region : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [204 empty] | TA
China | Meizu | 2-Platinum |  |  | M1972 | Meizu | Wireless Device | SmartPhone | a0D3A00000OSeRq | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A | SDR8150 |  | QET5100 | Third Party | QAT3550 | WCN3998 | WCN3998 | 6GB | 3100 | 6.01" |  | 12M + 20M（3倍光学变焦） | Android P | TBD | SM8150.LA.1.0 | SB4 | Meizu in-house team the first SM8150 project，MEIZU brand Y2019 flagship phone | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2019-01-07 | 2019-02-25 | 2019-04-04 | 2019-02-28 | [7 empty] | 2019-05-15 | 2019-05-15 |  | Jiechu Gui | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | *Meizu inhouse team cancelled SM7150 project, plan change to SDM712 platform while not finalized yet. plan kick off next week | Jiechu Gui | 2018-12-16 | [85 empty] | jgui@qct.qualcomm.com ; 2018-12-24 02:02:02Z | [11 empty] | PM660 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Evaluation project: No need CPI audit |  | 2019-01-01 Column76: EVT | [25 empty] | DVT | [37 empty] | PVT | [40 empty] | TA
China | Smartisan Technology Co., Ltd. | 3-Gold |  |  | Mark | N/A | Wireless Device | SmartPhone | a0D3A00000OeWVp | Hana | SM8150 | Beijing |  |  | PM8150;PM8150A;PM8150L | SDR8150 |  | QET5100 | Third Party | None | WCN3998 | WCN3998 | 8GB | 0 | 5.97" |  | 12MP + 20 MP | Android P | SM8150.LA.1.0 | SM8150.LA.1.0 | SB4 | Smartisan Jianguo R serial, 2019 product | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2017-08-25 | 2017-10-27 | 2018-01-22 | [8 empty] | 2019-05-15 | 2019-05-15 |  | Tianhao Fei |  | 1 | 1 |  |  |  | martisan SM8150 project | Tianhao Fei | 2018-07-08 | [51 empty] | 2018-03-25 | [33 empty] | tfei@qct.qualcomm.com ; 2018-07-09 03:28:48Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  | TDD/FDD | B3 (FDD); B5 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  | 3 Low: No Need For QTI Support | Qualcomm | SDRAM-LPDDR4 |  | [CCB Support Type:TSP] [CCB Note:Customer has tuning resource. Support case by case (06/23) All Gold/Silver projects will not be supported by QC Engr. according to the latest management team decision] [CCB Support Level:Low] [CCB Score:20] |  | 20 | Low | Customer has tuning resource. Support case by case (06/23) All Gold/Silver projects will not be supported by QC Engr. according to the latest management team decision | TSP | [21 empty] | Evaluation project: No need CPI audit | [204 empty] | TA
China | Beijing OrionStars Technology Co., Ltd. | 4-Silver |  |  | Greetbot 2.0 |  | Wireless Device | IOT Robots | a0D3A00000OSUiW | Napali | SDA845 | Beijing |  |  | PM8005;PM845;PMI8998 | None |  | None | None | None | WCN3990 | WCN3990 BT | 8GB |  |  |  |  | Android P |  | SDM845.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-05-15 | 2019-05-15 |  | Andy Li |  | 1 | 1 |  |  |  | * 2nd generation companion robotics | Andy Li | 2018-10-17 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-10-18 03:35:21Z | [11 empty] | WCD9341 |  |  | IoT Robotics | Direct OEM Support |  | China |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [204 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F3A-Android One |  | Wireless Device | SmartPhone | a0D3A00000OZjLZ | Talos | SM6150 | Beijing |  |  | PM6150;PM6150L | SDR660 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | >4GB | 3000 | 5.5 |  | 12M +5M +13M | Android P |  | SM6150.LA.1.0 | SB4 | Xiaomi 1st SM6150 in house project. | Parent CP for Original design (OEM) | F3A | Design/Development |  | 2019-01-11 | 2019-03-02 | 2019-04-12 |  |  | 2019-03-02 | [5 empty] | 2019-05-16 | 2019-05-16 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review; Schedule review |  |  | *F3A nagtive Android Version for globle shipping; F3 kickoff on 10/17; *P0 11/23, P1 12/14, P2 1/23, PreMP 4/8； *P0 build SMT start on 11/23, CS release upgrade done; *SM6150 F3A &F3B projects planned from Xiaomi, F3-Android One planned for oversea market; *Camera code alignment with SM8150 need to be identified, start working on the CAMx/3A source application for SM6150; | Guowei Qin | 2018-12-14 | [25 empty] | Planning | [24 empty] | Staffed/In progress | 2017-05-15 | [33 empty] | gqin@qct.qualcomm.com ; 2018-12-14 09:05:24Z | [11 empty] | PM660 |  |  | Mobile |  |  | India; Rest of World (ROW) | WSA8815 x2 (Stereo) | SN100U | WCN |  |  |  | No |  | 1 High: Full QTI Support Required | Qualcomm | [29 empty] | Mandatory Filed: Operator1 : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2019-01-01 Column80: EVT | [30 empty] | DVT | [40 empty] | PVT | [33 empty] | TA
China | Excelpoint Systems (H.K.) Limited | 4-Silver |  |  | EXPL_NB001 |  | Wireless Device | M2M Module | a0D3A00000OLmql | Lykan | MDM9206 | Shenzhen |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | No WLAN | No BT | 128MB |  | M2M Module, NA |  | NA | ThreadX |  | MDM9206.TX.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2018-12-20 | 2019-05-17 | No potential customer confirmed, reschedule | Jiaqi Fan |  | 1 | 1 |  |  |  | * system from TX move to LE | Jiaqi Fan | 2018-08-06 | [85 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-24 04:35:03Z | [11 empty] | Other |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B26 (FDD); B28 (FDD); B39 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [206 empty] | TA
China | Excelpoint Systems (H.K.) Limited | 4-Silver |  |  | EXPL_NB001 |  | Wireless Device | M2M Module | a0D3A00000OLmqg | Lykan | MDM9206 | Shenzhen |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | No WLAN | No BT | 128MB |  | M2M module,NA |  | NA | ThreadX |  | MDM9206.TX.3.0.1 | SB4 | Seems I created two EXPL_NB001. They are the same. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2018-12-20 | 2019-05-17 | No potential customer confirmed , reschedule | Jiaqi Fan |  | 1 | 1 | [91 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-24 04:30:16Z | [11 empty] | Other |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B26 (FDD); B28 (FDD); B39 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [206 empty] | TA
China | Wingtech | 2-Platinum |  |  | S88940AA1 | Lenovo surf NA | Wireless Device | SmartPhone | a0D3A00000OS1Pz | Feero | MSM8940 | Shanghai |  |  | PM8940;PMI8940;PMI8952 | WTR3925 |  | None | Third Party;None | None | WCN3660B | WCN3660B | 2GB | 3000 | 5 |  | 13M | Android P |  | Snapdragon_High_Med_2016.SPF.1.0 | SB4 | Xiaomi's new 8940 model, very tough schedule | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-10-19 | 2018-12-21 | 2019-01-18 | [8 empty] | 2019-05-17 | 2019-05-17 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * New project kicks off. | Tian Zhou | 2018-12-09 | Staffed/In progress | 2016-05-16 |  |  | tzhou@qct.qualcomm.com ; 2016-05-19 19:39:52Z | Planning | 2016-05-23 | [8 empty] | Planning | 2016-06-03 | [11 empty] | 4 | [11 empty] | Risk/Blocked | 2016-08-24 |  |  |  | Staffed/In progress | 2016-09-01 | [38 empty] | tzhou@qct.qualcomm.com ; 2018-09-17 09:37:01Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column59: DVT; 2019-01-01 Column87: PVT | [106 empty] | TA
China | Wingtech | 2-Platinum |  |  | S88941AA1 | Lenovo surf NA | Wireless Device | SmartPhone | a0D3A00000OS1Ld | Feero | MSM8940 | Shanghai |  |  | PM8940;PMI8940;PMI8952 | WTR3925 |  | None | Third Party;None | None | WCN3660B | WCN3660B | 2GB | 3000 | 5 |  | 13M | Android P |  | MSM8917.LA.3.2.1 | SB4 | Xiaomi's new 8940 model, very tough schedule | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-10-19 | 2018-12-21 | 2019-01-18 | [8 empty] | 2019-05-17 | 2019-05-17 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * New project kicks off * Special case, will use 2018 SPF AP + 2016 SPF 8940 | Tian Zhou | 2018-11-22 | Staffed/In progress | 2016-05-16 |  |  | tzhou@qct.qualcomm.com ; 2016-05-19 19:39:52Z | Planning | 2016-05-23 | [8 empty] | Planning | 2016-06-03 | [11 empty] | 4 | [11 empty] | Risk/Blocked | 2016-08-24 |  |  |  | Staffed/In progress | 2016-09-01 | [38 empty] | tzhou@qct.qualcomm.com ; 2018-09-17 02:28:03Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: LTE Capability : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column59: DVT; 2019-01-01 Column87: PVT | [106 empty] | TA
China | TP-LINK Technologies Co., Ltd. | 4-Silver |  |  | TL-MDM9207_MR6400(LA00) | MR6400(LA00) | Wireless Device | Mobile Router | a0D3A00000OSvNb | Lykan | MDM9207 | Shenzhen |  |  | PMD9607 | WTR2965 |  | Third Party | Third Party | None | QCA9377-3 | QCA9377-3 | 128MB | 2000 |  |  |  | ThinUI (no MM) | MDM9607.LE.1.0-00052-STD.PROD | MDM9607.LE.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2018-12-27 | 2019-02-26 | 2019-05-20 | [8 empty] | 2019-05-20 | 2019-05-20 |  | Jiuyao Shu | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Mifi project for ISP in Latin America. * PL: Ma youhua 18681572960. * schematic and PCB review are done. | Jiuyao Shu | 2018-12-16 | [20 empty] | Staffed/In progress | [64 empty] | jshu@qct.qualcomm.com ; 2018-11-15 03:15:19Z | [11 empty] | Other |  |  | Mobile |  |  | Latin America (LA) | Other | No NFC | None |  | FDD | B1 (FDD); B2 (FDD); B4 (FDD); B6 (FDD); B7 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column65: EVT | [26 empty] | DVT | [82 empty] | PVT
China | Shenzhen Hipad Telecommunication Technology Co., Ltd. | 3-Gold |  |  | HP58B91 |  | Wireless Device | SmartPhone | a0D3A00000OTEWL | Hathi | SDM429 | Shanghai |  |  | PM439 | WTR2965 |  | None | Third Party | Third Party | WCN3615 | WCN3615 | 2GB | 3500 | 5.85 |  |  | Android P | SDM429 | SDM429.LA.1.1 | SB4 | * Hiipad first SDM429 project for self-brand. | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | [11 empty] | 2019-05-20 | 2019-05-20 |  | Jiaqi Fan |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * Hiipad first SDM429 project for self-brand. | Jiaqi Fan | 2018-12-04 | [28 empty] | 2 | [56 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-04 10:53:48Z | [11 empty] | Other |  |  | Mobile |  | HRTXAH005-01, CUC1294A-11,CUCT, AP7219M-71 | China | Integrated | Other | WCN |  | TDD/FDD | B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B17 (FDD); B28 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Evaluation project: No need CPI audit | [209 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | CLB_WM9705D_071 | U9507C V3 | Wireless Device | M2M Module | a0D3A00000OTDlc | Lykan | MDM9628 | Shanghai |  |  | PMD9607 | WTR2655 |  | None | None | None | QCA9377-3 | No BT | 128MB |  |  |  | 5M | Linux Other | MDM9607.LE.1.0-00060-STD.PROD | MDM9607.LE.2.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2017-04-09 | 2017-06-15 | 2017-07-30 | [8 empty] | 2019-05-20 | 2019-05-20 |  | Weizheng Lv |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | *sunsea 9628 project。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-03 09:15:04Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B34 (TDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [209 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | LST_WM9703D_041EQ | U9507EQ | Wireless Device | M2M Module | a0D3A00000OTDlX | Lykan | MDM9607 | Shanghai | MDM9607-0 |  | PMD9607 | WTR2965 |  | None | None | None | QCA9377-3 | No BT | 128MB |  |  |  | 5M | Linux Other | MDM9607.LE.1.0-00060-STD.PROD | MDM9607.LE.2.0 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2017-04-09 | 2017-06-15 | 2017-07-30 | [8 empty] | 2019-05-20 | 2019-05-20 |  | Weizheng Lv |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * Sunsea 9x07 module for CPE mother board, need to support WLAN, LAN, BT * MDM9x07+QCA9377+AR8033 design。。 | Weizheng Lv | 2018-12-17 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-03 09:11:40Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B34 (TDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [209 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV_SDA845_sky blue |  | Wireless Device | VR/AR | a0D3A00000OSRDQ | Napali | SDM845 | Beijing |  |  | PM8005;PM845;PM8998 | Other |  | None | None | None | WCN3990 | WCN3990 BT | TBD/Unknown |  |  |  |  | Android O |  | SDM845.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) | Avatar | Design/Development | NA - Open Market | 2018-06-11 | 2018-08-20 | 2018-10-29 | [8 empty] | 2019-05-20 | 2019-05-20 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | * TC is the ODM for Lenovo SDA845 AR/VR project. * Use Lenovo own AR/VR SDK. * PM Du Guoqiang 13810860379. * No update this week. * EVT is done. | Jiuyao Shu | 2018-11-19 | [85 empty] | jshu@qct.qualcomm.com ; 2018-11-13 06:50:20Z | [11 empty] | WCD9340 |  |  | IoT VR/AR | Transparent OEM Support |  | North America (NA) | WSA8815 x2 (Stereo) | No NFC | None |  |  |  | No | [32 empty] | VR/AR Project: No need CPI audit |  | Column6: PVT | [109 empty] | TA
China | Shenzhen Hipad Telecommunication Technology Co., Ltd. | 3-Gold |  |  | HP58C91 |  | Wireless Device | SmartPhone | a0D3A00000OT9AQ | Shanti | SDM632 | Shanghai |  |  | PM8953;PMI632 | WTR2965 |  | QET4101 | Third Party | Third Party | WCN3615 | WCN3615 | 3GB |  | 5.85 |  | 13M | Android P |  | SDM632.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | [11 empty] | 2019-05-20 | 2019-05-20 |  | Jiaqi Fan |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | *Hipad’s leading SDM632 project, self-brand *For China market | Jiaqi Fan | 2018-11-28 | [40 empty] | Staffed/In progress | [44 empty] | jiaqfan@qct.qualcomm.com ; 2018-11-28 10:28:46Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B17 (FDD); B28 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand |  | SDRAM-LPDDR3 | [28 empty] | Evaluation project: No need CPI audit | [209 empty] | TA
China | TCL | 2-Platinum |  |  | U50A PLUS VZW | U50A PLUS VZW | Wireless Device | SmartPhone | a0D3A00000OejRJ | Feero Lite | MSM8917 | Shenzhen |  |  | PM8937 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3615 | WCN3615 | 3GB |  | 5.5 HD+ 18:9, 720x1440 |  | 8M FF | Android O | r3.0.1_00033.1.181765.0 | MSM8917.LA.3.0.1 | SB3 | TCL first MSM8917 project and big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | NA - Verizon Wireless | 2018-10-09 | 2018-12-06 | 2019-03-21 |  | 2018-11-01 | 2018-11-22 | 2019-03-05 |  |  |  |  | 2019-05-23 | 2019-05-23 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *new project with Android P designed by Huizhou team *SZ SW team is doing pre-LE test. *set up weekly meeting with customer for critical issue and *Started official LE on 7th Dec .ETA is 2019/2/27 | Haijun Wang | 2018-12-11 | [28 empty] | 2 | [56 empty] | haijunw@qct.qualcomm.com ; 2018-12-12 03:44:19Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Integrated | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B6 (FDD); B8 (FDD); B19 (FDD); B38 (TDD); B40 (TDD); B41-XGP (TDD) | No |  | 3 Low: No Need For QTI Support | Customer |  |  | OV12A(12M) +GC2375(2M ) | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column44: DVT | [49 empty] | PVT | [62 empty] | TA
China | Huaqin | 2-Platinum |  |  | A6098-SBM | Lenovo | Wireless Device | SmartPhone | a0D3A00000OSvMV | Jacala | SDM450 | Shanghai |  |  | PMI632;PM8953 | WTR3925 |  | QFE2101 | Third Party | None | WCN3660 | WCN3660 | 3GB | 3200 | 5.5 |  | 13M | Android P | SDM450.LA.3.2.1 | SDM450.LA.3.2.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | Japan - SoftBank Mobile | 2018-12-26 | 2019-01-30 | 2019-03-15 | [8 empty] | 2019-05-24 | 2019-05-24 |  | Hongye Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Schematics Review; Layout Review |  |  | * Lenovo SDM450 tablet project for Softbank; * customer also have Y-cable requirement. need discussion further | Hongye Liu | 2018-11-22 | Staffed/In progress |  |  |  | zge@qct.qualcomm.com ; 2016-05-03 20:03:09Z | [5 empty] | Planning |  |  |  |  | Planning | 2016-06-08 |  |  |  |  | 2017-05-02 |  |  |  | Planning | 2016-06-20 |  | 4 |  | Planning | 2016-06-13 |  |  |  | Planning | 2016-07-04 |  |  |  | Staffed/In progress | 2016-06-20 |  |  |  | Staffed/In progress | 2016-06-27 |  |  |  | Staffed/In progress | 2016-07-01 | [8 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2016-09-30 |  |  |  | hongyel@qct.qualcomm.com ; 2018-11-15 02:48:46Z | [11 empty] | PM8953 |  |  | Mobile |  |  | Japan | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column64: EVT; 2019-01-01 Column99: DVT | [43 empty] | PVT | [69 empty] | TA
China | ZTE | 1-Diamond |  |  | Z971_RCS |  | Wireless Device | SmartPhone | a0D3A00000OTDjW | Feero Lite | MSM8917 | Shanghai |  |  | PM8937;PMI8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 3140 | 5.5" |  | 13M | Android P | Snapdragon_High_Med_2018.SPF.1.0.1 | MSM8917.LA.3.2.1.1 | SB4 |  | Updated design | P817A22 | Evaluation | NA - AT&T Wireless | [5 empty] | 2019-02-15 | [5 empty] | 2019-05-24 | 2019-05-24 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE-NA 8917 RCS pre-research project for ATT&Cricket based on 2018.SPF.1.0.1 | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-12-03 06:09:17Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Integrated | Other | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Evaluation project: No need CPI audit | [213 empty] | TA
China | ZTE | 1-Diamond |  |  | ZM8350 | ZM8350 | Wireless Device | C-V2X | a0D3A00000OSXH7 | McLaren | MDM9150 | Xi'an |  |  | PMD9655 | WTR5975 |  | None | Third Party | None | Other | No BT | 256MB | 3000 | NO Display |  |  | Linux Other | Pre-FC 0.0.022.1 | MDM9150.LE.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-03-18 | 2017-05-06 | 2017-06-06 |  |  | 2017-07-14 | [5 empty] | 2019-05-24 | 2019-05-24 |  | Nicholas Chen | Eugenia Chen | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training; Schematics Review; Layout Review; System Design Review |  |  | * Plan to release INT B01 on 12/21 * EVT phase, SCH/Layout DR done, TO PCB on 11/9, the 1st board is back on 11/29, bring up is done on 12/14. Mother board plan to be back by end of Dec'18 * TADA sign is on going on 11/26 * ZTE 1st MDM9150 based module | Nicholas Chen | 2018-12-17 |  |  |  |  | jic@qct.qualcomm.com ; 2015-11-12 03:17:21Z | [80 empty] | akhosla@qct.qualcomm.com ; 2018-12-06 21:27:57Z | [11 empty] | NA |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD |  | No | [32 empty] | Strongly Requested Filed: LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [213 empty] | TA
China | Sunsea Internet of Things Technology Co., Ltd. | 4-Silver |  |  | LAD_MU8906D_079 | AC018 | Wireless Device | M2M Module | a0D3A00000OTDkt | Cheel | MSM8909 |  |  |  | PM8909 | WTR4905 |  | Third Party | Third Party | Third Party | WCN3610 | WCN3610 (BT) | 512MB |  |  |  |  | Android L |  | MSM8909.LA.1.1.c11 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-06-06 | 2018-07-18 | 2018-08-18 | [8 empty] | 2019-05-27 | 2019-05-27 |  | Weizheng Lv |  | 1 | 1 |  |  |  | *MSM8909 POS module to Landi from Longsung *Guide Sunsea to use MSM8909.LA1.1.c11 for POS. | Weizheng Lv | 2018-12-03 | [85 empty] | wlv@qct.qualcomm.com ; 2018-12-03 08:29:46Z | [11 empty] | PM8909 |  |  | IoT Smart-Cities | Direct OEM Support |  | China |  | No NFC | WCN |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [216 empty] | TA
China | Quectel | 2-Platinum |  |  | EM20-G |  | Wireless Device | Embedded Module | a0D3A00000OSRRi | Chiron | SDX24 | Shanghai |  |  | PMX24 | SDR855 |  | QET5100M | QPA8842;QPM4621;QPM4630;QPM4640 | QAT3514 (x4) | QCA6174A-1 | No BT | 1GB |  |  |  |  | ThinUI (no MM) |  | SDX24.LE.1.0 | SB3 | Quectel’s first SDX24 design for Global Open Market, and potential design win for Lenovo M.2 module for laptop | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2018-11-05 | 2019-02-04 | 2019-04-08 | [8 empty] | 2019-05-27 | 2019-05-27 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Quectel SDX24 CAT20 Module to Global Open Market, M.2 Module project for Laptop and Router. No L+L DLCA requirement so far. * SDX24+ SDR8150+QPM46xx for SDX24 SCH done * Discussing RF topologic for their CV2X project MDM9150 + SDX24. * Quectel requested windows PCIe/ MHI host driver for their M.2 module <<Lenovo, HP M.2 module RFQ ongoing with PdM | Li Wang | 2018-12-17 | [24 empty] | liw@qct.qualcomm.com ; 2018-10-15 01:56:30Z | [60 empty] | liw@qct.qualcomm.com ; 2018-11-13 05:45:59Z | [11 empty] | NA |  |  | Mobile |  |  | Rest of World (ROW) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B6 (FDD); B7 (FDD); B8 (FDD); B9 (FDD); B10 (FDD); B11 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B21 (FDD); B22 (FDD); B23 (FDD); B24 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column13: EVT |  |  |  |  | DVT | [62 empty] | PVT | [48 empty] | TA
China | ZTE | 1-Diamond |  |  | P685M99 |  | Wireless Device | Fixed WAN Router | a0D3A00000ORoNM | Carrera | SDX50M + SM8150 | Xi'an |  |  | PM8005;PM8150;PM8150A;PM8150B;PM8150L;PMK8002;PMX50 | QTM052;SDR8150;SDR8154 |  | QET5100 | QPA8842;QPA2625;QPM4630;QPM4640 | QAT3516 (x2);QAT3550 | Other | No BT | 6GB |  | 6.36 |  | 20M | Android P |  | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB4 | ZTE MBB's 5G CPE research project targeting for China&Japan market | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-10-17 |  |  |  |  | 2018-12-12 | [5 empty] | 2019-05-30 | 2019-05-30 |  | Baoming Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE XA MBB's 5G CPE model, targeting for CMCC and DoCoMo; * EVT board finished BU on Sub 6 with QC RFSW SH CE’s suppor; * Mmwave BU is planned in QC TW lab from Nov 26. | Baoming Zhang | 2018-11-19 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-11-02 10:27:18Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China; Japan |  | No NFC | None |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Evaluation project: No need CPI audit | [219 empty] | TA
China | Xiaomi | 1-Diamond |  |  | MHC0207Q1 |  | IOT | M2M Module | a0D3A00000OKk4B | Lykan | MDM9206 | Beijing |  |  | PMD9607 | WTR2965 |  | None | None | None | No WLAN | Integrated | <128MB | 0 | NO Display |  |  | ThreadX | MDM9206.TX.1.0-00025-STD.PROD-1 | MDM9206.TX.2.0 | SB4 | Xiaomi first MDM9x06 based embedded model | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2017-11-10 | 2017-12-15 | 2018-03-30 | 2018-02-28 |  | 2018-02-01 | [5 empty] | 2018-03-30 | 2019-05-30 |  | Guowei Qin |  | 1 | 1 |  |  |  | *Xiaomi 9206 project from the MiIOT division; *HW/BSP ODMed by Broadmobi, High level SW design from MiIOT; *plan to upgraded to TX 3.0 for the eSIM support; * 500~1000 samples plan to build by end of April; * Working interoperability with MiCloud. | Guowei Qin | 2018-12-16 |  |  |  | Direct OEM support | c_vingut@qct.qualcomm.com ; 2017-02-01 14:34:31Z | [80 empty] | gqin@qct.qualcomm.com ; 2018-11-07 03:02:53Z | [11 empty] | Other |  |  | IoT Smart-Cities | Direct OEM Support |  | China | Other | No NFC | None |  | FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B19 (FDD); B26 (FDD); B39 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [219 empty] | TA
China | Xiaomi | 1-Diamond |  |  | SDX50_5G_Evaluation |  | Wireless Device | SmartPhone | a0D3A00000OeRvs | Carrera | SDX50M + SM8150 | Beijing |  |  | PM8005 | SDR8154 |  | QET5100 | QPM5650;QPM5651 | Third Party | WCN3998 | WCN3998 | >4GB |  |  |  | 48M + 12M | Android P |  | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB3 | XiaoMi 5G SDX50 Sub6 leading project | Parent CP for Original design (OEM) |  | Evaluation |  | 2018-08-18 | [10 empty] | 2019-05-30 | 2019-05-30 |  | Wilson Fu | Michael Liu | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | * XiaoMI 5G evaluation project. * mmW EVB beam char/verification in SD lab are completed; Tput reach to 2.25Gbps. | Wilson Fu | 2018-12-23 | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:33:46Z | [5 empty] | Planning |  |  |  |  | Planning | 2018-08-18 |  |  | taoz@qct.qualcomm.com ; 2018-07-30 19:48:02Z | [5 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [29 empty] | Planning |  |  |  |  | taoz@qct.qualcomm.com ; 2018-07-03 02:16:03Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | Eastern Europe (EE) | Other | SN100U | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm |  |  | [CCB Assignment: Mingchen Gao/Monkey Hou] [CCB Support Type: DRI] [CCB Note: (5/26/2018) Xiaomi next flagship, features under discussion] [CCB Support Level: High] [CCB Score: 34] [CCB Project Info: Project: F1, ID: a0D3A00000OM0ZC] [DRI/POC: Mingchen Gao/Monkey Hou] | Mingchen Gao/Monkey Hou | 34 | High | (5/26/2018) Xiaomi next flagship, features under discussion | DRI | Mingchen Gao/Monkey Hou | [20 empty] | Evaluation project: No need CPI audit | [219 empty] | TA
China | OPPO | 1-Diamond |  |  | DD155 |  | Wireless Device | SmartPhone | a0D3A00000OSvUo | Warlock | SDM710 | Shenzhen |  |  | PM670;PM670A | SDR660 |  | None | Third Party | QAT3518 | WCN3990 | WCN3990 BT | 8GB | 3000 | 6" |  | 16M + 5M | Android P | Snapdragon_High_Mid_2017.SPF.1.0.c2-20060 | SDM710.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2019-01-30 | 2019-03-19 | 2019-05-20 | [8 empty] | 2019-05-30 | 2019-05-30 |  | Magic Wang | Nikhil Shevade | 1 | 1 |  |  |  | * SDM710 project | Magic Wang | 2018-11-14 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [45 empty] | Staffed/In progress | 2018-01-04 | [33 empty] | qiw@qct.qualcomm.com ; 2018-11-16 09:45:31Z | [11 empty] | NA |  |  | Mobile |  | QLN1030 D/P, QLN1020 P | China | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B10 (FDD); B18 (FDD); B19 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2019-01-01 Column99: EVT | [47 empty] | DVT | [61 empty] | PVT | [9 empty] | TA
China | Shenzhen Duubee Intelligent Technologies Co., Ltd. | 4-Silver |  |  | D602L | Gaia Lite | Wireless Device | SmartPhone | a0D3A00000ORxKC | Hathi | SDM439 | Shenzhen |  |  | PM439 | WTR2965 |  | QET4101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 3200 | 5.7" |  | 13MP | Android P |  | SDM439.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | LA - Open Market | 2018-11-09 | 2019-01-30 | 2019-04-01 | [8 empty] | 2019-05-30 | 2019-05-30 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * Duubee first SDM439 project for LA market. | Bruce Wang | 2018-09-12 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-11-14 03:56:10Z | [11 empty] | PM8937 |  |  | Mobile | Direct OEM Support |  | Latin America (LA) | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B28 (FDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column17: EVT; 2019-01-01 Column99: DVT | [60 empty] | PVT | [58 empty] | TA
China | SIM Technology Group (BVI) Limited | 3-Gold |  |  | SIM_8917_L2K |  | Wireless Device | SmartPhone | a0D3A00000OT937 | Feero Lite | MSM8917 | Shanghai |  |  | PM8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660B | WCN3660B | 2GB | 5000 | 8 |  | 8MP | Android N |  | MSM8917.LA.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-05-30 | 2019-05-30 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review; Schedule review; SW architecture review; Qualification: CDG; Qualification: GCF (Attach PIXIT); Qualification: BT (Attach PIXIT); Post mortem lessons learned |  |  | * SIM Shanghai project. * PL: Zuo Hongyan 18121093752. * TA: 2019/5/30. | Jiuyao Shu | 2018-11-27 | [85 empty] | binli@qct.qualcomm.com ; 2018-12-03 01:23:07Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | Undecided | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [219 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV-SRX1130-Model-472 |  | Wireless Device | IOT AIO VR | a0D3A00000OSUig | Kingsman | SXR1130 | Beijing |  |  | PM670 | WSA8810 |  | None | None | None | WCN3980 | WCN3980 BT | 3GB |  |  |  |  | Android O |  | SXR1130.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-05-30 | 2019-05-30 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | * SXR1130 VR design. ODM for Vuzix, it is a google glass like single eye display device. * PL: April Xu 15813889655 * Schematic review is done * No update this week. | Jiuyao Shu | 2018-12-23 | [85 empty] | jshu@qct.qualcomm.com ; 2018-10-18 03:42:37Z | [11 empty] | Other |  |  | IoT VR/AR | Transparent OEM Support |  | China |  | No NFC | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [219 empty] | TA
China | ZTE | 1-Diamond |  |  | NX629J |  | Wireless Device | SmartPhone | a0D3A00000OSKro | Hana | SM8150 | Shenzhen |  |  | PM8150A;PM8150B;PM8150 | SDR8150 |  | QET5100 | Third Party | None | WCN3998 | WCN3998 | 6GB | 4000 | 2340x1080 |  | 16M | Android P |  | SM8150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-07 | 2019-02-14 | 2019-02-14 | 2019-01-11 | [7 empty] | 2019-05-31 | 2019-05-31 |  | Xiangkui Liu |  | 1 | 1 |  |  |  | * (6.65"/FHD, 4GB/6GB + 64GB/128GB, china market target to launch end of May,2019) * Nubia 1st SM8150 project * EVT phase, the 1st EVT SW release to test team in last week. * Current some RF performance and other performance still on debugging. * Taped out 2nd HW version in last week, PCB plan back in end of December. And SMT plan in 1/3. | Xiangkui Liu | 2018-12-23 | [85 empty] | xiangkui@qct.qualcomm.com ; 2018-12-12 02:05:36Z | [11 empty] | WCD9341 |  |  | Mobile | Direct OEM Support | QM77033 QM77011 QM13126(TBD) | China |  | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column15: EVT | [14 empty] | PVT | [105 empty] | TA
China | ZTE | 1-Diamond |  |  | NX629J |  | Wireless Device | SmartPhone | a0D3A00000OSKrt | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150L | SDR8150 |  | QET5100 | Third Party | None | WCN3998 | WCN3998 | 6GB | 4000 | 2340x1080 |  | 16M | Android P |  | SM8150.LA.1.0 | SB4 |  | Unknown |  | Design/Development | China - Open Market | 2018-11-07 | 2019-02-14 | 2019-02-14 | 2019-01-11 | [7 empty] | 2019-05-31 | 2019-05-31 |  | Xiangkui Liu |  | 1 | 1 |  |  |  | * (6.65 "/FHD+,LPDDR4X 4GB/6GB EMMC5.1 64GB/128, china market target to launch end of April,2019) * Nubia 1st SM8150 4G project. * Nubia fininshed the schematic design and Qualcomm team still on going review. * PCB layou plan to finish in end of Oct. | Xiangkui Liu | 2018-10-21 | [85 empty] | xiangkui@qct.qualcomm.com ; 2018-10-08 03:17:45Z | [11 empty] | WCD9341 |  |  | Mobile | Direct OEM Support | QM77033 QM77011 QM13126(TBD) | China |  | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column15: EVT | [14 empty] | PVT | [105 empty] | TA
China | Shenzhen CooTelFone Technology Co., Ltd. | 4-Silver |  |  | Q2141 |  | Wireless Device | IOT Kids watch | a0D3A00000OSlkK | Cheel | MSM8909W | Shenzhen |  |  | PM8916-1 | WTR2965 |  | QET4101 | None | None | WCN3620 | WCN3620 | 512MB |  |  |  |  | Android for Wearables (LAW) |  | MSM8909W.LAW.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-05-31 | 2019-05-31 |  | Andy Li |  | 1 | 1 |  |  |  | * 2nd generation kid watch product for iFlytech, using TaoYun brand; * Target to launch in Q2'19, forecast 100K; * Both SDW2100 and SDW2500 are under evaluation | Andy Li | 2018-11-04 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-11-05 04:48:56Z | [11 empty] | NA |  |  | IoT Wearable | Direct OEM Support |  | China |  | Other | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [220 empty] | TA
China | TCL | 2-Platinum |  |  | Benz_Android_P_Upgrade | Alcatel 3C | Wireless Device | SmartPhone | a0D3A00000OS7xE | Hathi | SDM429 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3615 | WCN3615 | 2GB | 3500 | 5.94" |  | 12MP Bayer + 2MP Bayer | Android P | SDM429 | SDM429.LA.1.0.1 | SB4 |  | MR - Updated OS |  | Design/Development | LA - Telcel | 2018-08-20 | 2018-10-10 | 2018-11-20 |  |  | 2019-03-20 | 2019-04-29 |  |  |  |  | 2019-05-31 | 2019-05-31 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * Benz Android P OTA project. | Bruce Wang | 2018-09-24 | [28 empty] | 2 | [56 empty] | wbruce@qct.qualcomm.com ; 2018-12-04 02:26:20Z | [11 empty] | PM8937 |  |  | Mobile | Direct OEM Support | HRTXAH005-01, CUC1294A-11,CUCT, AP7219M-71 | Latin America (LA) | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B28 (FDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column28: PVT | [120 empty] | TA
China | Lenovo | 1-Diamond |  |  | TAB5 P upgrade |  | Wireless Device | Tablet | a0D3A00000OTFYu | Jacala | SDM450 | Beijing |  |  | PM8953 | WTR3925 |  | Third Party | Third Party | None | WCN3680B | WCN3680B | 3GB |  | 10" |  | 8M | Android P |  | SDM450.LA.3.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | NA - Open Market | 2018-01-28 | 2018-03-03 | 2018-06-01 | [8 empty] | 2019-05-31 | 2019-05-31 |  | Gavin Song |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | *Current Lenovo in house design for P upgrade * Previously ODM by wind | Gavin Song | 2018-12-04 | [85 empty] | huangeng@qct.qualcomm.com ; 2018-12-05 03:02:43Z | [11 empty] | Other |  |  | Compute |  |  | North America (NA) | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [220 empty] | TA
China | BBK | 1-Diamond |  |  | ETD1823 (8150 mmW ) |  | Wireless Device | SmartPhone | a0D3A00000OScpy | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8005 | Other |  | Third Party | QPM5650;QPM5651 | QAT3518;Third Party | WCN3998 | WCN3998 | 6GB | 3500 |  |  | 12M+5M | Android O | SM8150.LA.1.5 + SDX50M.TN.2.0 ES | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB4 | BBK 8150 mmw project; | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-10-10 | 2018-12-31 | 2019-05-30 | [8 empty] | 2019-06-01 | 2019-06-01 |  | Hui Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Local team will support vivo do initial mmW bringup work from next week , then vivo will go to TW lab after Dec 10 to do further online call and BF char test work. | Hui Zhang | 2018-11-18 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z | [20 empty] | Staffed/In progress | 2016-07-11 | [13 empty] | Staffed/In progress | 2016-07-11 |  |  |  | Planning | 2016-08-14 |  |  |  |  | 2017-10-08 | [28 empty] | Planning | 2016-02-20 |  |  |  | zhanghui@qct.qualcomm.com ; 2018-10-26 06:22:39Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B4 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR4X | [28 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column69: DVT | [119 empty] | PVT |  | TA
China | ZTE | 1-Diamond |  |  | Z2332CC | Z2332CC | Wireless Device | SmartPhone | a0D3A00000OSfOp | Cheel | MSM8909 | Shanghai |  |  | PM8909 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 512MB | 1500 | 2.8'' and 1.77" |  | 2M | Android O | MSM8909.LA.3.1.1 | MSM8909.LA.3.1.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2019-02-25 | 2019-04-29 | 2019-05-27 |  |  | 2019-02-01 | [5 empty] | 2019-06-03 | 2019-06-03 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE-NA 8909 Android Go project for Consumer Cellular with 512MB memory based on LA 3.1.1 PL (for RTT support) * Leverage the HW design as Z2321U. * Project status: confirmed, target TA by early of Jun 2019. | Frank Lu | 2018-12-16 | [85 empty] | yonggang@qct.qualcomm.com ; 2018-11-30 02:43:22Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | None |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [125 empty] | EVT | [62 empty] | DVT | [27 empty] | PVT | [6 empty] | TA
China | Shanghai BroadMobi Communication Technology Co., Ltd. | 4-Silver |  |  | M720 |  | Wireless Device | Telematics | a0D3A00000OT78F | Lykan | MDM9628 | Shanghai |  |  | PMD9607 | WTR2965 |  | QFE2101 | None | None | QCA9377 | QCA9377-3 | 512MB |  |  |  |  | ThinUI (no MM) |  | MDM9607.LE.2.0.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-07-01 | 2018-11-08 | 2018-12-30 |  |  | 2016-05-02 | [5 empty] | 2019-06-03 | 2019-06-03 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * 9x07 Module with TX1.0 small memory. | Li Wang | 2018-11-26 | [85 empty] | liw@qct.qualcomm.com ; 2018-12-04 07:05:59Z | [11 empty] | NA |  |  | Automotive |  |  | China | NA | No NFC | WCN |  | FDD | B3 (FDD); B7 (FDD); B20 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column16: DVT; 2018-12-01 Column68: PVT | [123 empty] | TA
China | ZTE | 1-Diamond |  |  | MF993 | 802ZT | Wireless Device | Mobile Router | a0D3A00000ODppF | Chiron | SDX24 | Xi'an |  |  | PMX24 | SDR855 |  | QET4101 | Third Party | None | Other | No BT | 512MB | 3000 | 2.4 |  | NA | Linux Other | SDX24.LE.1.0 | SDX24.LE.1.0 | SB3 | ZTE first SDX24 based uFi for Japan Softbank, Forecast is big. | Parent CP for Original design (OEM) |  | Design/Development | Japan - SoftBank Mobile | 2018-09-18 | 2018-11-12 | 2018-12-15 | 2018-11-20 |  | 2018-11-26 |  | 2019-01-07 |  | 2019-04-15 |  | 2019-06-14 | 2019-06-14 |  | Nicholas Chen | Lianfeng Li | 1 | 1 |  |  |  | * Plan to release INT B09 on 12/21 based on post CS1 * TELEC test started on 12/14 * TCP Peak Tput can reach 650Mbps, BCM has daily meeting with ZTE now * ZTE TO new PCB on 10/24, back on 11/22 * 2nd board with V2 chipset TO on 9/3, back on 9/17 * 1st board with V1 chipset, without WiFi, bring up finished on 8/15 * ZTE kicked off X24 based uFi for Softbank with 3rd party WiFI BCM4375, 11ax dual band | Nicholas Chen | 2018-12-17 | [85 empty] | jic@qct.qualcomm.com ; 2018-11-28 03:17:58Z | [11 empty] | NA |  |  | Mobile |  |  | Japan | NA | No NFC | None |  | TDD/FDD | B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B13 (FDD); B14 (FDD); B20 (FDD); B28 (FDD) | No |  |  |  | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-11-01 Column20: DVT; 2018-12-01 Column53: PVT | [134 empty] | TA
China | Huizhou Desay SV Automotive Co, Ltd. | 4-Silver |  |  | G6 Platform | NA | Automotive | Auto Infotainment | a0D3A00000NEahL | IstariAU | APQ8096AU | Beijing |  |  | PMM8996AU | Other | Unknown | Third Party | Third Party | None | QCA6574A-1 | QCA6574A-1 | 4GB |  | 12.3 |  | No | Android O |  | MSM8996AU.LA.1.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-06-14 | 2019-06-14 |  | Dan Li |  | 1 | 0 |  |  |  | * No plan by COB but by QCA6574 modules e.g. Murata * CSRB30124 is chip on board * A2 sample was delivered to Chehejia with DSI display only. Need to fix HDMI issue ASAP. * Explained to Desay and Chehejia about the limitation of Bluetooth connection to their requested scenarios (:1 x QCA65x4 only can support 1 x eSCO stream by one OS; Can support 2 x HFP connection, but cannot support eSCO stream concurrency). Got their confirmation. | Harvey Huang | 2018-03-12 | [85 empty] | ldan@qct.qualcomm.com ; 2018-03-28 07:00:57Z | [11 empty] | Other |  |  | Automotive |  | NA |  | Other | Other | Third party (non-SiLab) |  |  |  | No |  |  |  | LPDDR4 | [28 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty | [234 empty] | TA
China | BBK | 1-Diamond |  |  | TD1806 | TBD | Wireless Device | SmartPhone | a0D3A00000OSycN | Moorea | SM7150 | Shenzhen |  |  | PM7150 | Other |  | Third Party | Third Party | Third Party | WCN3980 | WCN3680 | 6GB |  | 6.28’ |  | 12M+ 5M | Android P | SDM710.LA.2.0-00050-STD.PROD-2 | SM7150.LA.1.0 | SB4 | *SM7150 evaluation project. target for China market. | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | [11 empty] | 2019-06-14 | 2019-06-14 |  | Jiaqi Fan | Karthik Koneru | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | *SM7150 evaluation project. target for China market. *Vivo highlight UFS boot GPIO 108 pull up issue, internal check. | Jiaqi Fan | 2018-12-16 | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2016-12-04 20:23:01Z | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | 2017-03-20 |  |  |  | Planning |  |  |  |  | Planning | [19 empty] | Staffed/In progress |  |  |  |  | Planning |  |  |  |  | jiaqfan@qct.qualcomm.com ; 2018-11-19 10:18:36Z | [11 empty] | WCD9370 |  |  | Mobile |  | QLN 4640 PRx | China | Other | No NFC | None |  | TDD | B1 (FDD); B3 (FDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Evaluation project: No need CPI audit | [234 empty] | TA
China | Huawei | 1-Diamond |  |  | Cassini | Huawei Watch 3 | Wireless Device | Wearable | a0D3A00000OZkYl | Cheel | MSM8909W | Xi'an |  |  | PMW3100 | WTR2965 |  | QET4101 | Third Party | None | WCN3620 | WCN3620 | 512MB | 420 | 1.39" |  | 5M | Android P | MSM8909W.LW.4.0.2 | MSM8909W.LW.4.0.2 | SB3 | * Huawei SDW3100 leading project, big volume forecast. | Parent CP for Original design (OEM) | Columbus | Design/Development | China - Open Market | 2019-03-22 | 2019-04-18 | 2019-05-10 |  |  | 2019-05-10 | [5 empty] | 2019-06-15 | 2019-06-15 |  | Yizhen Yang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review; Schedule review; SW architecture review |  |  | *Huawei next generation Watch 3. SDW3100 without BG. JDM with GoerTech. *Huawei are integrating QCOM LW 4.0.2 FC build SW. 1st PCB will return this weekend. | Yizhen Yang | 2018-12-20 |  |  |  |  | junjiel@qct.qualcomm.com ; 2016-04-22 02:14:10Z | [80 empty] | yizheny@qct.qualcomm.com ; 2018-12-21 06:11:21Z | [11 empty] | Other |  |  | IoT Wearable | Direct OEM Support |  | China | NA | No NFC | None |  | TDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [150 empty] | EVT | [26 empty] | DVT | [21 empty] | PVT | [35 empty] | TA
China | ZTE | 1-Diamond |  |  | Z6220C | Z6220C | Wireless Device | SmartPhone | a0D3A00000OSsFN | Hathi | SDM439 | Xi'an |  |  | PMI632;PM439 | WTR2965 |  | Third Party | Third Party | None | WCN3680B | WCN3680B | 2GB | 3100 | 6.26" |  | 16 | Android P | SDM439.LA.1.0.1 | SDM439.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Leap Wireless (Cricket) | 2019-01-01 | 2019-01-30 | 2019-03-20 |  |  | 2019-04-15 |  | 2019-05-13 |  |  |  | 2019-06-17 | 2019-06-17 |  | Nicholas Chen | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * EVT phase, SCH is done, final layout review is submitted. * ZTE-NA SDM439 leading project for Cricket based on 2018.SPF.1.0.1, LTE B66 is support | Nicholas Chen | 2018-12-17 |  |  |  |  | jic@qct.qualcomm.com ; 2017-02-12 23:07:46Z | [80 empty] | binli@qct.qualcomm.com ; 2018-12-17 07:36:19Z | [11 empty] | Other |  |  | Mobile | Direct OEM Support |  | China | Other | No NFC | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B14 (FDD); B29 (FDD); B30 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm |  |  | [CCB Assignment:Neo Zha] [CCB Support Type:DRI] [CCB Note:] [CCB Support Level:Low] [CCB Score:20] [DRI/PoC:Neo Zha] | Neo Zha | 20 | Low |  | DRI | Neo Zha | [20 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2019-01-01 Column70: EVT; 2019-01-01 Column99: DVT | [48 empty] | PVT | [88 empty] | TA
China | Huaqin | 2-Platinum |  |  | SA191 |  | Wireless Device | Tablet | a0D3A00000OT5vh | Napali | SDA845 | Shanghai |  |  | PM8005;PM845 | None |  | None | None | None | WCN3990 | WCN3990 BT | 4GB | 1300 | na |  | 20M | Android O | TBD | SDM845.LA.2.0 | SB3 | SDA845 ADAS project. | ODM or partner CP associated with an indirect account |  | Design/Development | NA - Open Market | 2018-10-18 | 2018-12-01 | 2019-02-28 | 2018-12-17 |  | 2018-12-17 | [5 empty] | 2019-06-17 | 2019-06-17 |  | Qiang Liu |  | 1 | 1 |  |  |  | * arranged con-call to clarify the feature scope with customer, Huaqin is evaluating the SW development effort *ADAS product. We're assisting customer on HW design review *SDA845 + MDM9x07 (USB modem), Target TA data is Jun.17.2019. | Qiang Liu | 2018-12-16 | [85 empty] | binli@qct.qualcomm.com ; 2018-11-23 01:44:08Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | North America (NA) | WSA8810 | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2018-12-01 Column39: DVT | [28 empty] | PVT | [108 empty] | TA
China | Chinachip Technology Limited | 4-Silver |  |  | QC450 |  | Wireless Device | SmartPhone | a0D3A00000OTFda | Jacala | SDM450 | Shenzhen |  |  | PM8953 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3660B | WCN3660B | 3GB |  | 7 |  |  | Android P |  | SDM450.LA.3.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Telecom (CTC) | [11 empty] | 2018-06-20 | 2019-06-20 |  | Jiaqi Fan |  | 1 | 1 | [91 empty] | jiaqfan@qct.qualcomm.com ; 2018-12-05 07:18:27Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China |  | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B20 (FDD); B26 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [240 empty] | TA
China | Wingtech | 2-Platinum |  |  | P81080AA1 | pad | Wireless Device | SmartPhone | a0D3A00000OTBtj | Hathi | SDM429 | Shenzhen |  |  | PM439;PMI632 | None |  | None | None | None | WCN3660B | WCN3660B | 2GB | 3300 | 8 |  | 8M | Android P | Snapdragon_High_Med_2016.SPF.1.0-05000-STD.PROD-1 | SDM429.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-10-19 | 2018-12-19 | 2019-01-31 | [8 empty] | 2019-06-21 | 2019-06-21 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Evaluation for PAD | Tian Zhou | 2018-11-29 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-11-30 02:03:56Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column57: DVT | PVT | [140 empty] | TA
China | Wingtech | 2-Platinum |  |  | P81081AA1 | pad | Wireless Device | SmartPhone | a0D3A00000OTBtt | Hathi | SDM429 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | None | None | None | WCN3660B | WCN3660B | 2GB | 3300 | 8 |  | 8M | Android P | Snapdragon_High_Med_2016.SPF.1.0-05000-STD.PROD-1 | SDM429.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-10-19 | 2018-12-19 | 2019-01-31 | [8 empty] | 2019-06-21 | 2019-06-21 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Evaluation for PAD | Tian Zhou | 2018-11-29 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-11-30 02:09:50Z | [11 empty] | PM8937 |  |  | Mobile |  |  | China | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column57: DVT | PVT | [140 empty] | TA
China | Wingtech | 2-Platinum |  |  | Clamshell | For Lenovo | Wireless Device | SmartPhone | a0D3A00000OT5ws | Napali | SDM850 | Shanghai |  |  | PM845;PM8998 | SDR845 |  | None | None | None | WCN3990 | WCN3990 BT | 4GB | 3000 | 5.5 |  | 13M | Win10 Redstone |  | SDM850.WP.1.2 | SB4 |  | ODM or partner CP associated with an indirect account | Planck(SDM850) | Evaluation | China - Open Market | 2018-12-21 | 2019-01-18 | 2019-03-22 | [8 empty] | 2019-06-21 | 2019-06-21 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Evaluation | Tian Zhou | 2018-11-22 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [15 empty] | Staffed/In progress | [64 empty] | tzhou@qct.qualcomm.com ; 2018-11-23 02:23:11Z | [11 empty] | WCD9341 |  |  | Compute |  |  | China | WSA8815 x2 (Stereo) | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column59: EVT; 2019-01-01 Column87: DVT | [50 empty] | PVT | [90 empty] | TA
China | Wingtech | 2-Platinum |  |  | T89629 | Nokia N3 - Deadpool | Wireless Device | SmartPhone | a0D3A00000ORub0 | Hathi | SDM429 | Shanghai |  |  | PM439;PMI632 | WTR2965 |  | None | None | None | WCN3615 | WCN3615 | 2GB | 3000 | 6.26 |  | 8M | Android P |  | SDM429.LA.1.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | NA - Verizon Wireless | 2018-10-10 | 2018-12-10 | 2019-01-11 | [8 empty] | 2019-06-21 | 2019-06-21 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Evaluation for Verizon, already had a con call for some preperation. | Tian Zhou | 2018-10-30 | Completed | 2015-12-11 |  |  | tzhou@qct.qualcomm.com ; 2016-01-31 19:53:12Z | Completed | 2015-12-28 | [8 empty] | Planning | 2016-01-18 | [8 empty] | Planning | 2016-02-18 |  | 4 |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 |  |  |  | Planning | 2016-03-08 | [33 empty] | tzhou@qct.qualcomm.com ; 2018-11-07 06:48:14Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  |  | B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR3 |  | [CCB Assignment:Zhiqiang Jin, Gary Ge(Lab)] [CCB Support Type:DRI, Service Lab] [CCB Note:(8/22) Gary Ge(Lab): 8/24-8/31, ISP(1) ODM： Xiaomi C3B] [CCB Support Level:Mid] [CCB Score:26] [DRI/PoC:Zhiqiang Jin] | Zhiqiang Jin | 26 | Mid | (8/22) Gary Ge(Lab): 8/24-8/31, ISP(1) ODM： Xiaomi C3B | DRI, Service Lab | Zhiqiang Jin, Gary Ge(Lab) | [20 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column48: DVT; 2019-01-01 Column80: PVT | [141 empty] | TA
China | Quectel | 2-Platinum |  |  | AG15 |  | Automotive | C-V2X | a0D3A00000ORXJs | McLaren | MDM9150 | Shanghai |  |  | PMD9655 | WTR5975 |  | Third Party | Third Party | None | Other | No BT | 256MB |  |  |  |  | Linux Other |  | MDM9150.LE.1.0 | SB3 | Leading MDM9150 project | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-09-17 | 2018-12-24 | 2019-04-29 |  |  | 2019-04-15 | [5 empty] | 2019-06-24 | 2019-06-24 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Quectel MDM9150 C-V2X leading project. * MDM9150.LE.1.0 AMSS Standard OEM released to Quectel. * EVT SMT on 9/24 and BU start from 9/27. * Workshop on 9/10. | Li Wang | 2018-09-11 | [85 empty] | akhosla@qct.qualcomm.com ; 2018-12-06 21:30:01Z | [11 empty] | NA |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD | B42 (TDD); B43 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column62: DVT | [88 empty] | PVT | [55 empty] | TA
China | ZTE | 1-Diamond |  |  | Z5152C | Z5152C | Wireless Device | SmartPhone | a0D3A00000OT66o | Feero Lite | MSM8917 | Xi'an |  |  | PM8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3680B | WCN3680B | 2GB | 2600 | 5.45" |  | 8M | Android P | Snapdragon_High_Med_2018.SPF.1.0.1 | MSM8917.LA.3.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - Leap Wireless (Cricket) | [5 empty] | 2019-03-15 | [5 empty] | 2019-06-24 | 2019-06-24 |  | Frank Lu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * ZTE-NA 8917 Android P project for Cricket & ATT based on 2018 SPF 1.0.1 PL. * SCH design review finished. * Target TA by end of Jun 2019. | Frank Lu | 2018-12-16 | [85 empty] | binli@qct.qualcomm.com ; 2018-12-03 01:23:51Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Other | Other | WCN |  | TDD/FDD | B2 (FDD); B4 (FDD); B5 (FDD); B12 (FDD); B14 (FDD); B30 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [244 empty] | TA
China | TCL | 2-Platinum |  |  | Niobe-VDF | Alcatel 3C | Wireless Device | SmartPhone | a0D3A00000OSgTL | Hathi | SDM429 | Shenzhen |  |  | PM439;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3615 | WCN3615 | 3GB | 3500 | 5.94" |  | 13MP Bayer + 5MP Bayer | Android P | SDM429 | SDM429.LA.1.0 | SB4 | * TCL first SDM429 project and big volume forecast. | Parent CP for Original design (OEM) |  | Design/Development | WE - Vodafone (U.K.) | 2019-08-07 | 2019-02-20 | 2019-05-03 |  | 2018-12-20 | [6 empty] | 2019-06-27 | 2019-06-27 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * TCL will kick off new project for EE | Haijun Wang | 2018-12-03 | [28 empty] | 2 | [56 empty] | haijunw@qct.qualcomm.com ; 2018-10-31 08:26:03Z | [11 empty] | PM8937 |  |  | Mobile | Direct OEM Support | HRTXAH005-01, CUC1294A-11,CUCT, AP7219M-71 | Eastern Europe (EE) | Integrated | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 |  | -- Bring-up/PLD gating: 09/15/2018 - 09/25/2018 -- Golden module ready: 09/25/2018 -- IQ Basic tuning: 09/26/2018 -10/25/2018 -- IQ Fine tuning: 11/25/2018 - 12/25/2018 -- Actuator Basic tuning: 10/25/2018 -11/25/2018 -- CAF tuning: 10/25/2018 -11/25/2018 -- PDAF/TOF fine tuning: 10/25/2018 -11/25/2018 | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty | [120 empty] | DVT | [71 empty] | PVT | [54 empty] | TA | [40 empty] | EVT
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV_APQ8053_Smartbot |  | Wireless Device | Robotics | a0D3A00000OE0XK | Jacala | APQ8053 | Beijing |  |  | PM8953;PMI8952 | Other |  | None | None | None | WCN3680B | WCN3680B | 2GB |  | None |  | None | Linux Other |  | APQ8053.LE.1.3 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-05-10 | 2018-07-17 | 2018-09-14 | [8 empty] | 2019-06-28 | 2019-06-28 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | *It is for iRobot smart robot . * PM: wang Wei 13910219876 * It is in DVT stage. * TA delayed due to customer budget issue in 2018 . | Jiuyao Shu | 2018-12-01 |  |  |  |  | junjiel@qct.qualcomm.com ; 2016-04-22 02:04:21Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-10-29 06:22:16Z | [11 empty] | NA |  |  | IoT Robotics | Transparent OEM Support |  | China | NA | No NFC | None |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [248 empty] | TA
China | Shanghai Tricheer Technology Co., Ltd. | 3-Gold |  |  | LCT_LV7700_ZAK | OBU | Automotive | Telematics | a0D3A00000OCfGQ | Lykan | MDM9628 | Xi'an |  |  | PMD9607 | WTR2965 |  | QFE2101 | None | None | QCA6564A-3 | QCA6564A-3 | 2GB |  |  |  |  | Linux Other | Pre-CS 0.0.030.1 | MDM9607.LE.2.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | SEA - Open Market | 2017-07-01 | 2017-10-20 | 2018-01-01 | [8 empty] | 2019-06-28 | 2019-06-28 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Per understanding of MHI/ ERP2 spec, SD team recommend MHI OBU project to change to MSM9207+QCA9377 because all the usual reasons for using 9628 (Factory Fit car OEM business, need precision GNSS, and DSRC) are not valid in this case. It can be treated as pure aftermarket product with 9x07 + 9377. MKT has formal informed Tricheer for this update. * Tricheer will deliver A sample of Type A to三菱 by end of Sep., and Type B by mid of Nov., 2017. Mitsubishi will start the verification then. | Harvey Huang | 2018-03-12 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-12-12 04:10:04Z | [11 empty] | NA |  |  | Automotive |  | WTR2965 | South East Asia (SEA) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD) | No |  |  |  | SDRAM-LPDDR2 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [248 empty] | TA
China | TCL | 2-Platinum |  |  | PM90 | PM90 | Wireless Device | SmartPhone | a0D3A00000OSROF | Starlord | SDM660 | Shanghai |  |  | PM660L;PM660 | SDR660 |  | QET4101 | Third Party | Third Party | WCN3990 | WCN3990 BT | 4GB |  | 5.0" |  | 112M AF(2L9)+13M AF(3M3 | Android O | SDM660.LA.2.1-21111-STD.PROD-1 | SDM660.LA.3.0 | SB4 | DM_0828>Use PM80+ housing except rear cover, sub bracket, IO connector mold. | Parent CP for Original design (OEM) |  | Design/Development | Korea - Open Market | 2018-12-01 | 2019-02-01 | [9 empty] | 2019-06-28 | 2019-06-28 |  | Haijun Wang |  | 1 | 1 |  |  |  | *New project for China &NA Open market *Doing HW design | Haijun Wang | 2018-12-03 | [85 empty] | haijunw@qct.qualcomm.com ; 2018-10-15 03:11:48Z | [11 empty] | PM660 |  |  | Mobile |  |  | Japan; Korea; North America (NA); Western Europe (WE) | WSA8815 | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B28 (FDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR4 |  | 前摄：ASA8001074C1 内置摄像头,Camera,Mobile Only,CMOS,8M,FF,6.7×6.7×H4.05 mm,FPC+30Pin 5806BTB,MIPI,S5K4H8,XA-0809C-H5531,N/A,N/A,For Pop5 2nd source,PC0KA0012A,SUNRISE 后摄：ASA1300044C1 内置摄像头,Camera,Mobile Only,CMOS,13M,AF,8.5×8.5×H4.0 mm,FPC+30PIN 5806BTB,MIPI,OV13855,Sunny 3923D,BKZM-BL68-E,DW9800W,For T2MINI,F13855AJ,QTECH | [26 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column39: EVT |  | DVT | [146 empty] | TA
China | Shanghai Tricheer Technology Co., Ltd. | 3-Gold |  |  | LC3110 |  | Automotive | Auto Infotainment | a0D3A00000OSx92 | Feero Lite | MSM8917 | Xi'an |  |  | PM8937 | WTR2965 |  | Third Party | Third Party | Third Party | WCN3615 | WCN3615 | 2GB |  | 7 |  | 8M | Android N |  | MSM8917.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-08-20 | 2018-09-25 | 2018-12-10 | [8 empty] | 2019-06-29 | 2019-06-29 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted | [90 empty] | wenjuanl@qct.qualcomm.com ; 2018-11-16 09:30:15Z | [11 empty] | PM8937 |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | [29 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column48: PVT | [149 empty] | TA
China | OnTim | 3-Gold |  |  | Q2151UNTR |  | Wireless Device | SmartPhone | a0D3A00000OTACb | Pukeena | QM215 | Beijing |  |  | PM215 | WTR2965 |  | QET4101 | None | None | WCN3615 | WCN3615 | 2GB | 3400 | 5.65 | FHD (1920x1080) | 13MP | Android P |  | QM215.LA.3.2.1.1 | SB4 | * 5" 854*480 for India market. | Parent CP for Original design (OEM) |  | Design/Development | India - Open Market | [11 empty] | 2019-06-30 | 2019-06-30 |  | Xiaoping Shi | Karnakoti Narayana | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting |  |  | * 5" 854 x 480 for India market. | Xiaoping Shi | 2018-12-16 | [85 empty] | xiaoshi@qct.qualcomm.com ; 2018-11-29 02:54:47Z | [11 empty] | PM8952 |  |  | Mobile |  |  | India | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [250 empty] | TA
China | MeiG Smart Technology Co., Ltd. | 3-Gold |  |  | USB800 | USB800 | Wireless Device | USB Modem | a0D3A00000OZlSZ | Stingray | SDX20 | Shanghai |  |  | PMX20 | SDR845 |  | Third Party | Third Party | Third Party | No WLAN | No BT | 512MB |  |  |  | 5M | Linux Other | SDX20.LE.1.1 | SDX20.LE.1.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | NA - AT&T Wireless | 2019-01-30 | 2019-04-15 | 2019-05-06 | 2019-04-26 |  | 2019-03-10 |  | 2019-04-26 |  | 2019-05-20 |  | 2019-06-30 | 2019-06-30 |  | Nicholas Chen |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * MeiG is responsible for HW, Inseego will do the SW. * MeiG kicked off this USB dongle for Inseego, and ATT will be the carrier. | Nicholas Chen | 2018-12-18 | [85 empty] | jic@qct.qualcomm.com ; 2018-12-18 08:57:36Z | [11 empty] | NA |  |  | Mobile |  |  | North America (NA) | NA | No NFC | None |  | FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B17 (FDD); B18 (FDD); B20 (FDD); B28 (FDD); B29 (FDD); B30 (FDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty |  | 2019-01-01 Column99: EVT | [74 empty] | DVT | [20 empty] | PVT | [54 empty] | TA
China | Meizu | 2-Platinum |  |  | M1991 | Meizu 16s Plus | Wireless Device | SmartPhone | a0D3A00000OTJs0 | Hana | SM8150 | Shenzhen |  |  | PM8150;PM8150A;PM8150B | SDR8150 |  | QET5100 | Third Party | QAT3514;QAT3550 | WCN3998 | WCN3998 | 6GB | 3100 | 6.01" |  | 12M + 20M（3倍光学变焦） | Android P | TBD | SM8150.LA.1.0 | SB4 | Meizu in-house team SM8150 the high end project，MEIZU brand Y2019 flagship phone | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2019-02-13 | 2019-04-10 | 2019-05-28 | 2019-04-19 | [7 empty] | 2019-07-03 | 2019-07-03 |  | Jiechu Gui | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * 6.492" FHD+ display. Triple cameras as rear camera, Wireless charger. Target to Launch to market in Aug. o ID/MD design ongoing o EVT SMT in Feb,13 | Jiechu Gui | 2018-12-16 | [85 empty] | jgui@qct.qualcomm.com ; 2018-12-10 02:04:37Z | [11 empty] | Other |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B20 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty | [113 empty] | EVT | [55 empty] | DVT | [47 empty] | PVT | [35 empty] | TA
China | Xiaomi | 1-Diamond |  |  | F5 | Mix series | Wireless Device | SmartPhone | a0D3A00000ORsli | Hana | SM8150 | Beijing |  |  | PM8150A;PM8150;PM8150B | SDR8150 |  | QET5100 | Third Party | Third Party | WCN3998 | WCN3998 | >4GB |  |  |  | 48M + 20M + 20M | Android P |  | SM8150.LA.1.0 | SB4 | XiaoMi 855 mix series | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-11-30 | 2019-01-04 | 2019-06-21 | [8 empty] | 2019-07-05 | 2019-07-05 |  | Wilson Fu | Michael Liu | 1 | 1 | Access to documentation granted; Access to Case granted; Training; Concept review; Kickoff meeting; Schematics Review; Layout Review; Requirement Review; System Design Review |  |  | * XiaoMI Mix series project on top of SM8150. * P0:1/10, P1: 2/6. P2: 4/8; P3: 5/20 MP @ July. | Wilson Fu | 2018-12-23 | Planning |  |  |  | xinliu@qct.qualcomm.com ; 2017-06-19 15:33:46Z | [5 empty] | Planning |  |  |  |  | Planning | [9 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [29 empty] | Planning |  |  |  |  | wilsonf@qct.qualcomm.com ; 2018-09-07 01:58:03Z | [11 empty] | WCD9340 |  |  | Mobile | Direct OEM Support |  | China | Other | SN100U | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm |  |  | [CCB Assignment: Mingchen Gao/Monkey Hou] [CCB Support Type: DRI] [CCB Note: (5/26/2018) Xiaomi next flagship, features under discussion] [CCB Support Level: High] [CCB Score: 34] [CCB Project Info: Project: F1, ID: a0D3A00000OM0ZC] [DRI/POC: Mingchen Gao/Monkey Hou] | Mingchen Gao/Monkey Hou | 34 | High | (5/26/2018) Xiaomi next flagship, features under discussion | DRI | Mingchen Gao/Monkey Hou | [20 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column38: EVT; 2019-01-01 Column73: DVT | [141 empty] | PVT | [13 empty] | TA
China | Wingtech | 2-Platinum |  |  | SDM1000-WOS | For Lenovo | Wireless Device | SmartPhone | a0D3A00000ORaFj | Poipu | SDM1000 | Shanghai |  |  | PMC1000 | SDR855 |  | QET5100 (x2) | QPM4621;QPM4630;QPM4640 | None | WCN3990 | WCN3990 BT | 4GB | 3000 | 5.5 |  | 13M | Win10 Redstone |  | MSM8998.WP.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2019-02-01 | 2019-03-01 | 2019-04-01 | [8 empty] | 2019-07-05 | 2019-07-05 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Evaluation, has opportunity to win the Lenovo ODM project. * some information is not locked yet. | Tian Zhou | 2018-12-09 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [15 empty] | Staffed/In progress | [64 empty] | tzhou@qct.qualcomm.com ; 2018-08-16 07:44:54Z | [11 empty] | WCD9341 |  |  | Compute |  |  | China | WSA8815 x2 (Stereo) | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Evaluation project: No need CPI audit | [101 empty] | EVT | [27 empty] | DVT | [30 empty] | PVT | [94 empty] | TA
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | KC_CB64_SDM429 |  | Wireless Device | SmartPhone | a0D3A00000OS40O | Hathi | SDM429 | Beijing |  |  | PM439;PMI632 | WTR2965 |  | QET4101 | Third Party | None | WCN3680B | WCN3980 BT | 3GB | 0 | 5" |  |  | Android P | SDM429.LA.1.0.1 | SDM429.LA.1.0.1 | SB4 | Kyocera ODM | ODM or partner CP associated with an indirect account |  | Design/Development | Japan - Open Market | 2018-10-11 | 2019-01-10 | 2019-04-10 | [8 empty] | 2019-07-10 | 2019-07-10 |  | Tianhao Fei |  | 1 | 1 |  |  |  | yocera ODM project, SDM429 in evaluation. | Tianhao Fei | 2018-09-19 | [40 empty] | Staffed/In progress | 2016-07-29 |  |  |  | Staffed/In progress | 2016-07-29 |  |  |  | Staffed/In progress | 2016-07-21 | [33 empty] | tfei@qct.qualcomm.com ; 2018-10-08 03:19:17Z | [11 empty] | PM8937 |  |  | Mobile |  |  | Japan | Integrated | Other | WCN |  | TDD/FDD | B3 (FDD); B5 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty |  | 2019-01-01 Column79: DVT | [69 empty] | PVT | [90 empty] | TA
China | Longcheer | 2-Platinum |  |  | M260 | LGE MH5 | Wireless Device | SmartPhone | a0D3A00000OSybj | Feero Lite | MSM8917 | Shanghai |  |  | PMI8937;PM8937 | WTR2965 |  | QFE2101 | Third Party | None | WCN3660B | WCN3660B | 2GB | 4000 | 8'' |  | 8M | Android P |  | MSM8917.LA.3.2.1 | SB4 | ODM for MOTO as Surf NA- Non CA | Parent CP for Original design (OEM) |  | Design/Development | NA - Open Market | 2018-12-10 | 2019-03-04 | 2019-06-06 | [8 empty] | 2019-07-29 | 2019-07-29 |  | Li Wang | qipl.ce.PEs qipl.ce.PEs | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; System Design Review |  |  | * 8917 Smartphone for LGE in NA operator Market * Longcheer's first ODM project for LGE * Will have multiple SKUs for different market with different configurations. * Request L+L on JO modem. | Li Wang | 2018-12-17 | [28 empty] | 2 | [56 empty] | liw@qct.qualcomm.com ; 2018-11-19 08:57:09Z | [11 empty] | PM8937 |  |  | Mobile |  |  | North America (NA) | Other | No NFC | WCN |  | FDD | B1 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B12 (FDD); B13 (FDD); B14 (FDD); B17 (FDD); B20 (FDD); B26 (FDD); B30 (FDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column48: EVT | [32 empty] | DVT | [93 empty] | PVT | [52 empty] | TA
China | Beijing Rockrobo Technology Co., Ltd. | 4-Silver |  |  | Tanos-V |  | IOT | IOT Smart Vacuum Cleaner | a0D3A00000OSO1b | Jacala | APQ8053 | Beijing |  |  | PM8953 | None |  | None | None | None | WCN3680B | WCN3660B | >4GB |  | 5.5 |  | 12M | Linux Other | Meta build APQ8053.LE.1.3-13036-STD.PROD-2 | APQ8053.LE.1.3 | SB4 | Xiaomi IoT echo company project; | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-09-17 | 2018-11-19 | 2019-03-04 | [8 empty] | 2019-07-30 | 2019-07-30 |  | Guowei Qin |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to tools granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | *RR brand APQ8053 vacuum cleaner project; *DualCamera bringup done, based on the TS evaluation board; *Audio wakeup required,3rd party solution in consideration; *Dual camera support on APQ8053 LE1.3 required, RR request camera tuning on-site training, SH camera tuning lab support the requirement in wk 11/26; *! Tanos-v facing WiFi EVM jumping issue, suggestion provide by RF HW; | Guowei Qin | 2018-12-16 | [25 empty] | Planning | [24 empty] | Staffed/In progress | 2017-11-27 | [33 empty] | gqin@qct.qualcomm.com ; 2018-10-11 02:39:29Z | [11 empty] | PM8953 |  |  | IoT Robotics | Direct OEM Support |  | China | Other | No NFC | WCN |  |  |  | No |  | 1 High: Full QTI Support Required | Qualcomm |  |  | 1.2PD 2. Real-time Bokeh 3. Manual 3A 4. slow motion(480fps/240 fps/120fps) | [26 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-11-01 Column27: DVT | [32 empty] | PVT | [147 empty] | TA
China | Longcheer | 2-Platinum |  |  | B821 |  | Wireless Device | IOT Smart watch | a0D3A00000ORvV6 | Cheel | MSM8909W | Shanghai |  |  | PMW3100 | WTR2965 |  | QFE2101 | None | None | WCN3620 | WCN3620 | 1GB |  |  |  |  | Android Wear (LW) |  | MSM8909W.LW.3.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | [12 empty] | 2019-07-30 | 2019-07-30 |  | Andy Li |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training |  |  | * Smart Watch project, for Montblanc | Andy Li | 2018-11-15 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-09-11 08:09:16Z | [11 empty] | NA |  |  | IoT Wearable | Direct OEM Support |  | China; North America (NA); Rest of World (ROW); Western Europe (WE) |  | Other | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B38 (TDD); B40 (TDD) | No | [32 empty] | Mandatory Filed: Operator1 : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [280 empty] | TA
China | ThunderSoft | 2-Platinum |  |  | TS_8909W_pluto |  | Wireless Device | Wearable | a0D3A00000ORkRV | Cheel | APQ8009W | Beijing |  |  | PMW3100 | WTR2965 |  | Third Party | None | None | WCN3610 | WCN3610 (BT) | 512MB | 500 | 1.22" |  | NO | Android N |  | MSM8909W.LAW.3.0.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-08-29 | 2018-09-30 | 2018-12-10 | [8 empty] | 2019-07-31 | 2019-07-31 |  | Jiuyao Shu |  | 1 | 1 |  |  |  | * Thundersoft SDW2500watch internal project. * PL: ChenXiangJin 18600261908 * EVT1 is ready. * EV2 will back in the week of 11/26. | Jiuyao Shu | 2018-11-20 |  |  |  |  | c_vingut@qct.qualcomm.com ; 2017-02-01 15:45:37Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-11-21 02:56:15Z | [11 empty] | PM8916 |  |  | IoT Wearable | Direct OEM Support | CXA4429GC: Ant. Swtich | China | NA | Other | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column48: PVT | [181 empty] | TA
China | Continental Automotive Systems | 3-Gold |  |  | Conti CNS3.0 |  | Automotive | Auto Infotainment | a0D3A00000OKjQx | IstariAU | APQ8096AU | Shanghai |  |  | PMM8996AU | Other |  | Third Party | Third Party | None | QCA6564AU-1 | QCA6574AU-1 | TBD/Unknown |  | 9"+ | FHD (1920x1080) | TBD/Unknown | Linux Other |  | APQ8096AU.HGH.1.0 | SB4 | Updated the project name to reflect the project support scope. | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2017-12-15 | [10 empty] | 2019-07-31 | 2019-07-31 |  | Vivian Liu |  | 1 | 1 |  |  |  | * Currently one CNS3.0 8L board is in the Connectivity team Ingolstadt for BT/Wifi testing. | Harvey Huang | 2018-03-12 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-05-09 02:15:21Z | [11 empty] | Other |  |  | Automotive |  |  | China | Other | Other | None |  |  |  | No |  |  | Qualcomm | [29 empty] | Evaluation project: No need CPI audit | [281 empty] | TA
China | Yanfeng Visteon Electronics Technology (Shanghai) Co., Ltd. | 4-Silver |  |  | CNS3.0 |  | Automotive | Auto Infotainment | a0D3A00000OCjv8 | IstariAU | APQ8096AU | Shanghai |  |  | PMM8996AU | Other |  | Third Party | Third Party | Third Party | Other | Other | TBD/Unknown |  | 9"+ | FHD (1920x1080) |  | Android N |  | MSM8996AU.HQX.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-07-31 | 2019-07-31 |  | Dan Li |  | 1 | 1 | [91 empty] | ldan@qct.qualcomm.com ; 2018-05-02 05:08:48Z | [11 empty] | Other |  |  | Automotive |  |  | China | Other | Undecided | Third party (non-SiLab) |  |  |  | No |  |  | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [281 empty] | TA
China | Zhuhai EWPE Information Technology Inc. | 3-Gold |  |  | G4 |  | Wireless Device | SmartPhone | a0D3A00000ORU63 | Warlock | SDM710 | Shenzhen |  |  | PM670;PM670A | SDR660 |  | QET4101 | None | None | WCN3990 | WCN3990 BT | 6GB | 4000 | 6.3" |  | 12M | Android P |  | SDM710.LA.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-12-18 | 2019-03-31 | 2019-05-31 | [8 empty] | 2019-07-31 | 2019-07-31 |  | Bruce Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Training; Concept review; Kickoff meeting; Requirement Review; Schedule review; SW architecture review |  |  | * [HW]P0 HW design is ongoing; * [SW]EVB test board debugging ongoing and no critical issue reported from customer this week. | Bruce Wang | 2018-12-16 | [85 empty] | wbruce@qct.qualcomm.com ; 2018-08-09 06:48:52Z | [11 empty] | WCD9335 |  |  | Mobile | Direct OEM Support |  | China |  | Other | WCN |  |  | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | [29 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty |  | 2018-12-01 Column56: EVT | [59 empty] | DVT | [60 empty] | PVT | [60 empty] | TA
China | CK Telecom (Heyuan) Limited | 3-Gold |  |  | D8050 |  | Wireless Device | SmartPhone | a0D3A00000OTAJ7 | Pukeena | QM215 | Shenzhen |  |  | PM215 | WTR2965 |  | QET4101 | Third Party | QAT3514 | WCN3660B | WCN3660 | 2GB | 2500 | 5.45" |  |  | Android P | MSM8909.LA.3.0 | MSM8909.LA.3.0 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | WE - Open Market | 2019-03-05 | 2019-04-12 | 2019-07-23 |  |  | 2019-07-30 | [5 empty] | 2019-08-28 | 2019-08-28 |  | Jiechu Gui | Karen Kwong | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Schematics Review; Layout Review; Qualification: CDG |  |  | * CKT the first QM125 project, target to Europe open marketing, just got the QC reference design file to begin SCH | Jiechu Gui | 2018-12-16 |  |  |  |  | jgui@qct.qualcomm.com ; 2015-08-21 00:56:13Z | [20 empty] | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning |  |  |  |  | Planning | [24 empty] | jgui@qct.qualcomm.com ; 2018-11-29 07:05:54Z | [11 empty] | Other |  |  | Mobile |  |  | Western Europe (WE) | Other | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B38 (TDD) | No |  | 2 Medium: Case by Case Support On Demand |  | SDRAM-LPDDR3 | [28 empty] | Evaluation project: No need CPI audit | [133 empty] | EVT | [37 empty] | DVT | [101 empty] | PVT | [35 empty] | TA
China | TCL | 2-Platinum |  |  | GoFlip3-TMO | TMO | Wireless Device | SmartPhone | a0D3A00000OTFX8 | Cheel | MSM8909 | Chengdu |  |  | PM8909 | WTR2965 |  | None | Third Party | None | WCN3610 | WCN3610 (BT) | 512MB | 2000 | 5" |  | 2M | KaiOS |  | MSM8905.LF.1.4 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | NA - T-Mobile (USA) | 2018-12-20 | 2019-02-20 | 2019-06-28 |  |  | 2019-06-12 | 2019-07-26 |  |  |  |  | 2019-08-30 | 2019-08-30 |  | Haijun Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * will KICK OFF | Haijun Wang | 2018-12-04 | [85 empty] | haijunw@qct.qualcomm.com ; 2018-12-05 02:44:39Z | [11 empty] | PM8909 |  |  | Mobile |  |  | North America (NA) | Other | Other | WCN |  | No | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty |  | 2018-12-01 Column58: EVT | [20 empty] | DVT | [127 empty] | PVT | [62 empty] | TA
China | Longcheer | 2-Platinum |  |  | SW901 |  | Wireless Device | IOT Kids watch | a0D3A00000OSvW9 | Cheel | MSM8909W | Shanghai |  |  | PMW3100 | WTR2965 |  | QET4101 | Third Party | None | WCN3620 | WCN3620 | 512MB |  |  |  |  | Android for Wearables (LAW) |  | MSM8909W.LAW.3.0.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-08-30 | 2019-08-30 |  | Andy Li |  | 1 | 1 |  |  |  | * Kid Watch for both Xiaoxun and Metoo (Xiaomi Ecosystem) brands * Wireless charging, dual camera (5MP+5MP), dual antenna, all mode | Andy Li | 2018-11-15 | [85 empty] | junjiel@qct.qualcomm.com ; 2018-11-15 08:18:55Z | [11 empty] | NA |  |  | IoT Wearable | Direct OEM Support |  | China |  | Other | None |  |  |  | No | [32 empty] | Mandatory Filed: Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [311 empty] | TA
China | MeiG Smart Technology Co., Ltd. | 3-Gold |  |  | MA800 | MA800 | Wireless Device | Telematics | a0D3A00000OSSJk | Lykan | MDM9628 | Xi'an |  |  | PMD9607 | WTR2965 |  | Third Party | Third Party | None | QCA6574A-1 | No BT | 256MB | 0 |  |  |  | Linux Other | MDM9607.LE.2.2-00060-STD.PROD-2 | MDM9607.LE.2.2 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2016-08-12 | 2016-10-12 | 2016-12-12 |  |  | 2016-11-01 | [5 empty] | 2019-08-30 | 2019-08-30 |  | Nicholas Chen |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * MeiG kicked off MDM9628 based module | Nicholas Chen | 2018-10-16 | [85 empty] | jic@qct.qualcomm.com ; 2018-10-16 09:12:59Z | [11 empty] | NA |  |  | Automotive |  |  | China; North America (NA) | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [311 empty] | TA
China | Zhejiang e-CarX Technology Co., Ltd. | 4-Silver |  |  | Geely DMA | NA | Automotive | Auto Infotainment | a0D3A00000OEn4E | IstariAU | APQ8096AU | Hangzhou |  |  | PMM8996AU | Other | Unknown | Third Party | Third Party | Third Party | QCA6574AU-1 | QCA6574AU-1 | TBD/Unknown |  |  |  |  | Android O |  | MSM8996AU.LA.1.2 | SB2 | S820A is key candidate for Geely’s new DMA platform, eCarX is Geely’s own invested infotainment and telematics supplier, potentially design frozen end of 2018, SOP 2019, life time volume 1.5Mu. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2020-06-30 | 2019-08-31 |  | Dan Li |  | 1 | 0 | [91 empty] | haoyuz@qct.qualcomm.com ; 2018-08-29 06:22:32Z | [11 empty] | NA |  |  | Automotive |  | NA |  | Other | Other | Third party (non-SiLab) |  |  |  | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [312 empty] | TA
China | BBK | 1-Diamond |  |  | ETD1816 (EXP1831) 8150 5G |  | Wireless Device | SmartPhone | a0D3A00000OH14z | Carrera | SDX50M + SM8150 | Shenzhen |  |  | PM8005 | Other |  | Third Party | QPM5650;QPM5651 | QAT3518;Third Party | WCN3998 | WCN3998 | 6GB | 3500 |  |  | 12M+5M | Android O | SM8150.LA.1.5 + SDX50M.TN.2.0 ES | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB3 | BBK 8150 1st 5G project; | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-10-10 | 2018-12-31 | 2019-05-30 | [8 empty] | 2019-09-01 | 2019-09-01 |  | Hui Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Marketing member visited vivo on 12/12 to clarify Sub6/mmw future SW/feature plan while vivo think CS delay impact their evaluation process. * Several stability or RF performance issue under tracking. vivo moved to 11/30 Pre-CS2.3 and more testing work is ongoing. | Hui Zhang | 2018-12-16 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-10-11 08:19:11Z | [5 empty] | Staffed/In progress | 2016-07-11 | 2016-07-11 |  | weitaol@qct.qualcomm.com ; 2016-08-18 18:39:15Z |  |  |  |  | eugeniac@qct.qualcomm.com ; 2016-04-07 17:03:21Z |  |  |  |  | eugeniac@qct.qualcomm.com ; 2016-04-07 17:03:21Z | Staffed/In progress | 2016-07-11 | 2016-08-11 |  | zhanghui@qct.qualcomm.com ; 2018-03-29 23:41:10Z | Planning | 2016-08-14 | 2016-08-14 |  | zhanghui@qct.qualcomm.com ; 2018-03-29 23:41:10Z |  | 2017-10-08 | 2017-10-08 |  | zhanghui@qct.qualcomm.com ; 2018-03-29 23:41:10Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-11-12 07:54:50Z | [19 empty] | eugeniac@qct.qualcomm.com ; 2016-04-07 17:03:21Z | Planning | 2016-02-20 |  |  | zhanghui@qct.qualcomm.com ; 2015-10-25 23:40:44Z | zhanghui@qct.qualcomm.com ; 2018-12-03 06:10:53Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B4 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0; C1900 BC1 | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR4X | [28 empty] | Evaluation project: No need CPI audit |  | 2018-12-01 Column69: DVT | [119 empty] | PVT | [93 empty] | TA
China | OPPO | 1-Diamond |  |  | AD090 |  | Wireless Device | SmartPhone | a0D3A00000OTMyH | Starlord | SDM660 | Shenzhen |  |  | PM660;PM660A | SDR660 |  | QET4101 | Third Party | Third Party | WCN3980 | WCN3980 BT | >4GB | 3000 |  |  |  | Android P | SDM660.LA.3.0-30092-STD.PROD-1 | SDM660.LA.3.0 | SB4 | * OPPO cooperates with Japan operator Rakuten Mobile | Existing design to a different carrier |  | Design/Development | Japan – Rakuten Mobile | 2019-03-20 | 2019-04-25 | 2019-05-30 |  | 2019-03-25 | [6 empty] | 2019-09-05 | 2019-09-05 |  | Hongbo Chen | Lianfeng Li | 1 | 1 |  |  |  | *It is a refresh project (Hardware) based on CPH1893 (R17 Neo) | Hongbo Chen | 2018-12-13 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [45 empty] | Staffed/In progress | 2017-02-17 | [33 empty] | hongboc@qct.qualcomm.com ; 2018-12-17 07:04:03Z | [11 empty] | NA |  |  | Mobile |  |  | Japan | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B26 (FDD); B28 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | LPDDR4 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty | [148 empty] | EVT | [35 empty] | DVT | [34 empty] | PVT | [97 empty] | TA
China | MeiG Smart Technology Co., Ltd. | 3-Gold |  |  | SLM758W |  | Wireless Device | IOT Smart Assistant | a0D3A00000OZkaI | Jacala | SDM450 | Shanghai |  |  | PM8953;PMI632 | WTR2965 |  | None | Third Party | None | WCN3680B | WCN3680B | 2GB |  | 5" |  | 13M | Android P |  | SDM450.LA.3.2.1 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | NA - Open Market | [11 empty] | 2019-09-10 | 2019-09-10 |  | Baoming Zhang |  | 1 | 1 | Access to documentation granted; Access to Case granted |  |  | * SDM450 Module Project for Smart Devices. * General case support | Baoming Zhang | 2018-12-16 | [85 empty] | baomingz@qct.qualcomm.com ; 2018-12-17 03:46:45Z | [11 empty] | NA |  |  | IoT Smart-Cities |  |  | North America (NA) | NA | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B34 (TDD); B39 (TDD) | No |  | 3 Low: No Need For QTI Support | Customer | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [322 empty] | TA
China | Fuzhou Wisbo Information Technology Co., Ltd. | 4-Silver |  |  | Wisbo_8909-AC018_update |  | Wireless Device | IOT Smart POS | a0D3A00000Oek7H | Cheel | MSM8909 | XiaMen |  |  | PM8909 | WTR4605 |  | Third Party | Third Party | Third Party | No WLAN | No BT | 1GB |  | 5" |  | 500W | Android N |  | MSM8909.LA.3.0 | SB4 |  | MR - Updated OS |  | Design/Development | China - Open Market | 2015-09-10 | 2015-11-15 | 2016-01-04 |  |  | 2015-10-22 | [5 empty] | 2019-09-16 | 2019-09-16 |  | Jiuyao Shu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Wisbo POS project in Xiamen *Base project is Wisbo_8909-AC018(All Modes). | Jiuyao Shu | 2018-12-01 |  |  |  |  | sfranco@qct.qualcomm.com ; 2016-11-02 18:35:54Z | [80 empty] | jshu@qct.qualcomm.com ; 2018-07-31 07:24:48Z | [11 empty] | PM8909 |  |  | IoT Smart-Cities | Direct OEM Support |  | China | Other | Other | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B4 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | [30 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [328 empty] | TA
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | RogueOne_robot |  | Wireless Device | IOT Robots | a0D3A00000OSzIv | Jacala | APQ8053 | Beijing |  |  | Other;PM8953 | None |  | None | None | None | QCA9379-7 | QCA9379-7 | 1GB | 0 | 5" |  | None | Android O | APQ8053.LE.1.5 | APQ8053.LE.1.5 | SB4 |  | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2015-12-30 | 2016-01-31 | 2016-03-30 | [8 empty] | 2019-09-17 | 2019-09-17 |  | Tianhao Fei |  | 1 | 1 |  |  |  | Robot ODM project, Navi board of kind of Home monitor robot | Tianhao Fei | 2018-11-19 | [40 empty] | Staffed/In progress | 2016-07-29 |  |  |  | Staffed/In progress | 2016-07-29 |  |  |  | Staffed/In progress | 2016-07-21 | [33 empty] | tfei@qct.qualcomm.com ; 2018-12-18 03:43:39Z | [11 empty] | PM8953 |  |  | IoT Robotics | Direct OEM Support |  | China | Integrated | No NFC | None |  | TDD/FDD | B3 (FDD); B5 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [329 empty] | TA
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | IVI-A1701 | N/A | Wireless Device | Auto Infotainment | a0D3A00000OCp6q | IstariAU | APQ8096AU | Shenzhen |  |  | PMM8996AU | RGR7640AU |  | None | None | None | QCA6564AU-3 | QCA6564AU-3 | 4GB | 0 | 12.8" | FHD (1920x1080) | 13M | Android O | APQ8096AU.HQX.1.0 | APQ8096AU.HQX.1.0 | SB3 | BYD IVI+Cluster 820A project BYD auto 2019 shipment plan | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | 2018-10-15 | 2018-01-10 | 2019-04-18 | [8 empty] | 2019-10-20 | 2019-09-30 |  | Tianhao Fei |  | 1 | 1 |  |  |  | VI+ Cluster, APQ8096AU.HQX.1.0 is designed for BYD requirement. FC release will be generated by Jan. IVI+Cluster+HUD + DVR+3D surround. HQX bring up on P0. Display, TP, audio issue in case support. APA, DMS and Face ID evaluation on SNPE testing environment. It plan to demo on CES 2019. Demo SW will generate before Dec 18th. First TA plan on Q3 end 2019 | Tianhao Fei | 2018-12-16 | [85 empty] | tfei@qct.qualcomm.com ; 2018-09-17 12:46:21Z | [11 empty] | WCD9335 |  |  | Automotive |  |  | China | Other | No NFC | WCN |  | No |  | No |  | 2 Medium: Case by Case Support On Demand | Qualcomm | SDRAM-LPDDR4 | [28 empty] | Strongly Requested Filed: LTE Supported Bands : Empty CDMA Supported Bands : Empty | [177 empty] | PVT | [164 empty] | TA
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | AM9628 |  | Wireless Device | Telematics | a0D3A00000OTKir | Lykan | MDM9628 | Beijing |  |  | PMD9607 | WTR2965 |  | None | Third Party | None | No WLAN | No BT | 256MB |  |  |  |  | Linux Other | MDM9607.LE.2.0.1 | MDM9607.LE.2.0.1 | SB3 | BYD in-house 4G Telematics modue, use with 820A IVI project. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2019-09-30 | 2019-09-30 |  | Tianhao Fei |  | 1 | 1 |  |  |  | DM9628 Telematics 4G module. It will be used with SD820A (IVI-A1701) project. Precise position application in evaluation. It needs PdM confirm to support on PL. P0 in HW design, and plan be back on Jan 15. TA plan align with 820A, target Q3 2019. | Tianhao Fei | 2018-12-16 | [85 empty] | tfei@qct.qualcomm.com ; 2018-12-11 07:08:36Z | [11 empty] | Other |  |  | Automotive |  |  | China | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B8 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [342 empty] | TA
China | CloudMinds (Shenzhen) Holdings Co., Ltd | 4-Silver |  |  | A3H |  | Wireless Device | SmartPhone | a0D3A00000OSgRU | Hana | SM8150 | Beijing |  |  | PM8150;PM8150B;PM8150L | SDR8150 |  | QET5100 | QPA2625;QPA8842;QPM4621;QPM4630;QPM4640 | QAT3516 | WCN3998 | WCN3998 | 4GB | 4510 | 5.7inch |  | 12M | Android P |  | SM8150.LA.1.0 | SB4 | SM8150 project for RED. | Parent CP for Original design (OEM) |  | Evaluation | NA - AT&T Wireless | 2019-02-25 | 2019-04-26 | 2019-08-29 | 2019-06-21 | [7 empty] | 2019-09-30 | 2019-09-30 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * CloudMinds' SM8150 project for RED in AT&T. * Next generation of RED Hydrogen One. * CM requests camX source code. | Huize Wang | 2018-12-23 | [85 empty] | huizew@qct.qualcomm.com ; 2018-10-31 06:45:34Z | [11 empty] | WCD9341 |  |  | Mobile | Direct OEM Support |  | North America (NA) | WSA8815 x2 (Stereo) | SN100U | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B18 (FDD); B19 (FDD); B20 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD); B29 (FDD); B30 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer |  |  | 3D camera | [26 empty] | Evaluation project: No need CPI audit | [125 empty] | EVT | [59 empty] | DVT | [124 empty] | PVT | [31 empty] | TA
China | OPPO | 1-Diamond |  |  | X55 Evaluation |  | Wireless Device | SmartPhone | a0D3A00000OTNBh | Huracan | SM8150P + SDX55M | Shenzhen |  |  | PM8009;PM8150;PMX55 | QTM525 (x2);SDR865;SMR526 |  | QET5100 | QPM4650;QPM8870 | QAT3516;QAT5515 | WCN3998 | WCN3998 | >4GB |  | 5.5" |  | 16MP+20MP | Android P |  | [SM8150.LA.1.5 + SDX50M.TN.2.0] | SB4 | OnePlus 1st 5G project | Parent CP for Original design (OEM) |  | Evaluation | WE-EE (UK) | 2018-08-06 | 2019-02-05 | 2019-03-09 | [8 empty] | 2019-10-01 | 2019-10-01 |  | Zhiyang Gao | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Training |  |  | *Evaluation | Zhiyang Gao | 2018-12-17 |  |  |  |  | qiw@qct.qualcomm.com ; 2015-12-29 22:30:15Z | [5 empty] | Staffed/In progress | [5 empty] | 2018-08-05 | [34 empty] | 2018-01-04 | [33 empty] | zhiyangg@qct.qualcomm.com ; 2018-12-17 11:19:10Z | [11 empty] | WCD9341 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B5 (FDD); B8 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | LPDDR4 | [28 empty] | Evaluation project: No need CPI audit | [105 empty] | DVT | [31 empty] | PVT | [205 empty] | TA
China | Huizhou BYD Electronic Co., Ltd. | 3-Gold |  |  | KC_Kids_phone |  | Wireless Device | SmartPhone | a0D3A00000OSi48 | Cheel | MSM8909 | Beijing |  |  | PM8916 | WTR2965 |  | None | Third Party | None | WCN3680B | WCN3980 BT | 3GB | 0 | 5" |  |  | Android O | MSM8909.LA.3.0.1 | MSM8909.LA.3.0.1 | SB4 | Kyocera ODM | ODM or partner CP associated with an indirect account |  | Design/Development | Japan - Open Market | 2015-12-30 | 2016-01-31 | 2016-03-30 | [8 empty] | 2019-10-17 | 2019-10-17 |  | Tianhao Fei |  | 1 | 1 |  |  |  | yocera ODM project | Tianhao Fei | 2018-10-31 | [40 empty] | Staffed/In progress | 2016-07-29 |  |  |  | Staffed/In progress | 2016-07-29 |  |  |  | Staffed/In progress | 2016-07-21 | [33 empty] | tfei@qct.qualcomm.com ; 2018-11-01 06:35:26Z | [11 empty] | PM8916 |  |  | Mobile |  |  | Japan | Integrated | Other | WCN |  | TDD/FDD | B3 (FDD); B5 (FDD); B7 (FDD); B20 (FDD); B38 (TDD); B39 (TDD); B40 (TDD) | No |  |  |  | SDRAM-LPDDR3 | [28 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty | [359 empty] | TA
China | GoerTek Inc. | 4-Silver |  |  | Wukong (former SHE) |  | Wireless Device | Wearable | a0D3A00000OCbX7 | Cheel | MSM8909W | Beijing |  |  | PM8916-1 | WTR2965 |  | QFE2101 | Third Party | None | WCN3610 | WCN3610 (BT) | 1GB |  | 1.39" |  |  | Android N |  | MSM8909W.LAW.2.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | China - China Unicom (CU) | [11 empty] | 2019-10-29 | 2019-10-29 |  | Huize Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Training |  |  | * smart watch with Paceware brand * Paceware will restart the project. The new name is Wukong. * meeting with Paceware to discuss their HW design changes. | Huize Wang | 2018-12-23 | [85 empty] | huizew@qct.qualcomm.com ; 2018-12-17 03:38:23Z | [11 empty] | PM8916 |  |  | IoT Wearable | Direct OEM Support | SKY77645-11+SKY77912-61 | China | Other | Other | None |  | TDD/FDD | B3 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [371 empty] | TA
China | Thundercomm Technology Co., Ltd. | 4-Silver |  |  | JV_QCS605_Santiago |  | Wireless Device | IOT Enterprise IP Security Camera | a0D3A00000OGrNh | RedDragon | QCS605 | Beijing |  |  | PM670;PM670L | Other |  | None | None | None | WCN3990 | WCN3990 BT | TBD/Unknown |  |  |  |  | Android O |  | QCS605.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Design/Development | Japan - Open Market | 2018-03-29 | 2018-11-30 | 2019-03-15 | [8 empty] | 2019-10-30 | 2019-10-30 |  | Jiuyao Shu | Andrew Poh | 1 | 1 |  |  |  | *TC project for Nikon. * PL: Laijinhe 15600036081 * EVT is ready. it is in EVT2 stage. * Feasibility-Phase1 has been done, starting Phase2. * Focus on Nikon's algorithm upgrading | Jiuyao Shu | 2018-12-23 | [85 empty] | jshu@qct.qualcomm.com ; 2018-09-10 06:42:35Z | [11 empty] | WCD9340 |  |  | IoT Connected Camera | Transparent OEM Support |  | Eastern Europe (EE); Rest of World (ROW); Western Europe (WE) | Other | Undecided | WCN |  |  |  | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-11-01 Column38: DVT | [43 empty] | PVT | [228 empty] | TA
China | Sierra Wireless, Inc. | 3-Gold |  |  | OCU4_9x40_V2 |  | Wireless Device | Telematics | a0D3A00000OFTOV | Tesla | MDM9640 | Shenzhen | MDM9640-1 |  | PMD9645 | WTR3925;WTR4905 |  | Third Party | Third Party | Third Party | Other | Other | TBD/Unknown |  |  |  |  | Linux Other | MDM9640.LE.3.1-00132-STD.PROD-1 | MDM9640.LE.3.1 | SB4 | * OCU4 project. Spin off of their AR759x design which is also based on MDM9x40. | Parent CP for Original design (OEM) |  | Design/Development | WE - Open Market | [5 empty] | 2019-04-30 | [5 empty] | 2019-10-31 | 2019-10-31 |  | Raj Pratha | Raj Pratha | 1 | 1 | [91 empty] | junok@qct.qualcomm.com ; 2017-04-04 00:14:12Z | [11 empty] | WCD9304 |  |  | Automotive |  |  | Western Europe (WE) | Other | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [373 empty] | TA
China | BBK | 1-Diamond |  |  | PD1824_5G (SDX55） |  | Wireless Device | SmartPhone | a0D3A00000OZoij | Huracan | SM8150P + SDX55M | Shenzhen |  |  | PM8150A;PM8150B | Other |  | None | Third Party | None | WCN3998 | WCN3998 | 6GB | 4000 |  |  | 12M+5M | Android P |  | SM8150.LA.1.0 | SB4 | BBK 1st SM8150p+SDX55 5G project; ,big volume forecast. | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2019-04-01 | 2019-06-01 | 2019-08-01 | [8 empty] | 2019-11-01 | 2019-11-01 |  | Hui Zhang | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted; Developer's Conference; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Early evaluation. | Hui Zhang | 2018-12-21 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-08-04 23:36:52Z | [20 empty] | Staffed/In progress | 2016-07-11 | [13 empty] | Staffed/In progress | 2016-07-11 |  |  |  | Planning | 2016-08-14 |  |  |  |  | 2017-10-08 | [28 empty] | Planning | 2016-02-20 |  |  |  | zhanghui@qct.qualcomm.com ; 2018-12-21 08:50:27Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B2 (FDD); B4 (FDD); B7 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 1 High: Full QTI Support Required | Qualcomm | SDRAM-LPDDR4X | [28 empty] | Evaluation project: No need CPI audit | [160 empty] | EVT | [60 empty] | DVT | [60 empty] | PVT | [91 empty] | TA
China | Xiaomi | 1-Diamond |  |  | Xiaomi wearable evaluation |  | IOT | Wearable | a0D3A00000OSnT8 | Cheel | MSM8909W | Beijing |  |  | PM8916-1;PMW3100 | WTR2955;WTR2965 |  | None;QET4101 | None | None;QFE2550 | No WLAN | Integrated | <128MB | 0 | NO Display |  |  | Android Wear (LW) |  | MSM8909W.LW.4.0 | SB4 | Xiaomi Wearable under evaluation. | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2018-11-14 | 2018-11-14 | 2018-11-14 | 2018-11-14 |  | 2018-11-14 | [5 empty] | 2019-11-07 | 2019-11-07 |  | Guowei Qin |  | 1 | 1 |  |  |  | *Xiaomi wearable under evaluaiton, will be kickoff in Jan, and target launch in Nov.2019; *The projects will be based on WearOS, Longcheer is the HW ODM for Xiaomi; *Initial spec and features has been discussed during SD product team visiting; *SDW2500 Reference board provided to Xiaomi; * Xiaomi request the algrithem accuricy comparision data, Music play in sport mode and feature list for different mode; | Guowei Qin | 2018-12-16 |  |  |  |  | c_vingut@qct.qualcomm.com ; 2017-02-01 14:34:31Z | [80 empty] | gqin@qct.qualcomm.com ; 2018-11-14 03:34:31Z | [11 empty] | Other |  |  | IoT Wearable | Direct OEM Support |  | China | Other | No NFC | None |  | FDD | B1 (FDD); B2 (FDD); B3 (FDD); B4 (FDD); B12 (FDD); B13 (FDD); B17 (FDD); B19 (FDD); B26 (FDD); B39 (TDD) | No | [32 empty] | Evaluation project: No need CPI audit |  | 2018-11-01 Column22: PVT | [280 empty] | TA
China | Wingtech | 2-Platinum |  |  | M6 | 8848 | Wireless Device | SmartPhone | a0D3A00000OTGsv | Huracan | SDX55 | Shanghai |  |  | PMX55 | SDR865 |  | None | Third Party | None | WCN3998 | WCN3998 | 4GB | 3000 | 5.5 |  | 13M | Android P |  | SM8150.LA.1.0 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | China - Open Market | 2017-07-07 | 2017-09-19 | 2017-10-30 | [8 empty] | 2019-11-22 | 2019-11-22 |  | Tian Zhou |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Training; Concept review; Kickoff meeting; Schematics Review |  |  | * Bring up ongoing, now mainly focus on Camera/RF feature o Upgrading to 11/14 release, will use it for CTA o Dual-camera didn't work, help with SR03743949 o RF bring up nearly finished o Some modem issues are under debugging o Build fail with CamerX code, under checking | Tian Zhou | 2018-12-06 |  |  |  |  | tzhou@qct.qualcomm.com ; 2015-08-17 22:33:01Z | [15 empty] | Staffed/In progress | [64 empty] | tzhou@qct.qualcomm.com ; 2018-12-06 08:30:17Z | [11 empty] | WCD9340 |  |  | Mobile |  |  | China | WSA8815 x2 (Stereo) | No NFC | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B9 (FDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No |  | 2 Medium: Case by Case Support On Demand | Customer | [29 empty] | Evaluation project: No need CPI audit | [395 empty] | TA
China | ZTE | 1-Diamond |  |  | GH820 | TBD | Wireless Device | SmartPhone | a0D3A00000OGrPA | Jacala | MSM8953 | Shenzhen |  |  | Other | Other |  | QFE2101 | QPA4361 | Third Party | WCN3615 | WCN3615 | 4GB | 3000 |  |  | 13MP | Android N | TBD | MSM8953.LA.2.0 | SB4 |  | Updated design |  | Design/Development | China - Open Market | 2018-08-30 | 2018-12-10 | 2019-03-15 | 2018-09-22 | [7 empty] | 2018-11-14 | 2019-11-30 |  | Xiangkui Liu | Lianfeng Li | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted |  |  | * (6.0"/FHD, 64+4GB, for Europe and Asia and china market target to launch end of Oct,2019) * EVT phase, Change the chipset SPEC from 14x14 to 14x12 * Finished the 1st board bring up, and some RF performation still on debugging. . * Currently still on debuig antenna performance an related factory tools development. * The 2nd board plan tape out in 1/10, then enter P1 phase. | Xiangkui Liu | 2018-12-23 |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-09-02 00:16:33Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-10-11 08:11:00Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-10-11 08:11:00Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2015-10-11 08:11:00Z |  |  |  |  | zhanghui@qct.qualcomm.com ; 2016-04-19 02:37:13Z | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2015-10-11 08:11:00Z | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2015-10-11 08:11:00Z | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2015-10-11 08:11:00Z |  |  |  |  | htan@qct.qualcomm.com ; 2016-10-21 07:34:28Z |  | 2017-07-21 | 2017-07-21 |  | htan@qct.qualcomm.com ; 2016-10-21 07:34:28Z |  |  |  |  | xiangkui@qct.qualcomm.com ; 2018-02-02 23:53:00Z | Planning |  |  |  | xiangkui@qct.qualcomm.com ; 2018-02-02 23:53:00Z | [15 empty] | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2016-04-19 02:37:13Z | Planning |  |  |  | zhanghui@qct.qualcomm.com ; 2016-04-19 02:37:13Z | xiangkui@qct.qualcomm.com ; 2018-08-27 03:07:46Z | [11 empty] | PM8953 |  |  | Mobile |  |  | China | Other | Other | WCN |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | Rev A | C850 BC0 | 2 Medium: Case by Case Support On Demand | Customer |  |  | [CCB Note: [7/26/2018]. 8953 project, support case by case] |  |  |  | [7/26/2018 | [22 empty] | Mandatory Filed: RF Chipset is Other; Strongly Requested Filed: Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column48: DVT | [43 empty] | PVT | [259 empty] | TA
China | Quectel | 2-Platinum |  |  | EG50 |  | Wireless Device | Embedded Module | a0D3A00000OTJuu | Huracan | SDX55 | Shanghai |  |  | PMK8002;PMX55 | SDR865 |  | QET5100;QET6100 | QPM5621;QPM5670;QPM5677;QPM5679 | None | No WLAN | No BT | 512MB |  |  |  |  | Linux Other |  | SDX55.LE.1.0 | SB2 | Global leading SDX55 MBB Module product. First application can be in a Home gateway/Router to Telstra w/ sub6. | Parent CP for Original design (OEM) |  | Design/Development | ROW - Open Market | 2019-03-04 | 2019-08-05 | 2019-11-18 | [8 empty] | 2019-12-30 | 2019-12-30 |  | Li Wang |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | * Quectel First SDX55 module for PC M.2 and Router. * Kicked off as CPE Module (Sub-6 only) to Technicolor/Telstra in with interconnection via PCIE 2.0 * SDX55 PK approved and Quectel is invited to join SDX55 Shanghai training session end-Dec . * Ref SCH to be published and shared to Quectel * Dell/HP M.2 PC module RFQ Q&A ongoing. | Li Wang | 2018-12-17 | [85 empty] | liw@qct.qualcomm.com ; 2018-12-13 08:22:13Z | [11 empty] | NA |  |  | Mobile |  |  | Rest of World (ROW) | NA | No NFC | None |  | No | B1 (FDD); B2 (FDD); B3 (FDD); B5 (FDD); B7 (FDD); B8 (FDD); B20 (FDD); B21 (FDD); B22 (FDD); B23 (FDD); B24 (FDD); B25 (FDD); B26 (FDD); B27 (FDD); B28 (FDD); B34 (TDD); B38 (TDD); B39 (TDD); B40 (TDD); B41 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [132 empty] | EVT | [153 empty] | DVT | [104 empty] | PVT | [41 empty] | TA
China | Quectel | 2-Platinum |  |  | AG52 |  | Automotive | Telematics + C-V2X | a0D3A00000OTAIs | Chiron | SDX24 | Shanghai |  |  | PMX24 | Other |  | Third Party | Third Party | Third Party | Other | No BT | 256MB |  |  |  |  | Linux Other |  | SDX24.LE.1.0 | SB4 | Leading MDM9150 project | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2019-01-31 | 2019-06-28 | 2019-08-30 | [8 empty] | 2019-12-31 | 2019-12-31 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  |  | Vivian Liu | 2018-12-12 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-12-12 08:52:13Z | [11 empty] | NA |  |  | Automotive |  | SDR8150 | China | NA | No NFC | None |  | TDD/FDD | B1 (FDD); B3 (FDD); B5 (FDD); B8 (FDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [100 empty] | EVT | [147 empty] | DVT | [62 empty] | PVT | [122 empty] | TA
China | SAIC MOTOR COMMERCIAL VEHICLE CO.,LTD | 4-Silver |  |  | iBox1.0 |  | Automotive | C-V2X | a0D3A00000OSx8s | McLaren | MDM9150 | Shanghai |  |  | PMD9655 | WTR5975 |  | Third Party | Third Party | None | Other | Other | 256MB |  |  |  |  | Linux Other |  | MDM9150.LE.1.0 | SB3 | Leading MDM9150 project | Parent CP for Original design (OEM) | AG15 | Design/Development | China - Open Market | 2018-09-17 | 2018-12-24 | 2019-04-29 |  |  | 2019-04-15 | [5 empty] | 2019-12-31 | 2019-12-31 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  | ocus on 9150 SDK integration support on customer's AP | Vivian Liu | 2018-11-16 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-12-18 11:08:17Z | [11 empty] | NA |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD | B42 (TDD); B43 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column62: DVT | [88 empty] | PVT | [245 empty] | TA
China | Continental Automotive Systems | 3-Gold |  |  | Didi_D01 |  | Automotive | Auto Infotainment | a0D3A00000OeMa8 | IstariAU | APQ8096AU | Beijing |  |  | None | Other |  | Third Party | Third Party | None | QCA6564AU-1 | QCA6564AU-1 | TBD/Unknown |  | 9"+ |  | TBD/Unknown | Android O |  | MSM8996AU.LA.1.2 | SB4 | Updated the project name to reflect the project support scope. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2020-02-28 | 2020-02-28 |  | Vivian Liu |  | 1 | 1 |  |  |  | he project was officially awarded by Didi in May, 2018, SOC is SA6155 and OS is Android. Current SoC Chip in system is still selected as APQ8096AU since SA6155 is not active in SF. Will update once it's available. | Vivian Liu | 2018-10-25 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-11-30 09:17:24Z | [11 empty] | Other |  |  | Automotive |  |  | China | Other | Other | None |  |  |  | No |  |  | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [493 empty] | TA
China | ArcherMind Technology (Nanjing) Co., Ltd. | 4-Silver |  |  | ArcherMind_S820A_QDP |  | Automotive | Auto Infotainment | a0D3A00000ODpto | IstariAU | APQ8096AU | Nanjing |  |  | PM8996 | Other |  | Third Party | Third Party | Third Party | QCA6574AU-1 | QCA6574A-1 | TBD/Unknown |  | 9"+ |  | TBD/unknown | Android N |  | APQ8096AU.HQX.1.0 | SB4 | It's used for ArcherMind who worked as QDP to support our S820A Customers. | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | [11 empty] | 2020-04-10 | 2020-04-10 |  | Vivian Liu |  | 1 | 1 | [91 empty] | wenjuanl@qct.qualcomm.com ; 2018-12-06 11:37:00Z | [11 empty] | Other |  |  | Automotive |  |  | China | Other | Undecided | Third party (non-SiLab) |  |  |  | No |  |  | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [535 empty] | TA
China | ThunderSoft | 2-Platinum |  |  | TS_S820A_QDP | NA | Automotive | Auto Infotainment | a0D3A00000ODptj | IstariAU | APQ8096AU | Shenzhen |  |  | Other | Other |  | None | None | None | QCA6574AU-1 | QCA6574AU-1 | TBD/Unknown |  | TBD |  | TBD | Linux Other |  | APQ8096AU.HQX.1.0 | SB4 | It's used for SF who worked as QDP to support our S820A Customers. | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | [11 empty] | 2020-04-10 | 2020-04-10 |  | Vivian Liu |  | 0 | 0 | [91 empty] | wenjuanl@qct.qualcomm.com ; 2018-05-10 08:42:17Z | [11 empty] | NA |  |  | Automotive |  | NA | China | Other | Other | Third party (non-SiLab) |  |  |  | No | [32 empty] | Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty | [535 empty] | TA
China | Hubei Ecarx Technology Co., Ltd. | 4-Silver |  |  | Geely 5DA |  | Automotive | Auto Infotainment | a0D3A00000OTC4K | IstariAU | APQ8096AU | Hangzhou |  |  | PMM8996AU | Other |  | Third Party | Third Party | Third Party | QCA6574AU-1 | QCA6574AU-1 | 4GB |  |  |  |  | Android P |  | APQ8096AU.LA.1.3 | SB3 | S820A is key candidate for Geely’s new DMA platform, eCarX is Geely’s own invested infotainment and telematics supplier. This is the earliest 820A project for eCarX. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2020-04-29 | 2020-04-29 |  | Dan Li |  | 1 | 1 |  |  |  | ey milestones: E2: Nov 20th, 2018 (Basic function) E3: Apr 20th, 2019 (Full function) E4: Sep 18th, 2019 (SW SOP) SOP: Apr 29th, 2020 | Dan Li | 2018-11-30 | [85 empty] | ldan@qct.qualcomm.com ; 2018-12-03 05:43:45Z | [11 empty] | Other |  |  | Automotive |  |  |  |  | Other | Third party (non-SiLab) |  |  |  | No | [32 empty] | Mandatory Filed: Target Region : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty | [554 empty] | TA
China | Taobao (China) Software Co., Ltd. | 4-Silver |  |  | Ali SNPE Evaluation |  | Automotive | Auto Infotainment | a0D3A00000OdjcM | IstariAU | APQ8096AU |  |  |  | PMM8996AU | None |  | None | None | None | No WLAN | No BT | TBD/Unknown |  |  |  |  | Linux Other |  | MSM8996AU.LV.0.1 | SB4 |  | Parent CP for Original design (OEM) |  | Evaluation | [12 empty] | 2020-05-30 | 2020-05-30 |  | Dan Li |  | 1 | 1 | [91 empty] | ldan@qct.qualcomm.com ; 2018-05-28 06:15:18Z | [11 empty] | NA |  |  | Automotive |  |  |  |  | No NFC | None |  |  |  | No | [32 empty] | Evaluation project: No need CPI audit | [585 empty] | TA
China | Quectel | 2-Platinum |  |  | AG36 |  | Automotive | Telematics | a0D3A00000OSx9H | Tesla | MDM9640 | Shanghai |  |  | PMD9645 | WTR3925 |  | Third Party | Third Party | None | Other | No BT | 256MB |  |  |  |  | Linux Other |  | MDM9640.LE.3.2 | SB4 | Leading MDM9150 project | ODM or partner CP associated with an indirect account |  | Design/Development | China - Open Market | 2018-09-17 | 2018-12-24 | 2019-04-29 |  |  | 2019-04-15 | [5 empty] | 2020-06-30 | 2020-06-30 |  | Vivian Liu |  | 1 | 1 | Access to documentation granted; Access to Case granted; Access to Software granted; Access to tools granted |  |  |  | Vivian Liu | 2018-12-17 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-11-16 10:02:09Z | [11 empty] | NA |  |  | Automotive |  |  | China | NA | No NFC | None |  | TDD/FDD | B42 (TDD); B43 (TDD) | No | [32 empty] | Strongly Requested Filed: Device Official Name : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty |  | 2018-12-01 Column62: DVT | [88 empty] | PVT
China | Yanfeng Visteon Electronics Technology (Shanghai) Co., Ltd. | 4-Silver |  |  | Geely PMA Smartcore |  | Automotive | Auto Infotainment | a0D3A00000OdTI7 | IstariAU | APQ8096AU | Hangzhou |  |  | PMM8996AU | Other |  | None | None | Third Party | Other | Other | 6GB |  |  |  |  | QNX |  | APQ8096AU.HQX.1.0 | SB3 | Geely is the fastest growing and biggest China domestic auto OEM. Geely has awarded their PMA infotainment project to YF-Visteon, lifetime volume 1.54 Million units. | Parent CP for Original design (OEM) |  | Design/Development | [12 empty] | 2020-10-31 | 2020-10-31 |  | Dan Li |  | 1 | 1 |  |  |  | igh level schedule: DVT: 2019 March PVT: 2020 Jan SOP : Oct. 2020 | Dan Li | 2018-05-07 | [85 empty] | ldan@qct.qualcomm.com ; 2018-05-07 09:55:33Z | [11 empty] | Other |  |  | Automotive |  |  |  |  | Other | SiLab |  |  |  | No | [32 empty] | Mandatory Filed: Operator1 : Empty Target Region : Empty Speaker Amplifier IC : Empty Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty
China | Hubei Ecarx Technology Co., Ltd. | 4-Silver |  |  | Geely DMA EX11 | NA | Automotive | Auto Infotainment | a0D3A00000OTC45 | IstariAU | APQ8096AU | Hangzhou |  |  | PMM8996AU | Other |  | Third Party | Third Party | Third Party | QCA6574AU-1 | QCA6574AU-1 | 6GB |  |  |  |  | Android P |  | APQ8096AU.LA.1.3 | SB2 | S820A is key candidate for Geely’s new DMA platform, eCarX is Geely’s own invested infotainment and telematics supplier. The project will SOP in 2020, life time volume 1.0Mu. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2020-11-13 | 2020-11-13 |  | Dan Li |  | 1 | 1 |  |  |  | X11 Key milestones: E3: Apr 17th, 2019 (Full function) E3U: Aug 7th , 2019 E4: Oct 23rd, 2019 (SW SOP) SOP: Nov 13th , 2020 | Dan Li | 2018-11-30 | [85 empty] | ldan@qct.qualcomm.com ; 2018-11-30 10:16:14Z | [11 empty] | Other |  |  | Automotive |  | NA |  | Other | Other | Third party (non-SiLab) |  |  |  | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty
China | Hubei Ecarx Technology Co., Ltd. | 4-Silver |  |  | Geely DMA KX11 | NA | Automotive | Auto Infotainment | a0D3A00000OTC4A | IstariAU | APQ8096AU | Hangzhou |  |  | PMM8996AU | Other |  | Third Party | Third Party | Third Party | QCA6574AU-1 | QCA6574AU-1 | 6GB |  |  |  |  | Android P |  | APQ8096AU.LA.1.3 | SB2 | S820A is key candidate for Geely’s new DMA platform, eCarX is Geely’s own invested infotainment and telematics supplier. The project will SOP in 2020, life time volume 1.0Mu. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2020-12-04 | 2020-12-04 |  | Dan Li |  | 1 | 1 |  |  |  | X11 Key milestones: E3: Mar 13th , 2019 (Full function) E4-1: Nov 13th , 2019 E4-2: Feb 5th , 2020 (SW SOP) SOP: Dec 4th , 2020 | Dan Li | 2018-11-30 | [85 empty] | ldan@qct.qualcomm.com ; 2018-11-30 10:21:09Z | [11 empty] | Other |  |  | Automotive |  | NA |  | Other | Other | Third party (non-SiLab) |  |  |  | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty
China | ZongMu Technology (Shanghai) Co., Ltd | 4-Silver |  |  | ZM_S820A_ADAS | NA | Automotive | Auto Infotainment | a0D3A00000NBzZV | IstariAU | APQ8096AU | Beijing |  |  | PMM8996AU | Other | Unknown | Third Party | Third Party | Third Party | No WLAN | Undecided | TBD/Unknown |  |  |  |  | Android M |  | APQ8096AU.LV.4.0 | SB5 |  | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2021-12-31 | 2021-12-31 |  | Dan Li |  | 1 | 1 | [91 empty] | weiweih@qct.qualcomm.com ; 2018-10-26 06:54:59Z | [11 empty] | NA |  |  | Automotive |  | NA |  | Other | Undecided | Third party (non-SiLab) |  |  |  | No | [32 empty] | Mandatory Filed: Target Region : Empty Strongly Requested Filed: LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty Display Physical Size (inches) : Empty RAM Type/technology : Empty
China | Pan Asia Technical Automotive Center Co., Ltd. | 4-Silver |  |  | PATAC Info 4.0 |  | Automotive | Auto Infotainment | a0D3A00000ORXHD | HanaAU | SA8155P | Shanghai |  |  | PMM8155AU | Other |  | Third Party | Third Party | None | Other | Other | TBD/Unknown |  | 9"+ |  | TBD/Unknown | Android O |  | SA8155P.LA.0.1 | SB3 | Shanghai GM/Pan Asia is key customer for auto business, we will provide local support to Pan Asia to support our global Info4.0 business with GM. | Parent CP for Original design (OEM) |  | Design/Development | China - Open Market | [11 empty] | 2022-02-28 | 2022-02-28 |  | Vivian Liu |  | 1 | 1 |  |  |  |  | Vivian Liu | 2018-11-28 | [85 empty] | wenjuanl@qct.qualcomm.com ; 2018-11-29 04:49:58Z | [11 empty] | NA |  |  | Automotive |  |  | China | Other | Other | None |  |  |  | No |  |  | Qualcomm | [29 empty] | Strongly Requested Filed: Device Official Name : Empty LTE Capability : Empty LTE Supported Bands : Empty CDMA Supported Bands : Empty RAM Type/technology : Empty